## Summary
PSS 2.0 — DEVELOPMENT ESTIMATION PLAN
Remaining scope to production go-live — grouped into 5 workstreams. Prepared for client review.
Workstream | Items | Dev h | QA/Verify h | Total h | Effort (days)
1. Business Modules | 34 | 227 | 105.5 | 332.5 | 55.5
2. Volunteer & Membership | 8 | 112 | 39 | 151 | 25
3. AI Features | 13 | 228 | 71 | 299 | 50
4. System, Roles & Platform | 44 | 518 | 199 | 717 | 119.5
5. Client Onboarding, Comms & Leads | 10 | 142 | 48 | 190 | 31.5
6. Engineering & Platform Foundations | 37 | 518 | 125 | 643 | 107
GRAND TOTAL | 146 | 1745 | 587.5 | 2332.5 | 389
PM contingency (15%) |  |  |  | 349.875 | 58.5
PLANNED TOTAL (with buffer) |  |  |  | 2682.375 | 447
DELIVERY TIMELINE (planned days ÷ team, at ~21 working days/month)
Team size | Person-days | Elapsed working days | Elapsed calendar (months) | Note
1 | 447 | 447 | 21.3 | Single AI-assisted senior dev (as estimated)
2 | 447 | 223.5 | 10.6 | One dev + one dev/QA in parallel
3 | 447 | 149 | 7.1 | Small squad (2 dev + 1 QA), most parallelisable
INDICATIVE COST (enter your blended day-rate in the yellow cell)
Blended day-rate (per person-day) | 0 | ← enter rate
Planned effort (person-days) | 447
Indicative project cost | 0
ASSUMPTIONS & BASIS OF ESTIMATE
1. Estimates are for ONE senior developer working AI-assisted (average prompting skill). Dev hours already include prompt iteration and reviewing/fixing AI output.
2. QA / Verify hours are separate and cover business-flow testing, defect fixing and UAT support.
3. 1 productive day = 6 focused hours. Days are rounded to the nearest 0.5.
4. A 15% PM contingency is added at the summary level for meetings, revisions, integration surprises and UAT rework.
5. Complexity: S ≤ 1 day, M ≈ 1–3 days, L ≈ 3–5 days, XL ≈ 5+ days of build. Priority: P1 = go-live critical, P2 = important, P3 = post-launch.
6. This plan covers REMAINING scope only. The separate production-readiness / code-audit estimation (335 findings) is tracked in its own workbook and is NOT included here to avoid double-counting.
7. Third-party costs (payment-gateway, SMS/WhatsApp, AI API usage, blob storage, email) are pass-through and NOT included in the effort above.
8. Timeline assumes requirements are stable and environments/credentials are available on time; scope changes are handled via change request.

## 1. Business Modules
PSS 2.0 — 1. Business Modules
Core fundraising & delivery modules to complete, integrate and business-test: Contacts, Donations, Grants, Case Management, Communication, Dashboards, Events.
# | Group | Work Item | Detail | Cx | Pri | Dev h | QA h | Total h | Days
1 | Contacts | Contact Import | Re-test end-to-end and harden — field mapping, dedupe on import, error-row report, large-file handling. | M | P2 | 5 | 2.5 | 7.5 | 1
2 | Contacts | Family | Re-test relationships, primary contact and merge behaviour. | S | P2 | 2.5 | 2 | 4.5 | 1
3 | Contacts | Duplicate Detection | Re-test match rules, merge and survivorship. | M | P2 | 3 | 2 | 5 | 1
4 | Contacts | Certificate Processing | Re-test generation, print and template binding. | S | P2 | 3 | 2 | 5 | 1
5 | Donations | Multi-currency completion | Finish contact-level currency + every amount surface (grids, tiles, receipts, drawers) still showing raw/base amounts. | L | P1 | 9.5 | 3.5 | 13 | 2
6 | Donations | Currency conversion coverage | Apply direct-pair FX consistently across dashboards, reports and reconciliations. | M | P1 | 7 | 3 | 10 | 1.5
7 | Donations | Currency decimal formatting | Standardise precision, grouping and symbol placement from the currency master. | S | P2 | 3.5 | 2 | 5.5 | 1
8 | Donations | Pledge lifecycle | Complete and verify schedule, partial payments, fulfilment, reminders, ageing and write-off. | L | P1 | 7 | 3 | 10 | 1.5
9 | Donations | Bulk Donation Upload | Complete & re-test template, validation, partial-failure handling and import receipting. | M | P2 | 5 | 2.5 | 7.5 | 1
10 | Donations | Donation / payment reconciliation | Matching, unmatched queue and matching against the real gateway settlement feed. | L | P1 | 9.5 | 3.5 | 13 | 2
11 | Donations | Refund flow | End-to-end approval, gateway reversal, receipt void and ledger reversal. | M | P1 | 6 | 2.5 | 8.5 | 1.5
12 | Donations | Matching-Gift | Complete screen + employer-match workflow (directory, ratio, claim, reconciliation). | M | P2 | 6 | 2.5 | 8.5 | 1.5
13 | Donations | Ambassador module | Full business-flow testing: collection, book master, allocations (allocation → collection → reconciliation). | M | P2 | 3.5 | 5 | 8.5 | 1.5
14 | Donations | Receipt & tax-certificate issuance | First-class flow: per-tenant number series, country tax format (80G), PDF, re-issue/void, annual consolidated receipts. | XL | P1 | 12 | 3.5 | 15.5 | 2.5
15 | Donations | Donation acknowledgement automation | Auto thank-you on receipt, tiered by amount and first-time vs repeat donor. | S | P2 | 3.5 | 2 | 5.5 | 1
16 | Donations | Recurring / subscription engine | Auto-charge schedule, failed-card retry, dunning, expiry/renewal, pause/cancel (distinct from pledges). | XL | P1 | 14.5 | 5 | 19.5 | 3
17 | Donations | Restricted / designated funds | Donor-restricted fund balances, allocation/release and over-spend guard so Grant/Case movements reconcile. | XL | P1 | 12 | 3.5 | 15.5 | 2.5
18 | Grants | Grant full business testing | Application → communication → fund collection → utilisation → reports, end to end. | M | P1 | 3.5 | 6 | 9.5 | 1.5
19 | Grants | Grant creation-flow fix | Enforce full intake (funder, award-letter evidence, budget lines) before advancing; route stage changes through proper approve/activate handlers. | L | P1 | 7 | 3 | 10 | 1.5
20 | Grants | Grant communication wiring | Compose-from-template funder emails + silent internal notifications + grant communication audit tab. | M | P1 | 5 | 2.5 | 7.5 | 1
21 | Case Management | Case full business retest | Program → fund request → allocation → publish → enrolment → case → service delivery. | M | P1 | 3.5 | 5 | 8.5 | 1.5
22 | Case Management | Case approval gating | Gate assistance and fund steps behind the approval process. | M | P1 | 3.5 | 2 | 5.5 | 1
23 | Case Management | Outcome & impact tracking | Beneficiary/case outcome metrics, before/after, funder-reportable. | L | P2 | 8.5 | 3 | 11.5 | 2
24 | Communication | SMS & WhatsApp real service | End-to-end provider account, send, delivery-status webhooks and templates (not just screens). | L | P1 | 12 | 5 | 17 | 3
25 | Communication | In-app notification service | Produce/deliver/read-state/bell UI, raised from key domain events across modules. | L | P1 | 9.5 | 3.5 | 13 | 2
26 | Communication | Prayer Request & reply service | Submission, moderation, reply dispatch and notification. | M | P2 | 5 | 2.5 | 7.5 | 1
27 | Communication | Contextual send actions | Email/SMS/WhatsApp directly from Event and Case screens. | M | P2 | 5 | 2 | 7 | 1
28 | Communication | Social-media communication | Channel account config + post/share/publish for Event, Case, etc. | M | P2 | 7 | 3 | 10 | 1.5
29 | Communication | Preference & unsubscribe centre | Per-channel/category opt-in-out, one-click unsubscribe, DND/DLT compliance. | M | P1 | 6 | 2.5 | 8.5 | 1.5
30 | Dashboards | All-module dashboards | Build missing, finish partial and bind widgets to live data across every module. | XL | P1 | 14.5 | 5 | 19.5 | 3
31 | Events | Events full-flow retest | Setup → registration → ticketing → check-in → analytics. | M | P2 | 3 | 2.5 | 5.5 | 1
32 | Events | Ticketing / registration / check-in | Paid/free tiers, QR check-in, capacity, waitlist. | L | P2 | 12 | 3.5 | 15.5 | 2.5
33 | Events | Event Auction commission | Commission calculation, payouts, settlement and reporting. | L | P2 | 7 | 2.5 | 9.5 | 1.5
34 | Events | Staff creation & role assignment | Re-test invite, role bind and capability take-effect. | S | P1 | 2.5 | 2 | 4.5 | 1
TOTAL — 34 items | [5 empty] | 227 | 105.5 | 332.5 | 55.5

## 2. Volunteer & Membership
PSS 2.0 — 2. Volunteer & Membership
Volunteer and Membership module completion, self-service portals, and cross-module volunteer service integration.
# | Group | Work Item | Detail | Cx | Pri | Dev h | QA h | Total h | Days
1 | Volunteer | Volunteer module completion | Public registration, profiles/roles, service allocations, working-hours monitoring; reconcile built screens vs scope. | L | P1 | 16 | 6 | 22 | 3.5
2 | Volunteer | Volunteer portal | Self-service hour tracking, availabilities, detail collection with hour approval. | L | P1 | 20 | 6 | 26 | 4.5
3 | Volunteer | Volunteer service integration | Cross-module volunteer picker into Event, P2P Fundraising and Case Management. | M | P2 | 12 | 5 | 17 | 3
4 | Membership | Membership module completion | Plan tiers, renewal, benefits; reconcile built screens vs scope. | L | P1 | 14 | 5 | 19 | 3
5 | Membership | Membership portal | Self-service join, renew and manage. | L | P2 | 16 | 5 | 21 | 3.5
6 | Membership | Renewal reminders & lapse | Wire renewal reminders and lapse handling into the notification service. | S | P2 | 6 | 3 | 9 | 1.5
7 | Engagement | Campaign / appeal management | Goal, thermometer, channel attribution, cost, ROI tying donations/events/P2P/crowdfunding to a parent campaign. | L | P2 | 16 | 5 | 21 | 3.5
8 | Engagement | Segmentation & saved lists | Dynamic donor segments feeding communication, exports and campaigns. | M | P2 | 12 | 4 | 16 | 2.5
TOTAL — 8 items | [5 empty] | 112 | 39 | 151 | 25

## 3. AI Features
PSS 2.0 — 3. AI Features
Application-wide AI capability build-out — platform service, predictive models, assistants and governance.
# | Group | Work Item | Detail | Cx | Pri | Dev h | QA h | Total h | Days
1 | AI Platform | AI service + fallback | Central AI gateway with provider fallback, ret/timeout, per-tenant keys. | L | P1 | 16 | 5 | 21 | 3.5
2 | AI Platform | AI utilisation tracking | Per-tenant usage metering, token/cost logging and quota surfacing. | M | P2 | 8 | 3 | 11 | 2
3 | AI Platform | AI governance | Prompt/PII redaction before send, per-tenant cost caps, output audit log, human-in-the-loop review. | L | P1 | 16 | 5 | 21 | 3.5
4 | Predictive | Engagement-score prediction | Donor/volunteer engagement scoring model + surfacing on records. | L | P2 | 16 | 5 | 21 | 3.5
5 | Predictive | Churn prediction | Lapse/churn-risk scoring with drivers and worklist. | L | P2 | 16 | 5 | 21 | 3.5
6 | Predictive | Donation / revenue forecasting | Goal-pacing and forecast at campaign and org level. | L | P2 | 20 | 6 | 26 | 4.5
7 | Predictive | Next-best-action & ask-amount | Per-donor recommendation (segmentation + propensity). | L | P2 | 20 | 6 | 26 | 4.5
8 | Predictive | Anomaly / fraud detection | Unusual amount, velocity and card-testing detection on donations/refunds. | L | P1 | 20 | 6 | 26 | 4.5
9 | Assistants | AI chatbot — Ask your data | NL query over tenant data with guardrails, tenant scoping and cited results. | XL | P1 | 30 | 8 | 38 | 6.5
10 | Assistants | Generative content assistant | Draft thank-you/campaign/grant-report/email copy from context with tone/length controls. | L | P2 | 16 | 5 | 21 | 3.5
11 | Assistants | Duplicate/merge suggestions | AI-assisted contact dedupe augmenting rule-based detection. | M | P2 | 12 | 4 | 16 | 2.5
12 | Intelligence | Document / receipt OCR | Scan cheque/receipt/ID into structured fields for offline donation and KYC capture. | XL | P2 | 24 | 8 | 32 | 5.5
13 | Intelligence | Sentiment & topic analysis | On inbound communication, prayer requests and feedback. | M | P3 | 14 | 5 | 19 | 3
TOTAL — 13 items | [5 empty] | 228 | 71 | 299 | 50

## 4. System, Roles & Platform
PSS 2.0 — 4. System, Roles & Platform
Platform configuration, roles/security, cross-cutting services, finance/reporting plumbing, integrations and release-readiness.
# | Group | Work Item | Detail | Cx | Pri | Dev h | QA h | Total h | Days
1 | Config & Roles | Role config & screen setup | Test roles, capabilities, menu access, widgets; confirm capability→menu→widget wiring per role. | M | P1 | 6 | 8 | 14 | 2.5
2 | Config & Roles | Grid configuration | Revisit grids, fields, layouts, custom fields, filters, columns; confirm per-grid integrity. | M | P1 | 6 | 6 | 12 | 2
3 | Config & Roles | Master Data & Type | Complete & re-test; verify type→data relationship and usage. | M | P2 | 8 | 4 | 12 | 2
4 | Config & Roles | Payment gateway & account config | Per-company gateway and bank-account configuration screen. | L | P1 | 12 | 5 | 17 | 3
5 | Config & Roles | Comms account config | WhatsApp/SMS/Email credentials, sender, test-send. | M | P1 | 10 | 4 | 14 | 2.5
6 | Config & Roles | Template approval flow | WhatsApp and SMS template approval workflow. | M | P2 | 8 | 3 | 11 | 2
7 | Config & Roles | Dashboard & widgets config | Layout, widget catalog, role binding. | M | P2 | 10 | 4 | 14 | 2.5
8 | Config & Roles | Settings hierarchy config | Setting-Group + Organization-Setting + User-Setting inheritance/override precedence. | M | P2 | 8 | 4 | 12 | 2
9 | Config & Roles | Automation-workflow config | Condition-based communication/job creation engine. | L | P2 | 20 | 6 | 26 | 4.5
10 | Config & Roles | Approver settings & approval process | Config-driven approval chains, wired into every module + central approval inbox. | XL | P1 | 24 | 8 | 32 | 5.5
11 | Platform Services | Grids import/toggle cleanup | Remove Import action + show/hide toggle from grids that don't need them. | S | P2 | 4 | 2 | 6 | 1
12 | Platform Services | Timezone handling | Store UTC, display org/user timezone across all dates, filters and reports. | L | P1 | 14 | 6 | 20 | 3.5
13 | Platform Services | Global audit trail | Who-changed-what-when with before/after, surfaced in UI, retention policy. | L | P1 | 16 | 6 | 22 | 3.5
14 | Platform Services | Document/file storage | Secure private blob (upload/download/virus-scan) unblocking grant attachments & KYC. | L | P1 | 16 | 5 | 21 | 3.5
15 | Platform Services | Global search | Across contacts, donations, cases, grants, etc. | M | P2 | 12 | 4 | 16 | 2.5
16 | Platform Services | Background-job monitoring | Queue health, retries, dead-letter, manual re-run for messaging/imports. | M | P2 | 12 | 4 | 16 | 2.5
17 | Platform Services | Tenant branding / white-label | Logo, colours, sender name, custom domain, email footer. | M | P2 | 12 | 4 | 16 | 2.5
18 | Platform Services | Module entitlement per tenant | Turn modules on/off, plan-gated features. | M | P2 | 12 | 4 | 16 | 2.5
19 | Platform Services | Reusable import framework | Validation, error report, partial-commit, rollback, mapping templates. | M | P2 | 12 | 5 | 17 | 3
20 | Platform Services | Health & observability | Health checks, error monitoring/alerting, structured logging, uptime. | M | P1 | 10 | 4 | 14 | 2.5
21 | Platform Services | Data-retention & purge engine | Per-entity/per-tenant archival and purge, compliance-driven. | M | P3 | 12 | 4 | 16 | 2.5
22 | Security & Compliance | Authentication hardening | MFA/2FA, SSO/OAuth, password policy, lockout, session timeout, concurrent-session control. | L | P1 | 20 | 6 | 26 | 4.5
23 | Security & Compliance | Data-privacy / DSAR | GDPR/DPDP export, erasure/anonymise, consent ledger, processing records. | L | P1 | 16 | 5 | 21 | 3.5
24 | Security & Compliance | PII field-level protection | Encryption at rest for sensitive fields, UI/log masking, PCI scope at gateway iframe. | M | P1 | 12 | 5 | 17 | 3
25 | Security & Compliance | Role/permission security review | Server-side authz on every mutation, tenant-isolation tests, IDOR checks. | M | P1 | 12 | 6 | 18 | 3
26 | Finance & Accounting | Tax integration | Tax config, computation at donation/receipt time, tax receipts and reports. | L | P1 | 12 | 5 | 17 | 3
27 | Finance & Accounting | Gateway settlement reconciliation | Match payout report to donations, fees, unsettled/disputed states. | M | P1 | 12 | 4 | 16 | 2.5
28 | Finance & Accounting | GL / accounting export | Tally/QuickBooks/Xero/CSV with chart-of-accounts and fund-dimension mapping. | L | P2 | 16 | 5 | 21 | 3.5
29 | Finance & Accounting | Financial & statutory reports | FCRA/annual return, fund-utilisation, receipts/donation registers. | M | P2 | 12 | 4 | 16 | 2.5
30 | Finance & Accounting | Multi-currency settlement & FX g/l | FX gain/loss at the ledger level. | M | P2 | 10 | 4 | 14 | 2.5
31 | Reporting | Standard report pack | Per-module reports (donations, donors, grants, cases, events, volunteers). | M | P2 | 14 | 4 | 18 | 3
32 | Reporting | Scheduled report delivery | Email report/export on a cadence to staff, funders, board. | M | P3 | 8 | 3 | 11 | 2
33 | Reporting | Export governance | Bulk-export permissions, watermarking, export audit. | S | P3 | 6 | 3 | 9 | 1.5
34 | Integrations | Public REST/webhook API | Per-tenant API keys; donate button, Zapier-style automation, CRM sync. | L | P2 | 16 | 5 | 21 | 3.5
35 | Integrations | Website embed / donate widget | OG-tagged public pages tying into external donation/crowdfund pages. | M | P2 | 10 | 4 | 14 | 2.5
36 | Integrations | Calendar / meeting integration | For events and volunteer scheduling. | M | P3 | 8 | 3 | 11 | 2
37 | Integrations | Accounting/CRM/marketing connectors | Connector framework + first connectors. | L | P3 | 16 | 5 | 21 | 3.5
38 | Release Readiness | Performance & load testing | Grids, bulk imports, report queries, concurrent tenants. | M | P1 | 10 | 4 | 14 | 2.5
39 | Release Readiness | Security testing | OWASP Top 10, dependency/CVE scan, pen-test pass. | M | P1 | 10 | 4 | 14 | 2.5
40 | Release Readiness | Accessibility & cross-browser | WCAG 2.1 AA + responsive verification. | M | P2 | 10 | 4 | 14 | 2.5
41 | Release Readiness | UAT scripts & regression suite | Per business flow + regression pack. | M | P1 | 12 | 6 | 18 | 3
42 | Release Readiness | Documentation set | Admin/user guides, API docs, data dictionary, runbooks. | M | P2 | 12 | 3 | 15 | 2.5
43 | Release Readiness | Backup / DR drill | Defined and tested RPO/RTO. | M | P1 | 8 | 3 | 11 | 2
44 | Release Readiness | Localization / i18n | Multi-language if serving multiple regions. | M | P3 | 12 | 4 | 16 | 2.5
TOTAL — 44 items | [5 empty] | 518 | 199 | 717 | 119.5

## 5. Client Onboarding, Comms & L
PSS 2.0 — 5. Client Onboarding, Comms & Leads
New-client acquisition and go-live: leads/prospect tracking, onboarding flow, client communications and data migration.
# | Group | Work Item | Detail | Cx | Pri | Dev h | QA h | Total h | Days
1 | Leads | Leads / prospect tracking | Lead capture, pipeline stages, owner assignment, follow-up tasks, activity log, convert-to-tenant. | XL | P1 | 24 | 8 | 32 | 5.5
2 | Leads | Lead source & attribution | Source tagging and marketing attribution on conversions. | M | P2 | 8 | 3 | 11 | 2
3 | Leads | Trial-to-paid conversion | Trial provisioning, conversion flow and plan assignment. | M | P1 | 12 | 4 | 16 | 2.5
4 | Onboarding | Guided onboarding wizard | Setup checklist: org profile → branding → users/roles → gateway → comms accounts → master data → go-live. | L | P1 | 20 | 6 | 26 | 4.5
5 | Onboarding | Onboarding progress & health | Per-client onboarding progress tracking and health score. | M | P2 | 10 | 4 | 14 | 2.5
6 | Onboarding | Legacy data-migration toolkit | Templates/validators for contacts, historical donations, receipts, pledges; dedupe on import + reconciliation report. | XL | P1 | 24 | 8 | 32 | 5.5
7 | Onboarding | Seed/demo dataset & sandbox | Demo data and sandbox environment for training and trials. | M | P2 | 10 | 3 | 13 | 2
8 | Onboarding | In-app guidance | Contextual help, tooltips, guided tours, help-centre links. | M | P2 | 12 | 4 | 16 | 2.5
9 | Onboarding | Environment & release management | Staging vs prod config, config promotion, per-tenant go-live cutover runbook. | M | P1 | 10 | 4 | 14 | 2.5
10 | Client Comms | Client communication sequences | Welcome, training invites, onboarding status updates, milestone nudges (staff-facing client lifecycle). | M | P2 | 12 | 4 | 16 | 2.5
TOTAL — 10 items | [5 empty] | 142 | 48 | 190 | 31.5

## 6. Engineering & Platform Found
PSS 2.0 — 6. Engineering & Platform Foundations
Enterprise developer-side / non-functional foundations that underpin every feature: DevOps & delivery, architecture services, data & persistence, observability, quality, security and frontend engineering. Distinct from the product features in tabs 1-5.
# | Group | Work Item | Detail | Cx | Pri | Dev h | QA h | Total h | Days
1 | DevOps & Delivery | CI/CD pipelines | Automated build, test, and multi-environment deploy (dev/staging/prod) with gated releases and rollback. | L | P1 | 24 | 4 | 28 | 4.5
2 | DevOps & Delivery | Infrastructure as Code | Terraform/Bicep for reproducible environment provisioning and drift control. | L | P1 | 20 | 3 | 23 | 4
3 | DevOps & Delivery | Containerization & orchestration | Docker images + App Service/Kubernetes deployment topology and scaling policy. | L | P1 | 16 | 3 | 19 | 3
4 | DevOps & Delivery | Secrets & config management | Key Vault, per-env config, secret rotation, no secrets in source. | M | P1 | 12 | 3 | 15 | 2.5
5 | DevOps & Delivery | Tenant provisioning automation | Automated create/seed/teardown/offboarding + data export per tenant. | L | P1 | 16 | 4 | 20 | 3.5
6 | Architecture & Services | Distributed caching (Redis) | Cache-aside for hot reads, invalidation strategy, per-tenant key scoping. | M | P1 | 14 | 3 | 17 | 3
7 | Architecture & Services | Message queue / event bus | Async messaging with outbox pattern, idempotency and dead-letter (infra under the job-monitor UI). | L | P1 | 24 | 5 | 29 | 5
8 | Architecture & Services | Background job scheduler | Hangfire/Quartz durable scheduler for recurring and deferred jobs. | M | P1 | 12 | 3 | 15 | 2.5
9 | Architecture & Services | Real-time infrastructure | SignalR/WebSocket for in-app notifications and live dashboard updates. | L | P2 | 16 | 4 | 20 | 3.5
10 | Architecture & Services | Resilience layer | Global exception handling, Polly retry/circuit-breaker, transient-fault handling. | M | P1 | 12 | 3 | 15 | 2.5
11 | Architecture & Services | API & GraphQL versioning | Schema governance, deprecation policy, backward compatibility. | M | P2 | 10 | 3 | 13 | 2
12 | Architecture & Services | Webhook delivery infra | Outbound webhook dispatch with retry, signing and dead-letter. | M | P2 | 10 | 3 | 13 | 2
13 | Architecture & Services | Email deliverability infra | SPF/DKIM/DMARC, bounce/complaint handling, sender reputation. | M | P1 | 10 | 3 | 13 | 2
14 | Data & Persistence | Search engine infra | Azure AI Search/Elasticsearch + indexing pipeline behind the global-search feature. | L | P2 | 20 | 5 | 25 | 4
15 | Data & Persistence | DB performance tuning | Indexing, query optimization, connection pooling, N+1 elimination. | M | P1 | 16 | 4 | 20 | 3.5
16 | Data & Persistence | Reporting read-model / ETL | Read models / materialized views so heavy reports don't hit the OLTP path. | L | P2 | 20 | 5 | 25 | 4
17 | Data & Persistence | Migration strategy & tooling | Repeatable EF migration process, seed framework, zero-downtime approach. | M | P1 | 10 | 3 | 13 | 2
18 | Data & Persistence | Optimistic concurrency rollout | Row-versioning / concurrency tokens across mutable entities. | M | P1 | 12 | 4 | 16 | 2.5
19 | Observability | Centralized structured logging | Serilog + correlation IDs + log aggregation/retention. | M | P1 | 10 | 2 | 12 | 2
20 | Observability | Distributed tracing & APM | OpenTelemetry / Application Insights end-to-end request tracing. | M | P1 | 12 | 3 | 15 | 2.5
21 | Observability | Metrics, alerting & SLOs | Uptime/error/latency metrics, dashboards and on-call alerting. | M | P1 | 10 | 3 | 13 | 2
22 | Quality Engineering | Automated test suites | Unit + integration coverage on critical paths with CI coverage gates. | XL | P1 | 30 | 6 | 36 | 6
23 | Quality Engineering | E2E test automation | Playwright automation for critical business flows in CI. | L | P1 | 20 | 5 | 25 | 4
24 | Quality Engineering | Test-data factories | Fixtures/builders and seeded test tenants for deterministic tests. | S | P2 | 8 | 2 | 10 | 1.5
25 | Quality Engineering | Code-quality gates | Lint, static analysis (SonarQube), PR checks and standards. | S | P2 | 8 | 2 | 10 | 1.5
26 | Security Engineering | Pipeline security scanning | SAST/DAST + dependency and secret scanning in CI. | M | P1 | 12 | 3 | 15 | 2.5
27 | Security Engineering | Rate limiting / WAF / DDoS | Throttling, WAF rules and DDoS protection at the edge. | M | P1 | 12 | 3 | 15 | 2.5
28 | Security Engineering | Security headers / CSP / CORS | Harden HTTP headers, content-security-policy and CORS. | S | P1 | 6 | 2 | 8 | 1.5
29 | Frontend Engineering | Design-system consolidation | Shared component library, tokens and pattern reuse across screens. | L | P2 | 20 | 4 | 24 | 4
30 | Frontend Engineering | FE performance & robustness | Code-splitting, bundle optimization, error boundaries, lazy loading. | M | P2 | 12 | 3 | 15 | 2.5
31 | Frontend Engineering | SSR/SEO & Core Web Vitals | Server rendering + SEO for public pages, performance budget. | M | P2 | 12 | 3 | 15 | 2.5
32 | Scale & Reliability | Azure Front Door setup | Global entry point / navigation: routing rules, origin groups, health probes, latency-based routing and regional failover. | L | P1 | 16 | 4 | 20 | 3.5
33 | Scale & Reliability | Front Door custom domains & TLS | Per-tenant / white-label custom-domain routing with managed TLS certificates and CNAME automation. | M | P1 | 12 | 3 | 15 | 2.5
34 | Scale & Reliability | Front Door WAF & rules engine | Edge WAF policy, DDoS protection and rules-engine navigation (path routing, redirects, header rewrite, edge caching). | M | P1 | 12 | 3 | 15 | 2.5
35 | Scale & Reliability | Horizontal scaling & CDN | Stateless services, distributed session store, CDN for static assets behind Front Door. | M | P2 | 12 | 3 | 15 | 2.5
36 | Scale & Reliability | Backup automation & PITR | Automated backups, point-in-time restore, geo-redundancy. | M | P1 | 10 | 3 | 13 | 2
37 | Scale & Reliability | Load & autoscaling architecture | Load-test-driven autoscaling rules and capacity planning. | M | P2 | 10 | 3 | 13 | 2
TOTAL — 37 items | [5 empty] | 518 | 125 | 643 | 107