## Summary
PSS 2.0 — DELIVERY PROGRESS MONITOR
Progress verified against live screen registry (build status). Effort shown as context — completed (git) and remaining (estimate) are NOT netted. Remaining = three bands: dev/build + dev-side testing + QA/UAT. Module-wise detail + git completed breakdown below.
130/216 |  | 54% |  | 1,164 h |  | 2,725 h
Web screens COMPLETE |  | Web screen % complete |  | Effort spent (git) |  | Effort remaining (est)
PROGRAMME AT A GLANCE
Web screens — completed / in-progress / not-built |  |  |  | 130 / 29 / 57 (of 216 buildable)
Mobile app — delivery status |  |  |  | Not started (0%) — screen development not begun for delivery
Remaining effort — dev/build + dev-side test + QA/UAT |  |  |  | 1,657 h + 497 h + 570 h = 2,725 h
Remaining go-live-critical effort (P1, incl. dev-test) |  |  |  | 1,442 h
Remaining work-packages (estimation items) |  |  |  | 141
Planned remaining incl. 15% PM buffer |  |  |  | 3,133 h ≈ 522 person-days
Indicative delivery @ 1 / 2 / 3 people |  |  |  | ≈ 24.9 mo / ≈ 12.4 mo / ≈ 8.3 mo
Excluded (separate infra owner): App Service / publish / CI-CD / provisioning |  |  |  | −105 h (5 items) — Azure Front Door retained
MODULE-WISE PROGRESS (verified by screen build-status)
Module | Category | Screens buildable | Done | In progress | Not built | Verified % complete | Completed h (git) | Remaining h (est) | Dev/build h (rem) | Dev-side test h (rem) | QA / UAT h (rem) | P1 rem (critical) | Status
Case Management † | Business | 10 | 10 | 0 | 0 | 80% | 71.4 | 30.1 | 15.5 | 4.6 | 10 | 16.1 | Near done
Fundraising & Donations | Business | 45 | 34 | 5 | 6 | 75.56% | 293.8 | 318.2 | 189 | 56.7 | 72.5 | 168.4 | Near done
Contacts | Business | 8 | 6 | 2 | 0 | 75% | 161.4 | 26.1 | 13.5 | 4 | 8.5 |  | Near done
Field Collection | Business | 13 | 9 | 1 | 3 | 69.23% | [6 empty] | Majority done
Certificate | Business | 3 | 2 | 0 | 1 | 66.67% | [6 empty] | Majority done
Prayer Request | Business | 3 | 2 | 1 | 0 | 66.67% | [6 empty] | Majority done
Reports & Dashboards | Business | 15 | 10 | 0 | 5 | 66.67% | 48.5 | 70.2 | 42.5 | 12.8 | 15 | 23.9 | Majority done
Communication | Business | 27 | 17 | 3 | 7 | 62.96% | 131.3 | 76.3 | 44.5 | 13.3 | 18.5 | 46.8 | Majority done
Events & Organization † | Business | 12 | 10 | 1 | 1 | 45% | 54.9 | 42.4 | 24.5 | 7.3 | 10.5 | 5.2 | In progress
Volunteer † | Business | 8 | 8 | 0 | 0 | 45% | 14.4 | 79.4 | 48 | 14.4 | 17 | 58.8 | In progress
Membership † | Business | 4 | 3 | 1 | 0 | 45% | 13.3 | 59.8 | 36 | 10.8 | 13 | 23.2 | In progress
Grants † | Business | 4 | 4 | 0 | 0 | 45% | 42.9 | 31.6 | 15.5 | 4.6 | 11.5 | 31.6 | In progress
System / Settings / Admin | Platform | 61 | 15 | 12 | 34 | 24.59% | 174.1 | 599.2 | 354 | 106.2 | 139 | 300.2 | Early
AI Intelligence | AI | 3 | 0 | 3 | 0 | 0% | 0.8 | 367.4 | 228 | 68.4 | 71 | 130.6 | Not started
Mobile App † | Mobile | — | — | — | — | 0% | [6 empty] | Not started
Client Onboarding, Comms & Leads | Growth | — | — | — | — |  |  | 232.6 | 142 | 42.6 | 48 | 147 | Not started
Engineering & Platform Foundations | Engineering | — | — | — | — |  |  | 791.2 | 504 | 151.2 | 136 | 490.6 | Not started
Cross-cutting / Shared | Shared | — | — | — | — |  | 156.7 | [5 empty] | Supporting
PROGRAMME TOTAL (web, excl. Mobile) |  | 216 | 130 | 29 | 57 | 53.52% | 1163.5 | 2724.6 | 1657 | 497.1 | 570.5 | 1442.5
† Delivery-lead verified completion — overrides registry build-flags: Events/Volunteer/Membership/Grants = 45% (functionally 40–50%), Case Management = 80%, Mobile = 0% (screen development not started). No module is treated as 100% (capped at 95%) — final hardening / business retest still pending. Programme-total 'Verified %' is screen-weighted across web modules. Remaining effort is THREE distinct bands: 'Dev/build h' = pure build (incl. AI prompt iteration & fixing, per estimate basis); 'Dev-side test h' = the SAME developer's own post-build test pass BEFORE QA — bulk-data insertion, cross-module testing, full business-flow self-verification and UX pain-point find-&-fix (new greenfield build, not a remap; sized at 30% of Dev/build); 'QA / UAT h' = the later independent QA / user-acceptance pass. The three sum to 'Remaining h'. P1 (critical) includes the dev-side test share of its build. Completed (git) and remaining (est) are shown side-by-side, never netted.
COMPLETED EFFORT — GIT MODULE BREAKDOWN (source: PSS-2.0-COMPLETED-HOURS-ACTUALS.xlsx)
1,801 non-merge commits (BE+FE), 21 Aug 2025 – 14 Jul 2026. Effort estimate, not timesheets. Same completed effort as the module table above, grouped by git module.
Git module | Commits | Completed h | % of completed
System / Access / Config | 263 | 174.1 | 14.96%
Contacts | 255 | 161.4 | 13.87%
Donations | 239 | 157.4 | 13.53%
Other / Shared | 243 | 156.7 | 13.47%
Communication | 204 | 131.3 | 11.28%
Campaigns / Crowdfund / P2P | 145 | 88.4 | 7.598%
Case & Program | 112 | 71.4 | 6.137%
Events & Auction | 83 | 54.9 | 4.719%
Reporting / Dashboard / Audit | 73 | 48.5 | 4.168%
Finance / Payment / Receipt | 74 | 45.5 | 3.911%
Grants | 62 | 42.9 | 3.687%
Volunteer | 22 | 14.4 | 1.238%
Membership | 20 | 13.3 | 1.143%
Pledge | 5 | 2.5 | 0.2149%
AI / AIDA | 1 | 0.8 | 0.06876%
TOTAL COMPLETED | 1801 | 1163.5 | 100%

## By Member
PSS 2.0 — EFFORT BY MEMBER (git-derived)
Per-member monthly burn (left) and module split (right). Source: PSS-2.0-COMPLETED-HOURS-ACTUALS.xlsx.
Karthick â€” 1189 commits Â· 207 active days Â· 737.8 est. hours
Month | Commits | Hours | Module | Commits | Hours
2025-09 | 87 | 39.8 | System / Access / Config | 162 | 107.6
2025-10 | 75 | 50.6 | Donations | 166 | 103.2
2025-11 | 83 | 57.5 | Other / Shared | 157 | 98.9
2025-12 | 73 | 53.3 | Contacts | 149 | 88.6
2026-01 | 65 | 43.6 | Communication | 135 | 80.1
2026-02 | 41 | 30.6 | Case & Program | 83 | 58.3
2026-03 | 98 | 54.8 | Campaigns / Crowdfund / P2P | 97 | 52.7
2026-04 | 163 | 89.8 | Events & Auction | 76 | 50.2
2026-05 | 219 | 132.7 | Finance / Payment / Receipt | 63 | 36.7
2026-06 | 169 | 117.1 | Grants | 37 | 24.6
2026-07 | 116 | 68.1 | Reporting / Dashboard / Audit | 39 | 22.7
|  |  | Volunteer | 12 | 7.4
|  |  | Membership | 7 | 3.6
|  |  | Pledge | 5 | 2.5
|  |  | AI / AIDA | 1 | 0.8
Kavinkumar Thirumalaisamy â€” 260 commits Â· 83 active days Â· 184.3 est. hours
Month | Commits | Hours | Module | Commits | Hours
2025-08 | 4 | 2.4 | System / Access / Config | 64 | 43
2025-09 | 7 | 4.7 | Contacts | 46 | 31.8
2025-11 | 43 | 31.5 | Other / Shared | 35 | 23.2
2025-12 | 36 | 25.4 | Communication | 27 | 19.5
2026-01 | 22 | 13.3 | Donations | 25 | 19
2026-02 | 16 | 10.4 | Reporting / Dashboard / Audit | 24 | 18.7
2026-03 | 29 | 21.9 | Campaigns / Crowdfund / P2P | 17 | 12.6
2026-04 | 65 | 46.8 | Volunteer | 10 | 7
2026-05 | 38 | 27.9 | Finance / Payment / Receipt | 7 | 5.8
|  |  | Events & Auction | 5 | 3.8
Saranya C â€” 251 commits Â· 91 active days Â· 179.9 est. hours
Month | Commits | Hours | Module | Commits | Hours
2025-11 | 24 | 13.9 | Contacts | 60 | 41.1
2025-12 | 52 | 34.8 | Donations | 47 | 34.5
2026-01 | 20 | 15.6 | Communication | 42 | 31.7
2026-02 | 33 | 24.9 | Other / Shared | 30 | 21.7
2026-03 | 23 | 16.8 | System / Access / Config | 30 | 20.1
2026-04 | 50 | 36.7 | Membership | 13 | 9.8
2026-05 | 33 | 25.2 | Case & Program | 10 | 7.5
2026-06 | 16 | 12 | Reporting / Dashboard / Audit | 9 | 6.7
|  |  | Finance / Payment / Receipt | 4 | 3
|  |  | Campaigns / Crowdfund / P2P | 4 | 2.9
|  |  | Events & Auction | 2 | 1
Shyam Prakash J â€” 54 commits Â· 12 active days Â· 39.7 est. hours
Month | Commits | Hours | Module | Commits | Hours
2026-06 | 54 | 39.7 | Campaigns / Crowdfund / P2P | 27 | 20.1
|  |  | Grants | 25 | 18.3
|  |  | Donations | 1 | 0.8
|  |  | Other / Shared | 1 | 0.4
Ganesh â€” 35 commits Â· 10 active days Â· 14.7 est. hours
Month | Commits | Hours | Module | Commits | Hours
2025-10 | 7 | 3.8 | Other / Shared | 10 | 6.6
2025-11 | 6 | 4.1 | Case & Program | 19 | 5.7
2026-06 | 22 | 6.8 | System / Access / Config | 5 | 2.1
|  |  | Reporting / Dashboard / Audit | 1 | 0.4
Divya S â€” 7 commits Â· 5 active days Â· 4.8 est. hours
Month | Commits | Hours | Module | Commits | Hours
2025-08 | 2 | 1.5 | Other / Shared | 5 | 3.5
2025-10 | 4 | 2.5 | System / Access / Config | 2 | 1.3
2026-04 | 1 | 0.8
PW Data Solutions â€” 5 commits Â· 2 active days Â· 2.3 est. hours
Month | Commits | Hours | Module | Commits | Hours
2025-10 | 4 | 1.6 | Other / Shared | 5 | 2.3
2026-05 | 1 | 0.8

## Commit Detail
PSS 2.0 — COMMIT DETAIL (raw backing data, both repos)
Every non-merge commit behind the effort figures. Filter/sort to audit any number. Source: PSS-2.0-COMPLETED-HOURS-ACTUALS.xlsx.
Repo | Hash | Author | Date/Time | Primary module | Files | Insertions | Deletions | Message
BE | d8ca7831 | Divya S | 2025-08-21 10:12 | System / Access / Config | 1755 | 63556 | 0 | PSS Core: Initial Setup
FE | c825a316 | Divya S | 2025-08-22 10:06 | Other / Shared | 1522 | 73332 | 0 | chore: initial project setup
FE | 9314e1e7 | Kavinkumar Thirumalaisamy | 2025-08-25 17:58 | Other / Shared | 10 | 14 | 14 | chore: changes in ui for ess to pss
FE | 7fb9cedd | Kavinkumar Thirumalaisamy | 2025-08-26 15:56 | Reporting / Dashboard / Audit | 20 | 745 | 335 | fix: new login design changes
BE | f64fb209 | Kavinkumar Thirumalaisamy | 2025-08-29 17:16 | System / Access / Config | 33 | 13724 | 18 | Forgot Password Full implementation changes
BE | ef021942 | Kavinkumar Thirumalaisamy | 2025-08-29 17:26 | System / Access / Config | 1 | 1 | 1 | removed dupicate string
BE | 3f3f05c3 | Kavinkumar Thirumalaisamy | 2025-09-02 09:56 | System / Access / Config | 16 | 882 | 587 | changes in data seeding process
BE | a2142f3f | Kavinkumar Thirumalaisamy | 2025-09-03 17:11 | Communication | 9 | 51 | 59 | changes for fluent validation
BE | d4b3dc68 | Kavinkumar Thirumalaisamy | 2025-09-03 17:20 | System / Access / Config | 12 | 597 | 758 | dataseed old file comitted
BE | 98fe1067 | Kavinkumar Thirumalaisamy | 2025-09-08 11:13 | Contacts | 23 | 12761 | 1 | contact type screen implementation changes
BE | 09e0fa45 | Kavinkumar Thirumalaisamy | 2025-09-08 14:33 | Contacts | 19 | 5094 | 2 | incoming mode screen implementation changes
BE | 74505c31 | Kavinkumar Thirumalaisamy | 2025-09-09 09:54 | Contacts | 21 | 5242 | 2 | incoming sub mode implementation changes
BE | 540eb9f1 | Kavinkumar Thirumalaisamy | 2025-09-12 09:49 | Other / Shared | 3 | 33 | 4 | new changes of Ess to pss
BE | 99ab9d2f | Karthick | 2025-09-15 12:37 | Other / Shared | 4 | 41 | 44 | chore: mig name instruction
BE | f536f367 | Karthick | 2025-09-15 12:39 | Other / Shared | 1 | 0 | 5 | fix: instrcuction folder path changes
BE | e2180511 | Karthick | 2025-09-15 13:24 | Other / Shared | 4 | 57 | 2 | fix: instruction commit issue
BE | 6ed43cb5 | Karthick | 2025-09-15 13:28 | Other / Shared | 6 | 0 | 49 | fix: instruction files remove
BE | ad20ae8d | Karthick | 2025-09-15 13:43 | Other / Shared | 1 | 3 | 4 | fix: instruction changes
BE | 820196ab | Karthick | 2025-09-18 07:56 | Contacts | 21 | 0 | 0 | fix: folder name changes contactlevelbusiness to contactbusiness
BE | 91b8c57b | Karthick | 2025-09-18 18:08 | System / Access / Config | 67 | 755 | 717 | fix: file cleanup from menu , capability , menucapability and forgot password
BE | 954788dd | Karthick | 2025-09-18 18:17 | Contacts | 7 | 4465 | 72 | fix: contact schema change from pss to corg
BE | 2019136c | Karthick | 2025-09-18 18:21 | Other / Shared | 1 | 4 | 0 | fix: instruction folder files missing
BE | 417b4d65 | Karthick | 2025-09-18 18:25 | Other / Shared | 1 | 0 | 16 | fix: apigateway removed
BE | 94619e99 | Karthick | 2025-09-18 18:26 | Other / Shared | 1 | 0 | 11 | fix: unwanted folder revmoing
BE | 85663f2e | Karthick | 2025-09-18 18:46 | Other / Shared | 18 | 1 | 329 | fix: building blocks cleanup
BE | c6af5f8b | Karthick | 2025-09-18 19:17 | Events & Auction | 75 | 4395 | 827 | fix: removed all entity event handler and currency rate property added into currency entity
BE | 2841644d | Karthick | 2025-09-18 19:34 | Other / Shared | 8 | 4522 | 3 | fix: entity type configuration to language
BE | e0c0fbc8 | Karthick | 2025-09-18 19:46 | Other / Shared | 9 | 4456 | 6 | fix: added new property gender to relation entity
BE | 241b3274 | Karthick | 2025-09-18 19:52 | Contacts | 11 | 4506 | 69 | fix: sortorder property name change to incoming mode and sub mode
FE | 1b881808 | Karthick | 2025-09-19 05:34 | Other / Shared | 158 | 7 | 515 | fix: removed ess academic relevant pages and organism moved to custom component
BE | 1b6e2977 | Karthick | 2025-09-19 06:10 | System / Access / Config | 59 | 62 | 29 | fix: included ientitycollection to all entities
FE | 2416c6b7 | Karthick | 2025-09-19 06:25 | Other / Shared | 143 | 5 | 5 | fix: core service change to shared service
BE | a07aba15 | Karthick | 2025-09-19 08:48 | Finance / Payment / Receipt | 19 | 5157 | 3 | chore: currencyconversion with migration
FE | 2a3644ab | Karthick | 2025-09-19 08:51 | Finance / Payment / Receipt | 13 | 274 | 6 | chore: currency conversion screen
BE | 5d49b86b | Karthick | 2025-09-19 10:09 | Other / Shared | 18 | 5219 | 0 | chore: occupation entity with migration
FE | e8b043c2 | Karthick | 2025-09-19 10:10 | Other / Shared | 13 | 279 | 1 | chore: occupation screen
BE | bc1fb88d | Karthick | 2025-09-19 10:20 | Contacts | 4 | 5 | 14 | fix: automation command line included in contact db context
BE | 568fecc6 | Karthick | 2025-09-19 11:38 | Contacts | 3 | 7 | 70 | fix: include automation command line to dbcontext
BE | 138426eb | Karthick | 2025-09-19 11:38 | Contacts | 18 | 5015 | 240 | fix: refactor contact type entity and endpoints
FE | 08939383 | Karthick | 2025-09-19 11:41 | Contacts | 23 | 297 | 2 | chore: implement contact type screen
BE | 9f99bbd5 | Karthick | 2025-09-19 12:47 | Contacts | 20 | 5333 | 8 | feat(contact): add company and migration
FE | be547de4 | Karthick | 2025-09-19 12:47 | Contacts | 6 | 10 | 4 | fix: include automation command line to contact service
FE | ba344801 | Karthick | 2025-09-19 12:48 | Contacts | 15 | 308 | 1 | feat(contact): implement company screen
BE | 0888f203 | Karthick | 2025-09-19 12:57 | Contacts | 19 | 5375 | 1 | feat(contact): add branch entity and migration
FE | 24cab938 | Karthick | 2025-09-19 12:58 | Contacts | 13 | 281 | 1 | feat(contact): implement branch screen
BE | e38f4c75 | Karthick | 2025-09-19 13:57 | Contacts | 20 | 5448 | 0 | feat(contact): add company country and migration
FE | bc382df2 | Karthick | 2025-09-19 13:58 | Contacts | 13 | 283 | 1 | feat(contact): implement companycountry screen
BE | ee03ddd3 | Karthick | 2025-09-19 14:36 | Donations | 25 | 5518 | 13 | feat(donation): add donation category entity and migration
FE | e543fd66 | Karthick | 2025-09-19 14:37 | Donations | 21 | 299 | 0 | feat(donation): implement donation category screen
BE | 2fb1b716 | Karthick | 2025-09-19 15:14 | Donations | 18 | 5537 | 2 | feat(donation): add donation group entity and migration
FE | ac588328 | Karthick | 2025-09-19 15:15 | Donations | 13 | 279 | 0 | feat(donation): implement donation group screen
BE | 9203a2df | Karthick | 2025-09-20 06:54 | Donations | 20 | 5696 | 2 | feat(donation): add donation purpose entity and migration
FE | fe1ae759 | Karthick | 2025-09-20 06:55 | Donations | 13 | 336 | 0 | feat(donation): implement donation purpose screen
BE | a226b292 | Karthick | 2025-09-20 08:01 | Donations | 21 | 5758 | 1 | feat(donation): add company donation purpose entity and migration
FE | 4a2c527e | Karthick | 2025-09-20 08:03 | Donations | 13 | 284 | 2 | feat(donation): implement comany donation purpose screen
BE | f8e5c491 | Karthick | 2025-09-20 09:07 | Other / Shared | 19 | 5772 | 1 | feat(core): add salutation entity and migration
FE | 45060464 | Karthick | 2025-09-20 09:08 | Other / Shared | 13 | 269 | 0 | feat(core): implement salutation screen
BE | 4e19974e | Karthick | 2025-09-20 10:18 | Other / Shared | 18 | 5778 | 0 | feat(core): add pincode entity and migration
FE | b8ae3900 | Karthick | 2025-09-20 10:20 | Other / Shared | 14 | 256 | 0 | feat(core): implement pincode screen
FE | 2759f637 | Karthick | 2025-09-20 10:39 | Contacts | 13 | 261 | 2 | feat(contact): implement branch pincode screen
BE | 08723927 | Karthick | 2025-09-20 10:40 | Contacts | 20 | 5896 | 2 | feat(contact): add branch pincode and migration
BE | b55d35e6 | Karthick | 2025-09-20 11:30 | Contacts | 24 | 6238 | 7 | feat(contact): add family entity and migration
FE | f0acefce | Karthick | 2025-09-20 11:31 | Contacts | 15 | 377 | 1 | feat(contact): implement family screen
FE | 6c25882a | Karthick | 2025-09-20 12:07 | Contacts | 13 | 658 | 1 | feat(contact): implement contact screen
BE | 72140455 | Karthick | 2025-09-20 12:08 | Contacts | 29 | 6943 | 10 | feat(contact): add contact entity and migration
BE | 605ad45e | Karthick | 2025-09-20 12:28 | Contacts | 20 | 6562 | 0 | feat(contact): add contact phone number entity and migration
FE | 313f14cc | Karthick | 2025-09-20 12:30 | Contacts | 13 | 339 | 2 | feat(contact): implement contact phone number screen
BE | 10ba2a38 | Karthick | 2025-09-20 12:41 | Contacts | 20 | 6614 | 0 | feat(contact): add contact email address entity and migration
FE | 152c1758 | Karthick | 2025-09-20 12:43 | Contacts | 13 | 303 | 0 | feat(contact): implement contact email address screen
BE | ee331f4b | Karthick | 2025-09-20 12:51 | Contacts | 25 | 6947 | 2 | feat(contact): add contact address entity and migration
FE | 9506a1af | Karthick | 2025-09-20 12:53 | Contacts | 13 | 386 | 1 | feat(contact): implement contact address screen
BE | 0841469c | Karthick | 2025-09-20 13:04 | Contacts | 21 | 6874 | 1 | feat(contact): add contact type assignment entity and migration
FE | 40cf16b5 | Karthick | 2025-09-20 13:06 | Contacts | 13 | 284 | 0 | feat(contact): implement contact type assignment screen
BE | a98a2c58 | Karthick | 2025-09-20 13:16 | Contacts | 20 | 6929 | 0 | feat(contact): add branch user entity and migration
FE | 9b1f4665 | Karthick | 2025-09-20 13:17 | Contacts | 13 | 280 | 0 | feat(contact): implement branch user screen
BE | b5fa5293 | Karthick | 2025-09-22 10:38 | Finance / Payment / Receipt | 6 | 6361 | 2 | feat(core): add startno and isonline to paymentmode entity
BE | 2a5d2997 | Karthick | 2025-09-22 10:46 | Finance / Payment / Receipt | 8 | 6275 | 3 | feat(core): add bankbranchname and bankbranchplace to bank entity
FE | c1af7822 | Karthick | 2025-09-22 14:41 | Other / Shared | 114 | 44 | 394 | fix: cleanup the folder structure and add proper menu hierarchy
BE | 9a6ff4f3 | Karthick | 2025-09-22 18:30 | Other / Shared | 10 | 6305 | 14 | feat: add pincode to locality entity and migrate
BE | f2d6d2c3 | Karthick | 2025-09-23 16:28 | Other / Shared | 1 | 146 | 0 | feat: implement gender crud endpoints
FE | e8751691 | Karthick | 2025-09-23 16:57 | Contacts | 11 | 91 | 80 | fix: apply proper property name to contact query and mutation
FE | 3f9c9e33 | Karthick | 2025-09-23 17:13 | Contacts | 13 | 278 | 0 | feat(contact): implement incoming mode screen
BE | 4fbf3d6d | Karthick | 2025-09-23 17:17 | Contacts | 17 | 6738 | 233 | refactor(contact): recreate the incoming mode
BE | 599f5c8b | Karthick | 2025-09-23 17:55 | Contacts | 18 | 6776 | 257 | refactor(contact): recreate the incoming sub mode entity and migrate
FE | 16d871f9 | Karthick | 2025-09-23 18:01 | Contacts | 13 | 291 | 0 | feat(contact): implement incoming sub mode screen
FE | a9e771b9 | Karthick | 2025-09-23 21:16 | Contacts | 10 | 48 | 280 | fix: get propery properties in contact module relevant query
BE | 71e1d952 | Karthick | 2025-09-24 11:22 | Contacts | 19 | 97 | 95 | fix: add primary key as nullable to all contact and donation module entity schemas
FE | 6314db02 | Karthick | 2025-09-24 12:11 | Contacts | 20 | 28 | 26 | fix: make primary field optional in create mutations for contact & donation screens
FE | d1d52444 | Karthick | 2025-09-24 15:58 | Contacts | 2 | 23 | 24 | fix: make company header/footer required in mutation and add pincode query to select widget
BE | c3e8be35 | Karthick | 2025-09-24 16:01 | Contacts | 13 | 83 | 24 | fix: include all property as searchable fields in company, branch and company country entity
BE | 9f3ebe05 | Karthick | 2025-09-25 20:57 | Other / Shared | 55 | 19288 | 161 | fix: tes the fix the issue all screen from contact and donation module
FE | 33a3a795 | Karthick | 2025-09-25 21:00 | Other / Shared | 30 | 453 | 216 | fix: test and fix the issues in all contact and donation module screens
BE | a0e80fb1 | Karthick | 2025-09-26 10:22 | Contacts | 21 | 7034 | 4 | feat(contact): add contact upi detail entity, migration and remove unused packages
FE | c12fda61 | Karthick | 2025-09-26 11:09 | Contacts | 13 | 293 | 0 | feat(contact): implement contact upi details screen
BE | a4e10a6e | Karthick | 2025-09-26 11:32 | Contacts | 1 | 5 | 5 | fix: correct the contact upi details response dto properties
BE | 9f2d7ef9 | Karthick | 2025-09-26 12:54 | System / Access / Config | 21 | 7124 | 39 | feat(auth): add role module entity and migration
FE | d0b3eb90 | Karthick | 2025-09-26 13:09 | System / Access / Config | 4 | 77 | 48 | feat: implement role based modules in master dashboard
FE | 5ca786d1 | Karthick | 2025-09-26 17:27 | Other / Shared | 18 | 118 | 72 | fix: theme not applied properly
FE | 6c897fe3 | Karthick | 2025-09-27 13:49 | System / Access / Config | 1 | 291 | 642 | fix: apply proper light and dark mode in master dashboard
FE | 294b5734 | Karthick | 2025-09-29 18:19 | System / Access / Config | 11 | 397 | 210 | refactor: change the master dashboard ui
BE | e5eeffce | Karthick | 2025-10-02 10:44 | System / Access / Config | 4 | 6382 | 1 | chore: add pkreferenceid to occupation entity
BE | e3adf8a6 | Karthick | 2025-10-02 11:06 | System / Access / Config | 4 | 6385 | 1 | chore: add pkreferenceid to incoming mode entity
BE | 3a591331 | Karthick | 2025-10-02 12:46 | System / Access / Config | 4 | 6388 | 1 | chore: add pkreferenceid to incomingsubmode entity
BE | 559a8ddb | Karthick | 2025-10-02 14:03 | Other / Shared | 13 | 6839 | 49 | chore: add currencyid to country entity
BE | 8214af8a | Karthick | 2025-10-03 06:50 | Contacts | 9 | 6480 | 6 | chore: add companyid and pkereferenceid to contacttype entity
BE | a34ff70b | Karthick | 2025-10-03 07:25 | System / Access / Config | 5 | 6490 | 4 | chore: add pkreferenceid to branch and increase the property size in company header footer propertie
BE | 9babd83b | Karthick | 2025-10-03 15:46 | Other / Shared | 22 | 8287 | 95 | chore: implement seed data for this entities gender,pincode,salutation,language and then add distric
BE | 520a03e5 | Karthick | 2025-10-03 17:44 | Other / Shared | 7 | 6581 | 7 | chore: add pkreferenceid to region entities
BE | b50313c1 | Karthick | 2025-10-03 18:44 | System / Access / Config | 4 | 6469 | 0 | chore: add pkreferenceid to state entity
BE | 81bedd06 | Karthick | 2025-10-04 11:16 | Contacts | 14 | 20553 | 56 | chore: add pkreferenceid and localityid to family entity
BE | 97852b6d | Karthick | 2025-10-04 12:51 | System / Access / Config | 4 | 6496 | 0 | chore: create unique index to userrole entity
BE | 84602c49 | Karthick | 2025-10-05 07:59 | Contacts | 5 | 6527 | 1 | chore: add initial field to contact entity
BE | f423f896 | Karthick | 2025-10-05 09:10 | Contacts | 10 | 6723 | 55 | fix: change address lines as nullable in contact addresses entity
BE | 7fbd6ae5 | Karthick | 2025-10-05 09:55 | Contacts | 9 | 6543 | 10 | fix: change verified date as nullable in contact child entities
BE | a76ac442 | Karthick | 2025-10-06 13:08 | Contacts | 10 | 6597 | 18 | feat: add pkreferenceid to all contact child entities
BE | b20bf7d6 | Karthick | 2025-10-06 17:40 | Contacts | 9 | 6544 | 1 | feat: add localityid to contact address entity and migrate
BE | 7fc58b57 | Karthick | 2025-10-06 18:08 | Contacts | 4 | 6511 | 0 | chore: add pkreferenceid to contact upi detail entity
BE | 0a396289 | Karthick | 2025-10-06 18:41 | Contacts | 4 | 6518 | 1 | fix: change assignedbyuserid as nullable in contact type assignement entity
BE | 366fb323 | Karthick | 2025-10-06 18:46 | Donations | 7 | 6563 | 6 | chore: add pkreferenceid to all donation relevant entities and migrate
BE | 8df8ccf7 | Karthick | 2025-10-06 19:53 | Donations | 4 | 6531 | 1 | fix: change enddate as nullable in donation purpose entity
BE | a01955f9 | Karthick | 2025-10-06 21:55 | System / Access / Config | 5 | 6549 | 9 | fix: change todate as nullable in company country entity
BE | 57c3870e | Karthick | 2025-10-06 21:58 | System / Access / Config | 4 | 6525 | 1 | chore: add pkreferenceid to company country entity
BE | 8507de10 | Karthick | 2025-10-07 10:39 | Finance / Payment / Receipt | 4 | 6528 | 4 | chore: add pkreferenceid to payment mode entity
BE | 1cbe5015 | Karthick | 2025-10-07 11:24 | System / Access / Config | 4 | 6552 | 3 | chore: add pkreferenceid and bankshortcode to bank entity
BE | b90e9549 | Karthick | 2025-10-07 15:06 | Finance / Payment / Receipt | 11 | 6623 | 40 | fix: remove bank code, branch name and place in bank entity
FE | 14510836 | Divya S | 2025-10-07 20:32 | Other / Shared | 9 | 210 | 6 | fix: added the missing file
BE | 196f76c0 | Karthick | 2025-10-07 21:53 | Finance / Payment / Receipt | 6 | 7830 | 9 | chore: add pkreferenceid to currency conversion entity
FE | 9e835c68 | Divya S | 2025-10-07 22:10 | Other / Shared | 1 | 0 | 0 | fix: change the lock file
FE | b682e660 | Divya S | 2025-10-07 22:26 | System / Access / Config | 3 | 2 | 11 | fix: build issue
BE | 55d9af5a | Karthick | 2025-10-08 10:38 | System / Access / Config | 9 | 19589 | 4 | chore: add pkreferenceid to branch pincode and branch user entity
BE | e9d8eeda | Karthick | 2025-10-08 12:36 | Finance / Payment / Receipt | 20 | 7336 | 2 | feat(contact): add companybank entity and migration
BE | 2f81fb67 | Karthick | 2025-10-08 13:31 | System / Access / Config | 6 | 13213 | 1 | fix: change pkreferenceid as int in branch pincodes
FE | 38b4d23c | Karthick | 2025-10-08 14:53 | Finance / Payment / Receipt | 13 | 281 | 0 | feat(contact): implement company bank screen
BE | c2c5f630 | Karthick | 2025-10-08 17:40 | Other / Shared | 5 | 18 | 16 | fix: include district object to locality schema and verify the search conditions in handler
FE | 9701bba2 | Karthick | 2025-10-08 17:41 | Other / Shared | 6 | 33 | 23 | fix: retest the region screens
FE | 72021853 | Divya S | 2025-10-08 12:29 | Other / Shared | 1 | 0 | 0 | Updated pnpm-lock.yaml
BE | 932be337 | Karthick | 2025-10-08 21:05 | Finance / Payment / Receipt | 5 | 76 | 66 | chore: add currency rate updation logics in currency conversion entity
FE | bf3c9d29 | Karthick | 2025-10-08 21:08 | Finance / Payment / Receipt | 4 | 11 | 28 | fix: bank screen and form rendering
BE | 1678ab6d | Karthick | 2025-10-10 11:29 | System / Access / Config | 5 | 6649 | 0 | feat(core): add grid type 2 properties to widget type entity and migration
BE | c23feb82 | Karthick | 2025-10-10 12:04 | System / Access / Config | 9 | 6772 | 12 | feat(core): add grid type 2 proeprties to grid entity and migration
FE | 03735c11 | Karthick | 2025-10-10 14:28 | System / Access / Config | 7 | 287 | 0 | feat(core): implement grid relationship entity and mutation
BE | bbe09c88 | Karthick | 2025-10-10 15:05 | System / Access / Config | 21 | 7612 | 4 | feat(core): add grid relationship entity and migration
BE | 3048c6ab | Karthick | 2025-10-10 15:44 | System / Access / Config | 22 | 7805 | 6 | feat(core): add grid widget entity and migration
FE | db3e7adc | Karthick | 2025-10-10 15:50 | System / Access / Config | 7 | 311 | 0 | feat(core): implement grid widget entity and mutation
BE | 35140240 | Karthick | 2025-10-10 15:58 | System / Access / Config | 20 | 7786 | 1 | feat(core): add grid layout step entity and migration
FE | bf0c2828 | Karthick | 2025-10-10 16:00 | System / Access / Config | 7 | 272 | 0 | feat(core): implement grid layout entity and mutation
FE | 1a4957ea | Karthick | 2025-10-14 12:24 | Other / Shared | 133 | 12438 | 61 | feat: impelement flow grid phase 1
FE | 197bc8ff | Karthick | 2025-10-15 22:30 | Other / Shared | 30 | 562 | 559 | fix: flow grid widget ui changes
BE | cc8aeb1e | Karthick | 2025-10-15 22:31 | System / Access / Config | 22 | 28335 | 27 | feat: flow grid relevant endpoint and schemas changes
FE | d42204a4 | PW Data Solutions | 2025-10-16 04:05 | Other / Shared | 1 | 11 | 9 | Updated azure-pipelines.yml
FE | e6053d98 | PW Data Solutions | 2025-10-16 07:18 | Other / Shared | 1 | 4 | 3 | Updated next.config.mjs
FE | 20d17ace | PW Data Solutions | 2025-10-16 07:21 | Other / Shared | 1 | 1 | 1 | Updated next.config.mjs.backup
FE | 30f9d61c | PW Data Solutions | 2025-10-16 07:22 | Other / Shared | 1 | 1 | 1 | Updated next.config.mjs
BE | 042ab5be | Karthick | 2025-10-16 13:24 | System / Access / Config | 11 | 7203 | 29 | chore: add parent widget id to grid widget entity and migration
BE | 10fa4c61 | Karthick | 2025-10-16 13:28 | System / Access / Config | 5 | 7049 | 6 | fix: remove un used properties in grid type entity and migration
BE | 955d48d4 | Karthick | 2025-10-16 13:38 | System / Access / Config | 5 | 7035 | 2 | fix: change stored procedure name as nullable in widget entity and migration
FE | 3d13ef3a | Karthick | 2025-10-16 14:47 | Contacts | 15 | 135 | 52 | fix: generate report rendering issue fix in contact module
BE | 78b45945 | Karthick | 2025-10-16 15:48 | System / Access / Config | 12 | 7105 | 37 | fix: remove un used properties in grid entity and migration
FE | 35feea09 | Karthick | 2025-10-16 19:52 | Other / Shared | 15 | 878 | 381 | refactor: flow grid entity changes and cleanup
BE | d5221fd1 | Karthick | 2025-10-16 19:53 | System / Access / Config | 2 | 36 | 53 | chore: linq query changes in flow grid by code endpoint
FE | 1ac961e3 | Karthick | 2025-10-17 11:27 | Other / Shared | 12 | 36 | 10 | chore: dashboard screens implementations
FE | 37128249 | Karthick | 2025-10-17 11:28 | Other / Shared | 1 | 4 | 4 | fix: base url change
FE | 732b629b | Karthick | 2025-10-17 11:29 | Other / Shared | 1 | 1 | 1 | fix: base url changes
FE | 3acdefe6 | Karthick | 2025-10-17 14:41 | System / Access / Config | 5 | 25 | 22 | fix: dashboard rendering module based
FE | b9e338fe | Karthick | 2025-10-17 16:41 | Other / Shared | 3 | 8 | 6 | fix: type issue fix in build
BE | bf790ec6 | Karthick | 2025-10-17 17:41 | Contacts | 11 | 472 | 0 | chore: implement export endpoint for company relevant entity
FE | c5313c95 | Karthick | 2025-10-23 06:33 | Other / Shared | 47 | 830 | 478 | chore: contact form refactor phase 1
FE | 7758a227 | Ganesh | 2025-10-23 16:57 | Other / Shared | 4 | 204 | 24 | chore: add loader layout skeletons
BE | 442ad2c0 | Karthick | 2025-10-23 17:01 | Contacts | 26 | 15145 | 167 | refactor: contact entity convert into universal basis
FE | 8000762d | Karthick | 2025-10-29 10:11 | Other / Shared | 68 | 8585 | 826 | chore: contact form refactor phase 2
BE | 33c5bb70 | Karthick | 2025-10-29 10:12 | Contacts | 24 | 28003 | 197 | chore: convert contact entity as universal basis phase2
FE | 140eee19 | Karthick | 2025-10-29 10:25 | Contacts | 13 | 293 | 0 | feat(contact): implement contact relationship screen
BE | d0d867bf | Karthick | 2025-10-29 10:42 | Contacts | 20 | 7761 | 1 | feat(contact): add contact relationship entity and migration
BE | e473eee3 | Ganesh | 2025-10-29 13:12 | System / Access / Config | 5 | 6950 | 2 | add custom field in the Field table
BE | efe926fa | Ganesh | 2025-10-29 13:14 | System / Access / Config | 21 | 453 | 0 | add custom field endpoints
BE | f5c37188 | Karthick | 2025-10-29 19:00 | Contacts | 9 | 7068 | 10 | fix: change foreign key relation of relationtypeid property in contact relation entity
FE | d4156fe8 | Karthick | 2025-10-30 12:27 | Contacts | 21 | 650 | 864 | chore: contact form refactor phase 3
FE | 3c8ca8da | Ganesh | 2025-10-30 13:49 | Other / Shared | 40 | 3738 | 146 | chore: custom field implementaion
FE | f7b2c198 | Karthick | 2025-10-31 09:46 | Contacts | 17 | 1942 | 564 | chore: contact screen refactor phase 4
BE | 87a7cb2f | Karthick | 2025-10-31 09:49 | Contacts | 10 | 14104 | 0 | chore: add jobtitle, employer organization field and isrefferal to contact entity
BE | 8446fdf6 | Karthick | 2025-10-31 10:09 | Contacts | 20 | 7825 | 2 | feat(contact): add contact social link entity and migration
FE | 5b22aa10 | Karthick | 2025-10-31 10:10 | Contacts | 13 | 262 | 0 | feat(contact): implement contact social link screen
FE | da074d5e | Karthick | 2025-10-31 11:48 | Contacts | 14 | 337 | 54 | chore: convert donotmail to donotpostal and implement contact social link tab in contact screen
BE | 940e6317 | Karthick | 2025-10-31 11:49 | Contacts | 5 | 7117 | 2 | fix: convert the property donotmail to donotpostal in contact entity
FE | 5c63d1f3 | Ganesh | 2025-10-31 13:01 | Other / Shared | 12 | 432 | 360 | chore: add custom field add queries and mutation
FE | d5020a93 | Ganesh | 2025-10-31 13:01 | Other / Shared | 13 | 153 | 118 | fix: grahql queries and mutaions
FE | 938fd2ce | Ganesh | 2025-10-31 15:57 | Other / Shared | 5 | 126 | 85 | chore: mutaion updates custom form field
FE | ef678e53 | Karthick | 2025-10-31 16:14 | Contacts | 11 | 458 | 58 | feat: implement optimized searchable select component via react-select lib
FE | 82757bb9 | Karthick | 2025-10-31 17:01 | Contacts | 7 | 83 | 5 | chore: assign value and disable parent dropdown field in all contact child gridform schema from
FE | 9d55bf24 | Karthick | 2025-10-31 19:18 | Contacts | 16 | 998 | 698 | fix: apply uniform header to all contact tabs internal components
FE | a66b443b | Ganesh | 2025-11-01 10:42 | Other / Shared | 4 | 118 | 287 | fix: remove ciustom field steal data
FE | 449d065d | Ganesh | 2025-11-01 11:22 | Other / Shared | 9 | 694 | 31 | fix: update mutaions for custom fields
FE | 57c1fd16 | Karthick | 2025-11-01 12:06 | Contacts | 10 | 318 | 168 | chore: apply ux to contact phone number details
FE | b6a2327d | Karthick | 2025-11-01 13:17 | Contacts | 3 | 462 | 56 | chore: apply ux to contact email address component
FE | e74455dd | Karthick | 2025-11-01 13:56 | Contacts | 3 | 424 | 134 | chore: apply ux to contact address comaponent
FE | d9b8d533 | Karthick | 2025-11-01 16:54 | Contacts | 24 | 1445 | 161 | chore: implement loading components and apply all the ares in contact screen
FE | 82ced660 | Karthick | 2025-11-02 20:30 | Contacts | 15 | 1202 | 335 | chore: apply ux to social link component and implement profile upload
BE | 5554c5c8 | Karthick | 2025-11-02 20:33 | Contacts | 8 | 101 | 8 | chore: implement contact profile upload endpoint
BE | 02cc71e9 | Ganesh | 2025-11-03 10:39 | System / Access / Config | 26 | 450 | 28 | add endpoints for custom field generration
FE | a149769f | Karthick | 2025-11-03 10:48 | Contacts | 5 | 73 | 10 | fix: refetch the parent record after save in cotact screen
BE | 79e754e6 | Ganesh | 2025-11-03 11:05 | System / Access / Config | 5 | 7138 | 12 | migration country custom fields
FE | 84867214 | Karthick | 2025-11-03 17:46 | Contacts | 12 | 224 | 162 | fix: remove unwanted column in contact address and ux handle in profile
FE | abd8bb39 | Karthick | 2025-11-03 18:54 | Contacts | 1 | 103 | 5 | fix: caluculate profile completion percentage properly
FE | 7ab698ee | Karthick | 2025-11-04 10:50 | Contacts | 10 | 512 | 67 | chore: implement atleast one communication details is required when create new contact
BE | 474b7887 | Karthick | 2025-11-04 10:53 | Contacts | 11 | 7207 | 21 | chore: implement atleast one communication detail is required relevant fuctionality in create contac
FE | 5e072baf | Karthick | 2025-11-04 14:09 | Other / Shared | 3 | 1221 | 0 | chore: implement rjsf field select v3 component
FE | 9e94ddcd | Ganesh | 2025-11-04 14:25 | Other / Shared | 11 | 215 | 113 | fix: add advanved and sorting
FE | 70b6d8c9 | Karthick | 2025-11-04 15:47 | Other / Shared | 2 | 211 | 28 | chore: implement rjsf field selectv3 manual search provision
FE | 9bd1e71b | Karthick | 2025-11-04 15:57 | Contacts | 8 | 14 | 37 | fix: remove unwanted console in contact screen
FE | eea786ee | Ganesh | 2025-11-04 16:57 | Other / Shared | 4 | 60 | 18 | fix: add custom form validations
BE | 2e85376b | Karthick | 2025-11-04 18:21 | Contacts | 7 | 7195 | 11 | chore: add countryid and stdcode properties to contact phone number entity - migration file name wro
FE | 56758f0a | Karthick | 2025-11-04 19:27 | Other / Shared | 5 | 515 | 3 | feat: implement custom label option in selectv3 dropdown
FE | 637c1f62 | Karthick | 2025-11-04 21:52 | Other / Shared | 3 | 100 | 3 | chore: add auto calculation for phono number in contact phone number
FE | 7f94169c | Karthick | 2025-11-04 21:54 | Other / Shared | 2 | 2837 | 0 | chore: add doc for select v3 component
BE | bcec4317 | Karthick | 2025-11-04 21:55 | Contacts | 1 | 3 | 0 | fix: add countryid and stdcode to contact phone number schema
FE | 918f2c8e | Karthick | 2025-11-04 21:57 | Other / Shared | 1 | 2 | 2 | fix: change the base url
FE | 19731117 | Karthick | 2025-11-04 22:11 | Other / Shared | 1 | 2 | 2 | fix: build and fix the type issue
BE | 7462a299 | Karthick | 2025-11-05 09:14 | Contacts | 3 | 19 | 7 | fix: change contact profile photo upload endpoint response
FE | 455c7ae9 | Karthick | 2025-11-05 09:17 | Contacts | 5 | 34 | 19 | fix: profile photo refresh
FE | 1b715932 | Karthick | 2025-11-05 11:36 | Other / Shared | 3 | 4 | 3 | fix: replace localhost url to actual url
FE | ba794ccf | Karthick | 2025-11-05 12:14 | Other / Shared | 1 | 1 | 1 | fix: change next auth secret key
FE | 7df19402 | Karthick | 2025-11-05 12:31 | Other / Shared | 1 | 1 | 1 | fix: replace next auth debug url in lanuch json
FE | b0f4b94d | Karthick | 2025-11-05 12:37 | Contacts | 4 | 87 | 4 | fix: apply default value to contact status field in contact screen
BE | 08e1434a | Karthick | 2025-11-05 19:02 | Contacts | 9 | 7166 | 32 | fix: remove address line 2,3,4 in contact address
FE | 27c4c4d4 | Karthick | 2025-11-06 09:51 | Other / Shared | 5 | 1513 | 0 | feat: implement selectv2.2 component with multiple depends on
FE | bb6997b1 | Karthick | 2025-11-06 15:45 | Other / Shared | 3 | 1143 | 0 | chore: add documents for region implementation
FE | f0937e6b | Karthick | 2025-11-06 16:51 | Other / Shared | 2 | 193 | 76 | chore: add ux to select componets
FE | 11af91ea | Karthick | 2025-11-06 19:24 | Other / Shared | 125 | 604 | 4794 | refactor: datatable form move to common
FE | 7e186cea | Karthick | 2025-11-06 19:27 | Other / Shared | 7 | 4101 | 0 | chore: add inline add option implementation docs
FE | 0560c9db | Karthick | 2025-11-07 13:41 | Other / Shared | 23 | 2231 | 4053 | feat: implement inline add functionality to apiselect v2 and v3 and implementation documents
BE | 0e74d706 | Karthick | 2025-11-07 13:46 | System / Access / Config | 2 | 2 | 2 | fix: add role capability childs to getall rolecapability dbcontext
FE | 647a017c | Karthick | 2025-11-07 18:38 | Other / Shared | 119 | 380 | 3371 | fix: cleanup the consoles
BE | 3171d352 | Kavinkumar Thirumalaisamy | 2025-11-10 16:28 | Contacts | 7 | 7174 | 1 | feat: new fields added in contact relationship
FE | ab19688a | Kavinkumar Thirumalaisamy | 2025-11-10 16:29 | Contacts | 2 | 75 | 55 | feat: new fields added in contact relationship
BE | 1bf2fd10 | Karthick | 2025-11-10 21:56 | Contacts | 9 | 7210 | 10 | fix: re added addressline1,2,3,4 in contact address entity
FE | d681110b | Karthick | 2025-11-10 22:06 | Other / Shared | 2 | 21 | 5 | fix: dependon field rendering issue fix
FE | 1ec0bc51 | Karthick | 2025-11-11 09:20 | Other / Shared | 1 | 9 | 10 | fix: apply the advance filter to selectv2 component
BE | 2fa4ab3b | Karthick | 2025-11-11 09:50 | Contacts | 2 | 1 | 7 | fix: remove the required option to address2,3,4 in contact create and update mutation
FE | 37048c44 | Kavinkumar Thirumalaisamy | 2025-11-11 16:24 | System / Access / Config | 4 | 23 | 4 | fix: edit forms errors fixed
BE | 90dfa0de | Kavinkumar Thirumalaisamy | 2025-11-11 18:15 | Contacts | 2 | 2 | 2 | fix: contact type company field added
FE | ffb4e831 | Kavinkumar Thirumalaisamy | 2025-11-11 18:16 | Contacts | 3 | 47 | 40 | fix: contact type company field added
BE | 22d6542c | Kavinkumar Thirumalaisamy | 2025-11-11 20:38 | Contacts | 70 | 9085 | 1767 | fix: backend incoming mode and sub mode change to channel type and contact channel changes
FE | 8a14835b | Kavinkumar Thirumalaisamy | 2025-11-11 20:38 | Contacts | 31 | 432 | 432 | fix: frontend incoming mode and sub mode change to channel type and contact channel changes
BE | 2ad6912d | Karthick | 2025-11-12 08:26 | Contacts | 21 | 8187 | 11 | feat(contact): add compaign entity and migration
FE | 44b47b5e | Karthick | 2025-11-12 08:29 | Contacts | 13 | 405 | 0 | feat(contact): implement compaign screen
FE | 7b5a7ccb | Karthick | 2025-11-12 08:45 | Contacts | 3 | 11 | 11 | fix: build and fix type issue
BE | eeecd251 | Karthick | 2025-11-12 09:24 | Events & Auction | 24 | 8595 | 4 | feat(contact): add event entity and migration
FE | 828d9ba8 | Karthick | 2025-11-12 09:24 | Events & Auction | 13 | 502 | 0 | feat(contact): implement event screen
BE | 7bf6762e | Kavinkumar Thirumalaisamy | 2025-11-12 10:00 | Contacts | 1 | 2 | 2 | fix: export issue fixed in channel type screen
BE | 7c44719f | Kavinkumar Thirumalaisamy | 2025-11-12 12:32 | Contacts | 23 | 7745 | 10 | feat: three entites added in company fields.
FE | 963b5b5f | Kavinkumar Thirumalaisamy | 2025-11-12 12:34 | Contacts | 9 | 44 | 21 | feat: three entities added in company field
FE | 4757ea22 | Karthick | 2025-11-12 13:28 | Contacts | 13 | 284 | 0 | feat(contact): implement organizational unit screen
BE | 9da2fffb | Karthick | 2025-11-12 13:29 | Contacts | 21 | 8424 | 22 | feat(contact): add organizational unit and migration
BE | 9e940c35 | Kavinkumar Thirumalaisamy | 2025-11-12 15:31 | System / Access / Config | 17 | 7752 | 16 | feat: company id added in jwt token
BE | 63cc99d3 | Karthick | 2025-11-12 15:39 | Campaigns / Crowdfund / P2P | 31 | 413 | 448 | fix: apply proper property name for campaign and event entities
BE | dff41d6b | Karthick | 2025-11-12 16:18 | Events & Auction | 3 | 8059 | 0 | fix: apply migration for campaign and event
FE | 5336cbfd | Karthick | 2025-11-12 17:19 | Contacts | 19 | 232 | 260 | fix: convert the compaign to campaign
BE | 4a349dde | Karthick | 2025-11-12 19:35 | Donations | 22 | 8886 | 9 | feat(contact): add donation entity and migration
BE | 8c658479 | Karthick | 2025-11-12 19:39 | Finance / Payment / Receipt | 4 | 8014 | 4 | fix: change receipt fields as nullable in donation
FE | a3de5c2c | Karthick | 2025-11-12 19:48 | Donations | 15 | 436 | 1 | feat(donation): implement donation screen
BE | b1d4face | Karthick | 2025-11-13 05:37 | Donations | 24 | 8899 | 15 | feat(donation): add donation distribution entity and migration
FE | 810fa042 | Karthick | 2025-11-13 05:39 | Donations | 16 | 378 | 80 | feat(donation): implement donation distribution screen
BE | 01cebbdb | Karthick | 2025-11-13 08:17 | Finance / Payment / Receipt | 23 | 9161 | 4 | feat(donation): add receipt donation entity and migration
FE | 40050ebd | Karthick | 2025-11-13 08:24 | Finance / Payment / Receipt | 13 | 408 | 0 | feat(donation): implement receipt donaion screen
BE | 5c851ce1 | Kavinkumar Thirumalaisamy | 2025-11-13 10:28 | System / Access / Config | 6 | 93 | 17 | feat : added company related fields in staff
FE | 1a9d4a9a | Kavinkumar Thirumalaisamy | 2025-11-13 10:29 | System / Access / Config | 4 | 46 | 5 | feat: added company related fields in staff
BE | 9b2ba356 | Kavinkumar Thirumalaisamy | 2025-11-13 11:02 | Contacts | 5 | 14 | 9 | fix: entity fixes
FE | e9223e4e | Kavinkumar Thirumalaisamy | 2025-11-13 11:03 | Contacts | 7 | 1 | 36 | fix: entity and query fixes
FE | aae824e2 | Karthick | 2025-11-13 11:25 | Donations | 13 | 473 | 0 | feat(donation): implement cheque donation screen
FE | 97604892 | Kavinkumar Thirumalaisamy | 2025-11-13 13:15 | Contacts | 3 | 24 | 23 | fix: common place holder values added
BE | 7e66d9b0 | Saranya C | 2025-11-13 15:05 | System / Access / Config | 6 | 403 | 4 | Completed Staff Category CRUD actions.
FE | cec20d80 | Saranya C | 2025-11-13 15:08 | Other / Shared | 1 | 1 | 1 | fix: make the visibilty view button in all screens
FE | 65c9e028 | Saranya C | 2025-11-13 15:10 | System / Access / Config | 3 | 6 | 11 | fix: completed Staffcategory crud workflow
BE | 1f8eaf56 | Kavinkumar Thirumalaisamy | 2025-11-13 17:11 | Contacts | 2 | 11 | 5 | fix: fixed inline dropdown loaded default values
FE | 1297e501 | Kavinkumar Thirumalaisamy | 2025-11-13 17:11 | Other / Shared | 3 | 183 | 130 | fix: inline dropdown default values added
BE | 965806f8 | Karthick | 2025-11-14 12:09 | Donations | 25 | 9535 | 15 | feat(donation): add cheque donation entity and migration
BE | 44d3f1ba | Kavinkumar Thirumalaisamy | 2025-11-14 13:06 | System / Access / Config | 5 | 8282 | 6 | change: parentunitid required to non required in OU
BE | e5677310 | Kavinkumar Thirumalaisamy | 2025-11-14 13:52 | Contacts | 6 | 121 | 11 | fix: organizationalunits entity changes
FE | b2db56a1 | Kavinkumar Thirumalaisamy | 2025-11-14 13:53 | Contacts | 3 | 28 | 9 | fix: organization units entity front end changes
FE | f8bb8bf6 | Kavinkumar Thirumalaisamy | 2025-11-14 18:47 | Campaigns / Crowdfund / P2P | 2 | 77 | 75 | fix: campaign entites fixes
BE | 3cd85099 | Kavinkumar Thirumalaisamy | 2025-11-14 18:47 | Campaigns / Crowdfund / P2P | 5 | 19 | 11 | fix: campain entity changes
FE | 3560ed9f | Kavinkumar Thirumalaisamy | 2025-11-15 17:03 | Other / Shared | 5 | 318 | 233 | fix: event related screen changes and default label fields added
BE | f4c1371c | Kavinkumar Thirumalaisamy | 2025-11-15 17:04 | Events & Auction | 5 | 19 | 6 | fix: event related screen changes and default label fields added
BE | a321bb02 | Karthick | 2025-11-15 17:48 | Other / Shared | 156 | 2906 | 530 | refactor: cleanup
BE | 411d7f15 | Karthick | 2025-11-16 10:14 | System / Access / Config | 1 | 1 | 0 | check: commit
BE | 4b17b74e | Karthick | 2025-11-16 11:38 | Other / Shared | 47 | 80 | 1462 | fix: fix the fluent service regisration error
FE | ef060a6d | Karthick | 2025-11-17 19:14 | Other / Shared | 41 | 5679 | 607 | chore: implement 360 degree filter base
BE | 804804a1 | Karthick | 2025-11-18 06:22 | System / Access / Config | 4 | 9395 | 2 | chore: add 360 degree filter relevant fields
FE | f363f344 | Karthick | 2025-11-18 16:28 | Communication | 17 | 354 | 1 | chore: implement company email provider screen
BE | baf87f7c | Karthick | 2025-11-18 16:38 | Communication | 34 | 9557 | 139 | feat(notify): add company email provider and migration
FE | d66bac8a | Karthick | 2025-11-18 16:56 | Communication | 13 | 294 | 0 | feat(notify): implement saved filter screen for recipient
BE | 137fb606 | Karthick | 2025-11-18 17:14 | Communication | 21 | 9519 | 2 | feat(notify): add saved filter entity and migration
FE | 8bd2a56d | Kavinkumar Thirumalaisamy | 2025-11-18 22:35 | Contacts | 31 | 4011 | 66 | chore: organizational custom from implementation front end changes
BE | 95f437b3 | Kavinkumar Thirumalaisamy | 2025-11-18 22:36 | Events & Auction | 13 | 223 | 17 | chore: organizational custom from implementation back end changes
FE | fffd8cbd | Kavinkumar Thirumalaisamy | 2025-11-18 22:46 | System / Access / Config | 4 | 7 | 6 | fix: build issue fixed
BE | d784d712 | Karthick | 2025-11-19 06:02 | Communication | 22 | 9798 | 6 | feat(notify): add email send job entity and migration
FE | 3b0b824b | Karthick | 2025-11-19 06:13 | Communication | 13 | 414 | 0 | feat(notify): implement email send job screen
FE | 21758d6e | Kavinkumar Thirumalaisamy | 2025-11-19 11:16 | Events & Auction | 5 | 152 | 29 | fix: changes for organization unit validations
BE | 3ad9f55c | Saranya C | 2025-11-19 11:17 | System / Access / Config | 9 | 182 | 32 | Completed Staff CRUD functionality/
FE | ff68ca70 | Saranya C | 2025-11-19 11:25 | System / Access / Config | 17 | 1894 | 11 | fix: completed the staff wizard screen with functionality
BE | 6694225d | Karthick | 2025-11-19 14:54 | Communication | 24 | 10068 | 6 | feat(notify): add email send job entity and migration
FE | af0808f8 | Karthick | 2025-11-19 15:31 | Communication | 13 | 469 | 0 | feat(notify): implement email send queue screen
BE | c6fb6bf7 | Karthick | 2025-11-20 20:02 | Communication | 64 | 1082 | 52 | feat: email service phase1
BE | bbedb7f7 | Kavinkumar Thirumalaisamy | 2025-11-20 22:01 | System / Access / Config | 1 | 2 | 2 | fix: remove referesh token two time configures
BE | 88ed9309 | Karthick | 2025-11-21 09:33 | Other / Shared | 184 | 711 | 404 | fix: check and fix the namespace issue
BE | f1a22916 | Karthick | 2025-11-21 11:56 | Communication | 19 | 27835 | 255 | fix: hangfire job testing part 1
BE | 5c3de76d | Kavinkumar Thirumalaisamy | 2025-11-21 12:33 | Contacts | 9 | 9284 | 6 | chore : added uniueIndex configuration using companyId field
BE | 9dde15e4 | Saranya C | 2025-11-21 12:49 | Contacts | 6 | 8946 | 2 | Fix: Updated the Date type in ContactRelationShipConfiguration
BE | 53a20bc6 | Kavinkumar Thirumalaisamy | 2025-11-21 13:51 | System / Access / Config | 15 | 1279 | 14 | feat: added multi tenant feature for company based filteration.
BE | 5d965932 | Saranya C | 2025-11-21 15:38 | Contacts | 6 | 8953 | 2 | Fix: Updated the dob date type in Contact Configuration.
BE | b7e9bbe9 | Karthick | 2025-11-21 16:02 | Communication | 10 | 9440 | 56 | fix: hangfire job testing part 2
BE | 28c7b085 | Karthick | 2025-11-21 16:47 | Communication | 8 | 259 | 39 | chore: add log for email service
FE | f8b13da2 | Karthick | 2025-11-21 18:48 | Communication | 31 | 49 | 93 | fix: folder cleanup then build and fix the type issues
FE | 8f0e1dda | Kavinkumar Thirumalaisamy | 2025-11-22 10:16 | Donations | 2 | 20 | 1 | fix: widget query added
FE | b269ffc9 | Karthick | 2025-11-24 08:58 | Communication | 24 | 1929 | 671 | feat: implement email job scheduler screen
BE | 72455c20 | Karthick | 2025-11-24 09:05 | Communication | 5 | 165 | 36 | chore: add update job update logics into email send job update mutation
BE | 2ab9d434 | Karthick | 2025-11-24 09:58 | Communication | 28 | 45 | 18 | fix: move base.support solution to inner base folder
BE | dd0f413d | Saranya C | 2025-11-25 09:30 | Contacts | 5 | 197 | 38 | Fix: completed the bulk assignement of Contact Type Assignment.
BE | c8d30091 | Saranya C | 2025-11-25 09:32 | Reporting / Dashboard / Audit | 2 | 5 | 4 | Fix: fixed the issue in contact generate report.
FE | 83736412 | Saranya C | 2025-11-25 09:37 | Contacts | 3 | 360 | 79 | fix: updated the contact type bulk assignment
FE | 44fac47d | Saranya C | 2025-11-25 09:38 | Contacts | 2 | 4 | 4 | fix: updated the date format in contact
BE | 15d9694c | Saranya C | 2025-11-25 10:51 | System / Access / Config | 1 | 2 | 2 | fix: worked in showing menu list for staff role.
FE | 16671ea0 | Karthick | 2025-11-25 11:07 | System / Access / Config | 3 | 5 | 0 | fix: new capability configuration
FE | 51abdf8a | Kavinkumar Thirumalaisamy | 2025-11-26 12:11 | Reporting / Dashboard / Audit | 2 | 585 | 3 | feat: multichart widget complete changes
BE | ac8fddf9 | Saranya C | 2025-11-26 12:42 | Contacts | 5 | 119 | 1 | chore: added export functionality in contact
FE | 95db2726 | Saranya C | 2025-11-26 13:35 | Contacts | 1 | 1 | 1 | fix: changed the label contributor type instead of contactbasetype
FE | 6bd4842b | Kavinkumar Thirumalaisamy | 2025-11-26 13:41 | Reporting / Dashboard / Audit | 1 | 4 | 4 | fix: configure widget property removed
BE | 30723868 | Kavinkumar Thirumalaisamy | 2025-11-27 14:49 | Other / Shared | 7 | 269 | 3 | fix: pincode screen issue fixed
FE | 9b076ccb | Kavinkumar Thirumalaisamy | 2025-11-27 14:49 | Other / Shared | 3 | 16 | 2 | fix: pincode queries and mutation changes
BE | 2b5274a2 | Saranya C | 2025-11-28 09:54 | Contacts | 9 | 9236 | 5 | fix: done migration on branchpincode to add companyid
FE | 90f5434f | Kavinkumar Thirumalaisamy | 2025-11-28 10:02 | Other / Shared | 4 | 566 | 274 | fix: fixed user profile screen
FE | b60e548a | Saranya C | 2025-11-28 10:41 | Contacts | 1 | 9 | 1 | fix: fixed index issue in contact
FE | 7f263c34 | Saranya C | 2025-11-28 10:46 | Contacts | 1 | 1 | 1 | fix: removed toast message in contact type
BE | d2f8a1f3 | Saranya C | 2025-11-28 12:48 | Contacts | 9 | 9226 | 3 | fix: done migration on ContactPhonenumber to add companyid
BE | 35a69740 | Saranya C | 2025-11-28 13:09 | Contacts | 9 | 9261 | 3 | fix: done migration on contactaddress to add companyid
FE | bf518a2e | Kavinkumar Thirumalaisamy | 2025-11-28 13:35 | Communication | 8 | 57 | 0 | feat: email template screen implemented
FE | 051c76a6 | Kavinkumar Thirumalaisamy | 2025-11-28 14:35 | Communication | 1 | 2 | 1 | fix: template screen issue
FE | 69ed1fdb | Kavinkumar Thirumalaisamy | 2025-11-28 14:43 | Communication | 7 | 0 | 57 | fix: removed unwanted added screen
BE | 249db446 | Saranya C | 2025-11-28 15:19 | Contacts | 8 | 9270 | 1 | fix: done migration on contacttypeassignment to add companyid
BE | 5833553e | Saranya C | 2025-11-28 15:36 | Contacts | 7 | 9257 | 1 | fix: done migration in contactrelationship to add companyid
BE | 82379d3c | Saranya C | 2025-11-28 15:48 | Contacts | 7 | 9269 | 2 | fix: done migration in contactsociallink to add companyid
BE | 790c0808 | Saranya C | 2025-11-28 16:09 | Contacts | 7 | 9283 | 1 | fix: done mogration in contactemailaddress to add companyid
FE | b2ade6b0 | Saranya C | 2025-11-28 16:13 | Other / Shared | 1 | 17 | 7 | fix: fixed select issue in dropdown selection
FE | 13860e12 | Kavinkumar Thirumalaisamy | 2025-11-29 10:10 | Other / Shared | 1 | 3 | 0 | fix: added new icons
FE | acce7d51 | Kavinkumar Thirumalaisamy | 2025-11-29 12:47 | System / Access / Config | 4 | 200 | 225 | fix: master dashboard changes
BE | 5ff7a20a | Karthick | 2025-11-30 09:14 | System / Access / Config | 9 | 9369 | 2 | feat: 360 degree base setup
FE | 3d639549 | Kavinkumar Thirumalaisamy | 2025-12-01 11:50 | System / Access / Config | 2 | 21 | 10 | fix: ui master dashboard changes
FE | 7c61fd66 | Saranya C | 2025-12-01 12:05 | Contacts | 11 | 1279 | 359 | chore: impletement communication type component in conatct
BE | 1bc4b92e | Saranya C | 2025-12-01 12:06 | Contacts | 2 | 98 | 33 | chore: implement communication type component in contact
FE | 5006b192 | Kavinkumar Thirumalaisamy | 2025-12-01 13:00 | Other / Shared | 6 | 10 | 0 | fix: build issue fixes for capabilities
FE | 4874cd03 | Saranya C | 2025-12-01 13:31 | Contacts | 4 | 13 | 19 | fix: updated the value of cantact base type
BE | 69aa6b6a | Saranya C | 2025-12-01 15:18 | Events & Auction | 1 | 1 | 1 | fix: added asnotracking in event query.
BE | 9ea6adaf | Saranya C | 2025-12-01 15:33 | Campaigns / Crowdfund / P2P | 2 | 4 | 1 | fix: added asnotracking in campaign and gridbycode query
BE | a4048954 | Saranya C | 2025-12-01 16:06 | System / Access / Config | 4 | 12 | 4 | fix: added asnotracking in query.
BE | 7a85004a | Saranya C | 2025-12-01 17:12 | System / Access / Config | 3 | 9 | 5 | fix: added asnotracking() in parentchildmenu,usermodule,floegridbycode query.
BE | bb6748e1 | Saranya C | 2025-12-01 18:18 | Contacts | 11 | 30 | 11 | fix: added asnotracking() in contact queries.
BE | 998d74ba | Saranya C | 2025-12-01 18:45 | System / Access / Config | 1 | 0 | 1 | fix: revert the asnotracking() in parentchildmenu query.
FE | fe863f66 | Karthick | 2025-12-02 08:39 | Other / Shared | 43 | 4415 | 2215 | feat: implement 360 degree filter
FE | a3b5d323 | Kavinkumar Thirumalaisamy | 2025-12-02 08:45 | Reporting / Dashboard / Audit | 7 | 203 | 62 | fix: module navigator issue fixed
BE | cacb387a | Saranya C | 2025-12-02 09:59 | Contacts | 10 | 30 | 10 | fix: added asnotracking method in getall queries.
FE | 95acf765 | Saranya C | 2025-12-02 14:02 | Contacts | 1 | 77 | 24 | fix: show popup message when navigate to other menu
FE | a18db4fc | Saranya C | 2025-12-02 14:03 | System / Access / Config | 3 | 8 | 4 | fix: added role capabilty access for print in contact
BE | 5f910bda | Saranya C | 2025-12-02 17:19 | System / Access / Config | 1 | 121 | 44 | fix: updated the query in getflowgridbycode
BE | 99fe0fa7 | Karthick | 2025-12-02 18:40 | Communication | 12 | 9272 | 329 | fix: fix the publish issue and remove filter category property in savedFilter entity
FE | d3f38ef5 | Saranya C | 2025-12-02 18:43 | Other / Shared | 1 | 2 | 1 | fix: changed the hostname pssdevelopment
FE | a95f9d1f | Karthick | 2025-12-03 08:04 | Communication | 25 | 2620 | 284 | feat: integrate 360 filter into email send job screen
FE | 1a417fb0 | Kavinkumar Thirumalaisamy | 2025-12-03 11:58 | Other / Shared | 268 | 1669 | 1740 | feat: updated lucide to iconify icons replacement changes
FE | 98b2c990 | Karthick | 2025-12-03 13:19 | Other / Shared | 21 | 603 | 333 | chore: apply proper ui to email send job screen
FE | 1c74286a | Kavinkumar Thirumalaisamy | 2025-12-03 13:38 | Reporting / Dashboard / Audit | 7 | 14 | 16 | fix: icons missing dashboard widgets
FE | 3d49c284 | Kavinkumar Thirumalaisamy | 2025-12-03 13:53 | Other / Shared | 8 | 46 | 66 | fix: console log removed
FE | b8ba6f3d | Kavinkumar Thirumalaisamy | 2025-12-03 13:55 | Other / Shared | 1 | 1 | 1 | fix: updated icon width and height adjustment
FE | feffaea5 | Saranya C | 2025-12-03 14:15 | Contacts | 3 | 50 | 21 | fix: rendering restricted message when selecting donotemail, donotsms, donotphone,donotpostal
FE | 34b5950a | Kavinkumar Thirumalaisamy | 2025-12-03 14:57 | Communication | 5 | 1186 | 16 | fix: build issue fixes
FE | eec99421 | Saranya C | 2025-12-03 15:03 | Communication | 1 | 24 | 51 | fix: updated the Formselect component for communication Type
FE | 16a43c84 | Saranya C | 2025-12-03 15:05 | Contacts | 3 | 142 | 8 | fix: added display name field in contact three tabs
FE | 6b2c8bd0 | Kavinkumar Thirumalaisamy | 2025-12-03 15:32 | System / Access / Config | 1 | 2 | 2 | fix: master dashboard issue fixes
FE | 4bc12ee2 | Kavinkumar Thirumalaisamy | 2025-12-03 15:36 | Communication | 2 | 21 | 19 | fix: build issues
FE | 4c992a01 | Karthick | 2025-12-03 15:46 | Reporting / Dashboard / Audit | 2 | 98 | 33 | fix: apply proper ui to report grid
FE | a9e51f1e | Kavinkumar Thirumalaisamy | 2025-12-03 16:02 | System / Access / Config | 3 | 4 | 4 | fix: icon height and width adjustments
FE | 59fa3175 | Kavinkumar Thirumalaisamy | 2025-12-03 16:29 | Reporting / Dashboard / Audit | 1 | 17 | 3 | fix: multichart widget changes
FE | fbfeacb1 | Karthick | 2025-12-03 16:34 | Contacts | 9 | 28 | 28 | fix: change oreganization unit to program
FE | 860c0d0d | Kavinkumar Thirumalaisamy | 2025-12-03 16:38 | Contacts | 1 | 2 | 2 | fix: oraganization Unit removed parentunit id field
BE | a7293170 | Kavinkumar Thirumalaisamy | 2025-12-03 17:16 | Other / Shared | 1 | 2 | 0 | fix: update profile photo issues fixed
BE | 45f14f88 | Kavinkumar Thirumalaisamy | 2025-12-03 18:57 | Other / Shared | 5 | 2 | 247 | fix: pincode api removed
BE | 106610a3 | Karthick | 2025-12-03 21:32 | Communication | 2 | 29 | 3 | fix: properly filter the contacts in email send service
FE | 9a8220f1 | Kavinkumar Thirumalaisamy | 2025-12-04 11:08 | Reporting / Dashboard / Audit | 2 | 112 | 12 | fix: dashboard widget changes
FE | 6ee3ffe9 | Kavinkumar Thirumalaisamy | 2025-12-04 11:50 | Contacts | 3 | 57 | 33 | fix: changes in bug fixes
BE | 75418e12 | Kavinkumar Thirumalaisamy | 2025-12-04 13:06 | Contacts | 2 | 4 | 4 | fix: invaild relation ship changes
BE | 648db1e3 | Kavinkumar Thirumalaisamy | 2025-12-04 13:23 | Contacts | 2 | 6 | 6 | fix: contact relation ship changes
FE | 753de53b | Kavinkumar Thirumalaisamy | 2025-12-04 14:55 | System / Access / Config | 1 | 3 | 3 | fix: module navigator added role based get the details
BE | 755c5184 | Karthick | 2025-12-04 14:55 | Communication | 7 | 9369 | 22 | fix: update email send queue status
FE | 6a73b0cb | Saranya C | 2025-12-04 14:58 | Contacts | 1 | 4 | 4 | fix: removed field in contact type assignment
BE | d9dd13c0 | Saranya C | 2025-12-04 14:59 | Contacts | 3 | 19 | 5 | fix: updated the date in contacttypeassignment.
FE | 69846e00 | Saranya C | 2025-12-04 23:03 | Contacts | 1 | 9 | 1 | fix: fixed index issue in organization unit
FE | 6a39f5d0 | Karthick | 2025-12-05 09:32 | Communication | 3 | 3 | 3 | fix: properly update job status in email send job screen
FE | 08ca5c81 | Karthick | 2025-12-05 09:33 | Other / Shared | 1 | 184 | 0 | feat: code reviewver
BE | 938dfeae | Karthick | 2025-12-05 17:02 | Other / Shared | 27 | 1290 | 0 | chore: backup the email service
FE | 987df868 | Kavinkumar Thirumalaisamy | 2025-12-05 17:43 | Donations | 10 | 222 | 186 | fix: donation module fixes
BE | 259724e3 | Kavinkumar Thirumalaisamy | 2025-12-05 17:44 | Donations | 16 | 9330 | 32 | fix: fixed issues the donation module screens
FE | 4a883c7d | Saranya C | 2025-12-06 11:43 | Reporting / Dashboard / Audit | 13 | 418 | 52 | fix: completed the report generation functionality with searching and sorting
BE | cef7d47a | Karthick | 2025-12-08 15:58 | Communication | 64 | 15539 | 389 | feat: implement bulk email send service with tracking
FE | fdeed899 | Karthick | 2025-12-09 13:33 | Communication | 7 | 146 | 29 | fix: change jobcode is an autogerate and include recipient type in email send job
BE | 624e28a1 | Karthick | 2025-12-09 13:37 | Communication | 14 | 269 | 68 | fix: test the email service and webhook
FE | 329bed3e | Karthick | 2025-12-09 14:33 | Communication | 13 | 447 | 2 | feat: implement placeholder definition screen
BE | 5d7d9096 | Karthick | 2025-12-09 14:34 | Communication | 12 | 680 | 1 | feat: add placeholder definition entity and migration
BE | 8eb3f208 | Karthick | 2025-12-10 10:02 | Communication | 21 | 10794 | 249 | fix: add property path resolver for placeholder and include compantid to email template
FE | ccb9fa1d | Karthick | 2025-12-10 22:14 | Other / Shared | 93 | 9982 | 179 | feat: implement email template editor
BE | f117926e | Karthick | 2025-12-10 22:17 | Communication | 7 | 19 | 154 | fix: remove static placeholder value from retrivel to dynamically
BE | b14ef5ba | Karthick | 2025-12-12 11:44 | Donations | 11 | 10326 | 27 | chore: add contactid and organizationalunitid to donation entity
FE | 268fe3ed | Karthick | 2025-12-12 11:47 | Communication | 1 | 2 | 2 | fix: change decription in user friendly format in email send job basic info
FE | 91fe3024 | Karthick | 2025-12-12 13:17 | System / Access / Config | 17 | 330 | 0 | feat: implement grid child collection category screen
BE | 2fd18c1b | Karthick | 2025-12-12 13:18 | System / Access / Config | 20 | 11062 | 11 | feat(core): add grid child collection category entity and migration
FE | a1fe18e6 | Karthick | 2025-12-12 14:04 | System / Access / Config | 13 | 335 | 0 | feat: implement grid child field screen
BE | 661bd027 | Karthick | 2025-12-12 14:11 | System / Access / Config | 21 | 11194 | 5 | feat(core): add grid child field entity and migration
FE | 0698b554 | Karthick | 2025-12-12 16:51 | System / Access / Config | 3 | 9 | 9 | fix: change usesummarycolumn to usesummarytable in grid child collection category
BE | 16b6af19 | Karthick | 2025-12-12 16:53 | System / Access / Config | 7 | 10397 | 4 | fix: rename the column usesummarycolumn to usesummarytable in grid child collection entity
FE | 3346f58d | Saranya C | 2025-12-12 17:32 | Other / Shared | 1 | 4 | 4 | fix: hide the custom loader in formselect component
BE | 21e076b9 | Kavinkumar Thirumalaisamy | 2025-12-13 13:12 | Other / Shared | 12 | 9480 | 0 | feat: added Site maintanance implementation
FE | b9ae61a6 | Kavinkumar Thirumalaisamy | 2025-12-13 13:14 | Other / Shared | 12 | 322 | 3 | feat: site maintance chanages
FE | a54940e6 | Saranya C | 2025-12-13 17:11 | Other / Shared | 13 | 281 | 3 | chore: implement manual refresh and auto Refresh in grid
FE | 5ff4ef5f | Saranya C | 2025-12-13 17:13 | Other / Shared | 2 | 2 | 2 | fix: change the fieldkey in component column
FE | 52124da8 | Karthick | 2025-12-14 18:50 | Other / Shared | 52 | 4038 | 1018 | fix: test 360 degree filter with aggregation fields
BE | d3e96ad5 | Karthick | 2025-12-14 18:52 | System / Access / Config | 20 | 12947 | 139 | fix: retest 360 degree filter functionality with aggregation fields
BE | 2c39cc92 | Karthick | 2025-12-15 11:23 | System / Access / Config | 5 | 10464 | 2 | chore: add iconclass property to grid child collection category
FE | 14ec1a23 | Saranya C | 2025-12-15 12:35 | System / Access / Config | 1 | 2 | 0 | fix: changed pageindex in rolecapabilities query
FE | 5338828c | Saranya C | 2025-12-15 12:37 | System / Access / Config | 1 | 18 | 17 | fix: comment the hasCapabilitiesForModule
FE | a78d47f6 | Saranya C | 2025-12-15 12:40 | Other / Shared | 2 | 14 | 1 | fix: added enableautorefresh, enablemanualrefresh
BE | c35e336e | Karthick | 2025-12-16 07:38 | Communication | 13 | 533 | 127 | fix: retest webhook event tracking
FE | 860268f8 | Karthick | 2025-12-16 15:44 | Other / Shared | 5 | 128 | 16 | chore: handle ux for recurring job cron expression
BE | 31a2b30a | Karthick | 2025-12-16 16:19 | Communication | 17 | 21052 | 106 | fix: log user email activities via webhook
FE | 9f0a4098 | Karthick | 2025-12-16 17:44 | System / Access / Config | 17 | 32 | 854 | fix: remove unused dtos and queries
BE | ff7a309f | Karthick | 2025-12-16 17:48 | System / Access / Config | 36 | 10384 | 1700 | fix: remove unused entities
FE | 0da43bcd | Saranya C | 2025-12-16 19:23 | Other / Shared | 2 | 66 | 7 | fix: added status bar text in contact filter
BE | 6af21fa8 | Karthick | 2025-12-17 10:29 | System / Access / Config | 2 | 113 | 1 | fix: include the lessthan and between operators in apply grid features method
FE | 9218e207 | Karthick | 2025-12-17 10:31 | Other / Shared | 4 | 227 | 129 | fix: handle the static value source int 360 filter fields
BE | ed962a18 | Karthick | 2025-12-17 12:09 | Communication | 13 | 10658 | 55 | chore: include webhook tracking log
BE | 77f63834 | Karthick | 2025-12-17 13:25 | Communication | 2 | 136 | 19 | fix: handle in and not in operator query builder seperatly
BE | 363989d9 | Karthick | 2025-12-17 15:11 | System / Access / Config | 1 | 166 | 20 | fix: handle min and max conditions rendering in apply grid feature
FE | 47b85274 | Karthick | 2025-12-18 13:20 | Communication | 5 | 498 | 206 | chore: implement 360 filter in email send job
BE | 536ad255 | Karthick | 2025-12-19 07:48 | System / Access / Config | 6 | 10259 | 21 | fix: remove unused fields in grid field entity
FE | 659cc240 | Karthick | 2025-12-19 15:59 | Other / Shared | 6 | 41 | 25 | fix: remove unused properties in grid field
BE | 60a392a2 | Karthick | 2025-12-24 17:33 | Communication | 13 | 21487 | 60 | fix: remove sortorder and add collectionpath field in placeholder definition entity
BE | d1c845de | Saranya C | 2025-12-24 17:39 | System / Access / Config | 7 | 10258 | 2 | fix: add filterrecipienttypeid in savedfilterconfiguration
FE | 25ef47f3 | Karthick | 2025-12-24 17:42 | Communication | 5 | 103 | 114 | fix: add aggregation placeholder properties to placeholder definition dtos query and mutation
FE | fa9aa53d | Saranya C | 2025-12-24 17:43 | Communication | 13 | 1326 | 250 | fix: update savedfilter menu into customized form
BE | 11bb53c3 | Saranya C | 2025-12-24 18:03 | Communication | 1 | 0 | 1 | fix: remove lastuserat property from savedfilter
FE | ada81730 | Saranya C | 2025-12-24 18:19 | Other / Shared | 18 | 347 | 131 | fix: make form fields uniform
BE | 8bddc14f | Karthick | 2025-12-24 19:30 | Communication | 6 | 36 | 42 | fix: remove auth for emailservice webhook
BE | 3c354c1f | Karthick | 2025-12-25 10:06 | Communication | 12 | 10302 | 16 | chore: add emailcc functionality in email service
BE | fcb23c36 | Saranya C | 2025-12-25 10:12 | Other / Shared | 2 | 23 | 1 | fix: update the publish profile
FE | 61bf1425 | Saranya C | 2025-12-25 10:17 | Communication | 8 | 709 | 140 | fix: conver the advanced grid to flow grid in email template screen
FE | d6999f4b | Karthick | 2025-12-25 13:08 | Other / Shared | 16 | 2712 | 100 | feat: implement placeholder builder component
FE | 1d32d1fe | Karthick | 2025-12-25 17:59 | Communication | 8 | 288 | 211 | chore: implement placeholder edit functionality in placeholder dropdown
BE | aadf53be | Kavinkumar Thirumalaisamy | 2025-12-26 10:26 | Reporting / Dashboard / Audit | 18 | 21475 | 2 | feat: Powerbireport(report imlementaion)
BE | 7d46b8c7 | Karthick | 2025-12-26 10:54 | Communication | 1 | 1 | 1 | fix: include placeholder type in get by id placeholder definition dbcontext
BE | c9e566fa | Karthick | 2025-12-26 16:16 | Communication | 6 | 178 | 196 | fix: remove ignore null value condition in mapping schemas
FE | cc0d464a | Karthick | 2025-12-26 16:17 | Communication | 26 | 3148 | 1731 | fix: test the crud operation in placeholder definition screen
FE | e28ecdd3 | Saranya C | 2025-12-26 16:43 | Other / Shared | 1 | 1 | 0 | fix: export email template stores in index
FE | c394f8e1 | Saranya C | 2025-12-26 17:42 | Other / Shared | 3 | 225 | 47 | fix: convert advancedgrid to flow customized in email template screen
FE | e6bad542 | Karthick | 2025-12-27 10:23 | Communication | 21 | 224 | 103 | fix: move email template screen under the email service route path
FE | 15d38027 | Saranya C | 2025-12-27 10:41 | Communication | 2 | 45 | 17 | fix: fix update issue in savedfilter
BE | d716b27a | Saranya C | 2025-12-27 10:46 | Communication | 1 | 5 | 1 | fix: display the emailcontenttype in emailtemplate screen
FE | e86b2068 | Karthick | 2025-12-27 11:08 | Communication | 7 | 356 | 16 | chore: implement placeholder suggestion component for email template subject
BE | af303868 | Kavinkumar Thirumalaisamy | 2025-12-27 11:20 | Reporting / Dashboard / Audit | 21 | 11432 | 7 | feat: power Bi (reports get all,and report data end point created)
FE | 3048d30a | Kavinkumar Thirumalaisamy | 2025-12-27 11:38 | Other / Shared | 14 | 845 | 0 | chore: power bi front end full impelementation changes
FE | e3200e0b | Karthick | 2025-12-27 11:58 | Other / Shared | 4 | 288 | 191 | fix: change date picker component in placeholder builder
BE | ba512143 | Karthick | 2025-12-27 12:11 | Contacts | 4 | 21 | 4 | fix: include company id to contact email and relationship
BE | f4d210a9 | Kavinkumar Thirumalaisamy | 2025-12-27 12:23 | Reporting / Dashboard / Audit | 1 | 113 | 113 | fix: comment for mutations in power bi
FE | e89a749c | Kavinkumar Thirumalaisamy | 2025-12-27 12:47 | Reporting / Dashboard / Audit | 1 | 3 | 2 | fix: power bi design changes
FE | be2ef4b1 | Karthick | 2025-12-27 14:04 | Other / Shared | 4 | 146 | 46 | chore: include default fetch functionality
BE | 284424e7 | Karthick | 2025-12-27 14:07 | Other / Shared | 1 | 2 | 2 | fix: change the country sort order direction in get all country
BE | d4b64f76 | Saranya C | 2025-12-27 14:29 | Contacts | 2 | 7 | 3 | fix: add companyid in code
FE | af76bf78 | Kavinkumar Thirumalaisamy | 2025-12-27 15:07 | Reporting / Dashboard / Audit | 1 | 5 | 4 | fix: power bi report design issues
FE | 322cc21f | Saranya C | 2025-12-27 15:46 | Communication | 2 | 7 | 2 | chore: add notes for fromemail field in emailtemplate screen
FE | 1b9113b5 | Karthick | 2025-12-28 12:23 | Other / Shared | 8 | 138 | 42 | fix: include placeholder code in form and add tooltip for placeholder in email template editor
FE | e1d974d2 | Karthick | 2025-12-29 13:22 | Reporting / Dashboard / Audit | 20 | 342 | 0 | feat: add power bi report master screen
BE | cd06af42 | Karthick | 2025-12-29 13:38 | Reporting / Dashboard / Audit | 18 | 686 | 52 | refactor: execute power bi report entity via automation
BE | fde76894 | Kavinkumar Thirumalaisamy | 2025-12-29 15:26 | Reporting / Dashboard / Audit | 19 | 31878 | 341 | fix: power bi report commonly set two folder to one folder
FE | 3be1ebc1 | Saranya C | 2025-12-29 16:04 | Contacts | 2 | 5 | 32 | fix: remove orderby and make nullable orderby,description in contacttype
BE | b57af761 | Saranya C | 2025-12-29 16:08 | Contacts | 9 | 21108 | 6 | fix: make nullable orderby , description fields in contacttype
BE | 09f9a237 | Saranya C | 2025-12-29 17:08 | Contacts | 7 | 10558 | 5 | fix: make nullable orderby and description in contactchannel
FE | de00de7e | Karthick | 2025-12-29 17:10 | Other / Shared | 4 | 771 | 0 | chore: implement autogenerate widget in rjsf
BE | ada4ef04 | Saranya C | 2025-12-30 10:30 | Contacts | 7 | 10560 | 5 | fix: make orderby and description as nullable in channeltype screen
FE | 451ac2f3 | Saranya C | 2025-12-30 10:31 | Contacts | 1 | 0 | 16 | fix: remove orderby in channeltype screen
BE | 466a81aa | Kavinkumar Thirumalaisamy | 2025-12-30 12:29 | Reporting / Dashboard / Audit | 15 | 10814 | 64 | fix: powerbireport master screen changes
FE | a7088ed0 | Kavinkumar Thirumalaisamy | 2025-12-30 12:32 | Reporting / Dashboard / Audit | 8 | 319 | 85 | fix: power bi report front changes
BE | 10019848 | Kavinkumar Thirumalaisamy | 2025-12-30 13:40 | Reporting / Dashboard / Audit | 18 | 11231 | 20 | feat: power bi user mapping new implementation completed
FE | fd0373f4 | Kavinkumar Thirumalaisamy | 2025-12-30 13:42 | Reporting / Dashboard / Audit | 15 | 290 | 1 | feat: front end implementation of power bi user mapping
FE | 8248cf6c | Kavinkumar Thirumalaisamy | 2025-12-30 15:56 | Reporting / Dashboard / Audit | 2 | 15 | 2 | fix: power bi ssr rendering warnings fixed
FE | cecc752b | Karthick | 2025-12-30 19:48 | Other / Shared | 43 | 4997 | 132 | fix: handle email template design when copy and paste
FE | 944f29d9 | Saranya C | 2025-12-31 10:47 | Contacts | 1 | 6 | 6 | fix: change label name unit type to program type
FE | 66341d17 | Saranya C | 2025-12-31 10:50 | Events & Auction | 2 | 5 | 3 | fix: change form field input to textarea
FE | b7ec6201 | Saranya C | 2025-12-31 10:55 | Other / Shared | 1 | 0 | 0 | fix: package conflict
BE | 4761b5c4 | Saranya C | 2025-12-31 10:59 | Contacts | 13 | 2954 | 87 | fix: fix export issue in contact module
BE | b6aa2deb | Karthick | 2025-12-31 11:47 | Contacts | 6 | 10619 | 6 | fix: change the unique index in contact type entity
BE | 9baf0337 | Saranya C | 2025-12-31 12:44 | Contacts | 3 | 447 | 68 | fix: fix export issue in contact and organizationalunit screen
BE | 8b8a7cc7 | Karthick | 2025-12-31 13:34 | Contacts | 7 | 10569 | 4 | chore: add contactchannelname is unique index in contact channel entity
BE | 765c65db | Saranya C | 2025-12-31 13:49 | Donations | 3 | 567 | 0 | fix: fix export issue in donation , donationdistribution screen
BE | ea77b5b9 | Karthick | 2025-12-31 13:50 | Contacts | 4 | 10619 | 4 | chore: add emil property is unique index in contactemailaddress entity
BE | d8675937 | Karthick | 2025-12-31 13:59 | Contacts | 4 | 10623 | 2 | chore: add unique index for phonenumber to contactphonenumber entity
BE | 3464d31f | Karthick | 2025-12-31 14:13 | Contacts | 4 | 10647 | 2 | chore: add unique index for relationname in contactrelationship entity
BE | 14d9bbf6 | Karthick | 2025-12-31 14:19 | Contacts | 4 | 10638 | 2 | chore: add unique index for link in contact social link entity
FE | a31047b5 | Saranya C | 2025-12-31 16:49 | Contacts | 1 | 1 | 1 | fix: update the contactcode in contactrelationship
FE | 71b23f45 | Karthick | 2025-12-31 17:23 | Contacts | 14 | 96 | 69 | fix: add isactive filter rule to fetch contact child details
FE | 7fad8e1b | Karthick | 2025-12-31 19:08 | Other / Shared | 4 | 348 | 2 | chore: add phone number validation to rjsf schema
FE | b24575bd | Karthick | 2025-12-31 19:24 | Other / Shared | 2 | 176 | 31 | fix: include parent object concept to data table print table option
BE | 36bc183d | Karthick | 2025-12-31 19:26 | Contacts | 10 | 267 | 8 | fix: add unique index validation rule in validator
FE | 6cee06f6 | Karthick | 2026-01-01 17:05 | System / Access / Config | 6 | 17 | 19 | fix: optimize the spaces in sidebar
FE | 0c73dfe0 | Karthick | 2026-01-01 19:09 | Other / Shared | 25 | 444 | 321 | fix: change advanced grid ui and ux
FE | ad749302 | Karthick | 2026-01-02 10:59 | Other / Shared | 5 | 298 | 76 | chore: implement column pinning option in grid
FE | f148a0e0 | Karthick | 2026-01-02 13:42 | Other / Shared | 15 | 1173 | 389 | fix: include data retrival option in advanced grid
BE | ec7547cb | Kavinkumar Thirumalaisamy | 2026-01-02 16:35 | Contacts | 116 | 21518 | 262 | fix: common entities move from contact to application changes
FE | c9526dcd | Karthick | 2026-01-02 16:36 | Other / Shared | 26 | 1327 | 415 | refactor: upgrade flow grid ui and ux
FE | 125ce6b3 | Kavinkumar Thirumalaisamy | 2026-01-02 16:38 | Contacts | 41 | 148 | 97 | fix: moved contact to application pages for common entities
FE | 1853c950 | Karthick | 2026-01-03 11:57 | Other / Shared | 23 | 810 | 512 | fix: handle proper skeletons for grids
BE | e7404a9b | Kavinkumar Thirumalaisamy | 2026-01-03 17:46 | System / Access / Config | 1 | 2 | 1 | removed line from branch
BE | 59633e52 | Kavinkumar Thirumalaisamy | 2026-01-03 17:49 | Campaigns / Crowdfund / P2P | 1 | 1 | 1 | fix: removed line from configuration
FE | 63514d71 | Karthick | 2026-01-03 19:34 | Other / Shared | 17 | 1785 | 1291 | fix: apply uniform style for all the rjsf widgets
FE | d07950e5 | Karthick | 2026-01-03 22:54 | Other / Shared | 192 | 1649 | 1117 | fix: apply common ui and ux for flow grid form fields and replace light icon to normal
FE | ef529066 | Karthick | 2026-01-04 21:09 | Contacts | 22 | 1835 | 2660 | refactor: redesign ui and ux functionalities
FE | b0e98a3c | Karthick | 2026-01-04 21:50 | Communication | 4 | 454 | 419 | fix: redesign saved filter screen with ui and ux
BE | f4468394 | Kavinkumar Thirumalaisamy | 2026-01-05 10:07 | System / Access / Config | 6 | 10668 | 3 | fix: Foreign key behaviour changes for cascade to restrict.
BE | 95bef50b | Kavinkumar Thirumalaisamy | 2026-01-05 10:16 | System / Access / Config | 4 | 10606 | 1 | fix: delete behaviour changes for userdashboards
FE | 14fa405f | Karthick | 2026-01-05 10:36 | Communication | 3 | 9 | 9 | fix: fix column alignment in view page from saved filter screen
BE | 54cf582f | Saranya C | 2026-01-05 11:14 | System / Access / Config | 489 | 5227 | 4815 | fix: change the setting business seperate command, query, validator and handler files into single f
BE | 04197781 | Saranya C | 2026-01-05 12:44 | System / Access / Config | 23 | 231 | 196 | fix: changed the staffs folder command,query, validator and handler files into single file.
FE | f6b4fee4 | Kavinkumar Thirumalaisamy | 2026-01-05 16:58 | Contacts | 2 | 175 | 208 | fix: oraganization unit flow grid form ui changes
BE | 5ffee30d | Saranya C | 2026-01-06 10:08 | System / Access / Config | 255 | 2477 | 2375 | fix: convert the CQRS files into single file in Application business and Auth business
BE | 6b6c8c0e | Saranya C | 2026-01-06 10:27 | System / Access / Config | 10 | 120 | 132 | fix: convert cqrs files of widgetrole into single file
FE | bb58cd3b | Kavinkumar Thirumalaisamy | 2026-01-06 11:18 | Contacts | 8 | 1203 | 1066 | fix: contact module custom form design changes (breadcrumbs,tab header)
FE | b569862f | Kavinkumar Thirumalaisamy | 2026-01-06 12:04 | Communication | 4 | 386 | 341 | fix: communication module new design changes fixes
BE | 90d82b44 | Saranya C | 2026-01-06 12:16 | Communication | 132 | 1388 | 1386 | fix: convert the cqrs files of notifybusiness into single file
BE | e5d06a7a | Saranya C | 2026-01-06 15:19 | Other / Shared | 398 | 3920 | 3831 | fix: convert the cqrs files of sharedbusiness into single file
BE | a9f4fee0 | Karthick | 2026-01-06 16:38 | Other / Shared | 29 | 1268 | 5 | feat: implement global search endpoint
FE | b827084c | Karthick | 2026-01-06 20:39 | Other / Shared | 27 | 2542 | 181 | feat: implement global search component
FE | a08f9f45 | Karthick | 2026-01-07 13:06 | Communication | 10 | 397 | 372 | refactor: apply unform design for the placeholder definition screen
BE | e9143463 | Karthick | 2026-01-07 18:35 | System / Access / Config | 18 | 21698 | 5 | feat: add entitytype and searchable entity and migration
BE | 1173db7b | Karthick | 2026-01-07 21:23 | Other / Shared | 8 | 66 | 12 | feat: include role access for global search endpoint
FE | eccff630 | Saranya C | 2026-01-08 12:14 | Other / Shared | 17 | 236 | 94 | fix: fix 360 degree save issue and set the loader for menus
FE | 5a0d6588 | Karthick | 2026-01-08 12:28 | Other / Shared | 3 | 5272 | 0 | docs: add approach docs for global search
FE | 0906b990 | Karthick | 2026-01-08 21:29 | Other / Shared | 19 | 91 | 133 | fix: build and fix the type issue
FE | f750d96a | Kavinkumar Thirumalaisamy | 2026-01-09 12:01 | Contacts | 9 | 100 | 2 | fix: child label widget added
BE | 550622d4 | Karthick | 2026-01-10 10:28 | System / Access / Config | 2 | 13 | 13 | fix: change fieldcode to fieldkey for delete opertion in custo fields
FE | cb712752 | Kavinkumar Thirumalaisamy | 2026-01-10 14:45 | Other / Shared | 2 | 487 | 193 | fix: drodown performance completed
BE | 93ec05a1 | Karthick | 2026-01-10 19:15 | Contacts | 17 | 32863 | 28 | chore: include custom field filteration logics in apply grid feature
FE | 4c95c04a | Karthick | 2026-01-11 19:20 | Other / Shared | 53 | 3517 | 345 | feat: implement custom field in flow grid and add filter for custom field
BE | ae976916 | Karthick | 2026-01-11 19:22 | System / Access / Config | 11 | 10823 | 12 | chore: add fieldtypeid to field entity and migration
BE | d093831f | Saranya C | 2026-01-12 13:13 | Reporting / Dashboard / Audit | 2 | 74 | 13 | <communicationreport>(<reportcreation>): <added new reports>
FE | cda0abed | Saranya C | 2026-01-12 14:03 | Communication | 7 | 263 | 1 | feat(communication): add generate reports P20-87
FE | 894e6af2 | Kavinkumar Thirumalaisamy | 2026-01-12 16:44 | Reporting / Dashboard / Audit | 2 | 3 | 3 | fix: icons changes
FE | b5a72e02 | Karthick | 2026-01-12 18:17 | Other / Shared | 38 | 1376 | 679 | chore: implement navigation for the global searched items P20-86
FE | 48239723 | Kavinkumar Thirumalaisamy | 2026-01-13 10:51 | Other / Shared | 11 | 399 | 343 | fix: report datatable and datatable advanced and flow design changes
FE | 61fd6a26 | Kavinkumar Thirumalaisamy | 2026-01-13 11:05 | Other / Shared | 1 | 11 | 11 | fix: build error fix
FE | 481a7a75 | Kavinkumar Thirumalaisamy | 2026-01-13 11:06 | Contacts | 2 | 8 | 4 | fix: build issue fixed
FE | 7370112d | Karthick | 2026-01-13 11:29 | System / Access / Config | 29 | 806 | 470 | feat: implement breadcrumb to all the screens with navigation PS20-96
FE | da1343d2 | Kavinkumar Thirumalaisamy | 2026-01-13 13:33 | Reporting / Dashboard / Audit | 14 | 26 | 26 | fix: icons issues fixes
FE | cf432688 | Karthick | 2026-01-13 15:25 | Other / Shared | 7 | 71 | 45 | fix: apply grid initial loading state true in grid store
BE | 2291a718 | Karthick | 2026-01-13 15:30 | Other / Shared | 4 | 17 | 1 | fix: add module code and name in global search result
FE | 4283ff43 | Saranya C | 2026-01-14 10:15 | Donations | 8 | 72 | 2 | feat(Donation): add new reports P20-88
FE | 92ffc2a7 | Karthick | 2026-01-14 11:28 | Other / Shared | 4 | 361 | 18 | feat: implement profile component base P20-97
FE | 34daf02d | Saranya C | 2026-01-14 11:30 | Donations | 1 | 1 | 1 | fix(donation): build issue fix P20-88
BE | ce48786a | Saranya C | 2026-01-14 11:45 | Other / Shared | 1 | 3 | 2 | fix(donation): add donationgeneratereport in decoratorreportmodules
BE | d39877eb | Saranya C | 2026-01-14 13:04 | Other / Shared | 1 | 1 | 0 | fix(donation): add decorator properties
BE | 992dee46 | Kavinkumar Thirumalaisamy | 2026-01-14 13:48 | System / Access / Config | 7 | 10866 | 7 | fix: quick filter - backend dashboard added dropdown based filteration - P20-95
FE | 96f9b53b | Kavinkumar Thirumalaisamy | 2026-01-14 13:50 | Reporting / Dashboard / Audit | 20 | 3895 | 189 | feat: quick filter - front end dashboard added dropdown based filteration - P20-95
FE | 7e4ed699 | Karthick | 2026-01-18 07:56 | Other / Shared | 18 | 4925 | 1276 | fix: prevent the copy paste content in email editor
FE | ba02b26e | Karthick | 2026-01-19 08:56 | Other / Shared | 26 | 3040 | 100 | feat: implement shortcut keys base P20-98
FE | c26bf3f5 | Saranya C | 2026-01-19 11:24 | Reporting / Dashboard / Audit | 2 | 2 | 5 | fix(donation): add dropdown label in apiselectv2 P20-88
FE | dab4bffb | Kavinkumar Thirumalaisamy | 2026-01-20 10:09 | Reporting / Dashboard / Audit | 8 | 1009 | 1 | fix: dashboard - implemented geographical dashboard - P20-57
BE | cc4f55bc | Saranya C | 2026-01-20 10:24 | Reporting / Dashboard / Audit | 2 | 6 | 2 | fix(donation): fix export issue in report P20-88
FE | 6db311b9 | Karthick | 2026-01-20 11:51 | Other / Shared | 6 | 1708 | 69 | fix: prevent bullet mark and flex from email content in email editor P20-90
FE | ca178359 | Karthick | 2026-01-20 11:51 | Other / Shared | 6 | 1708 | 69 | fix: prevent bullent mark and flex from email content in email editor P20-90
FE | 6df982cd | Karthick | 2026-01-20 13:15 | Other / Shared | 1 | 3 | 4 | fix: hide the gird view option
BE | 997298a5 | Karthick | 2026-01-20 17:35 | Other / Shared | 3 | 49 | 1 | fix: change database connection string and publish profile for uat
BE | 94e1f69a | Karthick | 2026-01-20 18:16 | System / Access / Config | 1 | 1 | 1 | fix: change database in connection string
FE | 83951c2a | Saranya C | 2026-01-21 17:41 | Reporting / Dashboard / Audit | 5 | 838 | 162 | feat(donation): implement dashboard P20-94
FE | 747ea288 | Karthick | 2026-01-21 22:55 | Other / Shared | 33 | 1374 | 878 | fix: handle ui ux and mobile compatibility in over all layout part 1 P20-99
FE | d1a8073e | Saranya C | 2026-01-22 16:55 | Communication | 2 | 7 | 2 | fix(communication): fix auto job code generation issue in email send job
FE | 3d58d306 | Karthick | 2026-01-22 19:44 | Other / Shared | 30 | 1530 | 1468 | fix: handle ui ux and mobile compatibility in modals and form fields P20-99
FE | b5cd07b9 | Karthick | 2026-01-26 16:39 | Other / Shared | 125 | 3909 | 2275 | fix: handle ui ux and device compatibility for grids part 1 P20-99
FE | 31c57a10 | Karthick | 2026-01-26 19:21 | Other / Shared | 15 | 150 | 25 | fix: add ux for grid bookmarks P20-99
BE | 2c1cabdf | Karthick | 2026-01-27 16:20 | System / Access / Config | 5 | 19 | 10 | fix: include contact role capability to user role capability and companyid include in the blob stora
FE | 6c70ce8f | Karthick | 2026-01-27 16:53 | Other / Shared | 8 | 679 | 443 | fix: add profile photo upload functionality P20-97
FE | dad9d13f | Saranya C | 2026-01-27 18:16 | Other / Shared | 8 | 517 | 9 | feat(communication): add new dashboard P20-93
BE | 48587eb6 | Karthick | 2026-01-28 09:58 | System / Access / Config | 7 | 10802 | 10 | fix: add companyid to role entity and migration P20-100
BE | dbe6e64a | Karthick | 2026-01-28 10:15 | Donations | 8 | 10821 | 6 | fix: add companyid to donation purpose entity and migration P20-100
BE | ca4b36d0 | Karthick | 2026-01-28 10:27 | Donations | 7 | 10831 | 1 | fix: add companyid to donation category entity and migration P20-100
BE | 06a4a553 | Karthick | 2026-01-28 10:38 | Donations | 7 | 10849 | 1 | fix: add companyid to donation group entity and migration
BE | 722b674b | Karthick | 2026-01-28 10:53 | Reporting / Dashboard / Audit | 7 | 10881 | 0 | fix: add companyid to report entity and migration P20-100
BE | e5d874a9 | Karthick | 2026-01-28 11:15 | Reporting / Dashboard / Audit | 7 | 10897 | 0 | fix: add companyid to dahsboard entity and migration P20-100
BE | f6e4729f | Karthick | 2026-01-28 11:32 | System / Access / Config | 7 | 10918 | 1 | fix: add companyid to staff category entity and migration P20-100
BE | f4cb9520 | Karthick | 2026-01-28 11:47 | Contacts | 7 | 10932 | 6 | fix: add issystem to contact schema entity with migration P20-100
BE | e118f801 | Karthick | 2026-01-28 12:33 | Communication | 13 | 11146 | 33 | fix: add companyid to notify schema entities and migration
BE | 3b33c6e7 | Karthick | 2026-01-28 12:57 | System / Access / Config | 17 | 11297 | 10 | fix: add companyid to setting schema entities and migration
BE | df72f6dd | Karthick | 2026-01-28 13:33 | Other / Shared | 12 | 11 | 35 | fix: clean up the unused using in shared configuration
BE | 09bf6640 | Karthick | 2026-01-28 14:46 | System / Access / Config | 34 | 3744 | 56 | fix: aet primary key as nullable in entity schemas
BE | e2f2ca4d | Karthick | 2026-01-28 14:46 | System / Access / Config | 34 | 56 | 3744 | Revert "fix: aet primary key as nullable in entity schemas"
BE | f2a6c2be | Karthick | 2026-01-28 14:48 | System / Access / Config | 34 | 3744 | 56 | Reapply "fix: aet primary key as nullable in entity schemas"
BE | c2894ac1 | Karthick | 2026-01-28 15:50 | System / Access / Config | 2 | 2 | 2 | fix: increase the menuicon property length in menu entity mutations P20-100
BE | 55f9948a | Karthick | 2026-01-28 18:12 | Other / Shared | 1 | 30 | 21 | fix: include issystem property to tenant context
FE | a7d45177 | Karthick | 2026-01-29 17:19 | System / Access / Config | 28 | 674 | 186 | feat: implement role module configuration in role capability editor P20-100
FE | 4d784313 | Karthick | 2026-01-29 19:30 | System / Access / Config | 4 | 69 | 43 | fix: handle z-index in the role capability modal actions
BE | 7bfab478 | Karthick | 2026-01-29 19:36 | System / Access / Config | 3 | 59 | 1 | feature: implement role module update mutation for with collection support
BE | f7526f06 | Karthick | 2026-01-30 12:07 | System / Access / Config | 5 | 11030 | 0 | feature: add issystem field in master data entity and migration P20-100
FE | 1d4bd68b | Karthick | 2026-01-30 22:28 | Other / Shared | 36 | 673 | 645 | fix: qa test issue fix P20-101
FE | bb7ab02a | Saranya C | 2026-01-31 10:09 | Other / Shared | 7 | 1586 | 3 | fix(contact): fix issue in daterangepicker
BE | e384e856 | Saranya C | 2026-01-31 10:11 | System / Access / Config | 4 | 5 | 5 | fix: change issystemtype to issystem in masterdatatype column
FE | fadd4e74 | Karthick | 2026-01-31 10:12 | Contacts | 7 | 165 | 36 | fix: disable the not developed menus in profile component P20-100
FE | f2cb4af9 | Karthick | 2026-01-31 14:39 | Contacts | 17 | 1036 | 1161 | fix: apply contact screen ui and functionality to program screen P20-101
FE | 49f7b936 | Karthick | 2026-01-31 14:57 | Other / Shared | 3 | 5 | 4 | fix: build and fix the type issue P20-101
FE | 5addc5e6 | Karthick | 2026-01-31 15:52 | Other / Shared | 10 | 59 | 37 | fix: add comming soon in the keyboard shortcut key modal P20-100
FE | b064ca66 | Kavinkumar Thirumalaisamy | 2026-01-31 19:24 | System / Access / Config | 33 | 8005 | 216 | feat: contact grid import front end changes - P20-92
BE | 887544dc | Kavinkumar Thirumalaisamy | 2026-01-31 19:26 | System / Access / Config | 69 | 85153 | 1 | feat: Newly added Grid import - P20-92
FE | 2e3ccec8 | Kavinkumar Thirumalaisamy | 2026-01-31 19:28 | Other / Shared | 1 | 4 | 4 | fix: base url changes
BE | 91b2b280 | Kavinkumar Thirumalaisamy | 2026-02-01 11:10 | System / Access / Config | 5 | 108 | 13 | fix: changes for timeour error for laong data process -P20-92
FE | 0982079e | Kavinkumar Thirumalaisamy | 2026-02-02 13:31 | System / Access / Config | 37 | 1324 | 146 | fix: import relevant changes
BE | 72c7360f | Kavinkumar Thirumalaisamy | 2026-02-02 13:32 | System / Access / Config | 21 | 1183 | 29 | New : import session log screen implemented
FE | a0293ce7 | Saranya C | 2026-02-02 19:54 | Other / Shared | 13 | 679 | 253 | fix(communication): fix ui-ux mobile compatability in savedfilter screen
FE | 60053509 | Saranya C | 2026-02-03 14:00 | Communication | 8 | 296 | 53 | fix(communication): change ui-ux mobile comaptability in placeholder definition screen
FE | 7fe5a80b | Saranya C | 2026-02-03 16:23 | Communication | 5 | 367 | 142 | fix(communication): change ui-ux mobile compatability in emailtemplate screen
FE | 5224e3df | Saranya C | 2026-02-04 06:32 | Communication | 10 | 410 | 237 | fix(communication): change ui-ux mobile compatability in emailsendjob screen
BE | 99f64c35 | Kavinkumar Thirumalaisamy | 2026-02-04 10:59 | System / Access / Config | 13 | 23595 | 396 | import system : downloading lookups conditional changes - P20-78
BE | 25669de5 | Karthick | 2026-02-04 14:18 | Other / Shared | 7 | 4561 | 0 | feature: preapre document for multi tenant implenentation P20-100
FE | 9960b956 | Kavinkumar Thirumalaisamy | 2026-02-04 14:24 | System / Access / Config | 17 | 2587 | 557 | fix: import new changes for signalR connecting and job rewrited
BE | c5169350 | Karthick | 2026-02-04 15:43 | System / Access / Config | 1 | 1 | 1 | fix: change connection string from uat to dev
BE | 258b0f43 | Karthick | 2026-02-04 15:53 | System / Access / Config | 1 | 1 | 2 | fix: change connection string from uat to dev
FE | d9bdfa0a | Kavinkumar Thirumalaisamy | 2026-02-04 17:59 | System / Access / Config | 3 | 40 | 9 | fix: fixes of import - P20-78
BE | f23be301 | Kavinkumar Thirumalaisamy | 2026-02-04 18:00 | System / Access / Config | 1 | 8 | 4 | fix: fixes of order by in template generation of import - P20-78
FE | 50fb53a1 | Kavinkumar Thirumalaisamy | 2026-02-04 18:16 | System / Access / Config | 1 | 1 | 1 | fix: build issue for import
BE | 82ee4f1b | Karthick | 2026-02-04 18:18 | System / Access / Config | 3 | 1052 | 596 | feature: add proper seed data for country currency state P20-102
FE | 6752cb31 | Saranya C | 2026-02-05 00:00 | Reporting / Dashboard / Audit | 20 | 583 | 250 | fix(communication): fix ui-ux mobile compatability in generate report
FE | 78a7ceb7 | Saranya C | 2026-02-05 05:18 | Communication | 4 | 14 | 12 | fix(communication): set breadcrumb path in communication module
FE | 200347ed | Saranya C | 2026-02-05 05:25 | Communication | 6 | 119 | 9 | fix(communication): add recipienttypeid in placeholderdefinitions mutations
FE | 6cec04f5 | Kavinkumar Thirumalaisamy | 2026-02-05 10:08 | System / Access / Config | 6 | 358 | 21 | fix: excel export issues resolved - P20 - 78
FE | f569242b | Kavinkumar Thirumalaisamy | 2026-02-05 10:09 | Other / Shared | 1 | 2 | 2 | fix: config changes
FE | cae2fa4f | Kavinkumar Thirumalaisamy | 2026-02-05 10:33 | System / Access / Config | 3 | 174 | 26 | fix: file upload issue fixed - P20 - 78
BE | 9fe01363 | Karthick | 2026-02-05 12:47 | System / Access / Config | 7 | 45412 | 1745 | feature: add proper seed data for district pincode and states P20-102
FE | 7a48f19a | Kavinkumar Thirumalaisamy | 2026-02-05 14:53 | System / Access / Config | 1 | 0 | 2 | fix: sample download template getting error - P20-78
BE | 16d1383e | Karthick | 2026-02-06 14:23 | System / Access / Config | 6 | 54284 | 40537 | fix: add proper seed data for district localities states and pincodes P20-102
BE | cc1fdb73 | Karthick | 2026-02-06 17:39 | System / Access / Config | 5 | 20090 | 16722 | fix: update database values to region seed data json files
FE | 17e58aa0 | Saranya C | 2026-02-09 12:29 | Reporting / Dashboard / Audit | 44 | 5077 | 13 | fix: display the dashboard widgets table using grid data-table-form
BE | 307fe771 | Saranya C | 2026-02-09 12:46 | Communication | 9 | 11083 | 5 | fix(communication): add recipienttypeid property in placeholderdefinion entity.
BE | 3a425840 | Karthick | 2026-02-09 12:46 | Other / Shared | 21 | 0 | 892 | fix: remove backup email service implementation
FE | bdbaf18e | Karthick | 2026-02-09 14:21 | Donations | 13 | 428 | 0 | feat: add online donation screen P20-46
BE | c174f4f4 | Karthick | 2026-02-09 14:22 | Donations | 22 | 12727 | 5 | feat: add online donation entity and migration P20-46
FE | e1187ef7 | Kavinkumar Thirumalaisamy | 2026-02-10 11:41 | System / Access / Config | 3 | 62 | 65 | fix: filtering stage data's fixed - P20-78
BE | bca9b13f | Karthick | 2026-02-11 10:54 | Donations | 19 | 11932 | 2 | fix: add organization unit to donation purpose and parent tables
FE | a152a28e | Saranya C | 2026-02-11 12:12 | Contacts | 5 | 216 | 2 | fix(contact): add recent dobation in contact screen
BE | 5e19f9a8 | Saranya C | 2026-02-11 12:15 | Contacts | 3 | 22 | 7 | fix(contact): add recent donation in contact screen
BE | d0b684dd | Karthick | 2026-02-11 14:43 | Donations | 14 | 11840 | 24 | fix: remove organizationalunitid in donation category and group entity
FE | 73c5e7de | Saranya C | 2026-02-11 15:39 | System / Access / Config | 11 | 43 | 0 | fix(organization): move organization relevant screens from contact to organization module
BE | 022442ef | Karthick | 2026-02-11 17:15 | Donations | 21 | 12586 | 5 | feat: add contact donation purpose entity and migration P20-105
FE | 6a83ab69 | Karthick | 2026-02-11 17:22 | Donations | 13 | 264 | 1 | feat: add contact donation purpose screen P20-105
BE | d9a86983 | Karthick | 2026-02-13 13:47 | Donations | 6 | 11918 | 6 | fix: change unique index in donation purpose entity and parent entity P20-102
FE | 177d24a5 | Kavinkumar Thirumalaisamy | 2026-02-13 16:32 | Reporting / Dashboard / Audit | 4 | 15 | 3 | fix: power-bi response issue fixed
BE | 7f58fa3f | Kavinkumar Thirumalaisamy | 2026-02-13 16:32 | Reporting / Dashboard / Audit | 6 | 46 | 32 | fix: power bi staff issue fixed
FE | 87eb01ee | Saranya C | 2026-02-13 16:53 | Donations | 22 | 1087 | 42 | fix(organization): add the program type donation purpose tab in program screen
BE | 9ddb113a | Saranya C | 2026-02-13 16:57 | Donations | 8 | 132 | 10 | fix(organization): add donation purpose tab in program screen
BE | 71360a14 | Karthick | 2026-02-13 21:59 | Contacts | 4 | 11861 | 6 | fix: add pkreferenceid into contact donation purpose entity P20-102
BE | 22acaa80 | Karthick | 2026-02-16 11:52 | Donations | 5 | 11875 | 0 | fix: add pkreferenceid to donation entity P20-102
BE | ff2e453a | Karthick | 2026-02-16 12:39 | Communication | 24 | 24705 | 2 | feat: add contact prayer request entity and migration P20-106
FE | 69a5942c | Karthick | 2026-02-16 12:40 | Communication | 13 | 296 | 2 | feat: implement contact prayer request screen P20-106
FE | 03b09f0a | Karthick | 2026-02-16 14:27 | Reporting / Dashboard / Audit | 2 | 93 | 105 | fix: add proper dashboard icons in dashboard creation modal P20-99
BE | bd57354d | Karthick | 2026-02-16 16:02 | Donations | 12 | 12001 | 19 | fix: change source type foreign key relation in donation entity and add migration
BE | c331e04b | Karthick | 2026-02-16 19:41 | Donations | 14 | 23960 | 16 | fix: add pkreferenceid in cheque and online donation entity P20-102
BE | 76b66a6e | Karthick | 2026-02-16 21:41 | Donations | 11 | 36116 | 20 | fix: change non required properties as nullable in online donation entity P20-102
FE | 3dcfa5a8 | Karthick | 2026-02-17 09:39 | Reporting / Dashboard / Audit | 7 | 14 | 1 | fix: fix the save issue while dashboard creation P20-101
FE | f6096509 | Saranya C | 2026-02-17 10:14 | Donations | 9 | 826 | 10 | fix(donation): implement view-page in donation screen
BE | 07bf7912 | Saranya C | 2026-02-17 10:19 | Donations | 4 | 92 | 9 | fix(donation) : implement view-page in donation screen
FE | d2040c18 | Karthick | 2026-02-17 11:12 | Other / Shared | 5 | 76 | 14 | fix: add user based global recent search P20-101
FE | 31b89a85 | Saranya C | 2026-02-17 13:22 | Other / Shared | 6 | 32 | 31 | fix: fix communication details issue in contact screen
BE | 1495a780 | Saranya C | 2026-02-18 10:38 | Communication | 5 | 1132 | 0 | fix: fix export issue in communication module.
FE | 416441a9 | Saranya C | 2026-02-18 10:43 | Other / Shared | 2 | 34 | 137 | fix: fix bug list issues in contact module
BE | c886d58d | Karthick | 2026-02-18 18:31 | Other / Shared | 2 | 2551 | 0 | feat: add field and data level approach docs
BE | 5a4c2293 | Karthick | 2026-02-18 18:59 | System / Access / Config | 9 | 23932 | 6 | fix: add issystem field to grid child entity P20-111
BE | 1c04b783 | Saranya C | 2026-02-18 20:30 | System / Access / Config | 7 | 11960 | 1 | fix(hrms): fix the issue in staff screen p20-110
FE | 3aae613d | Saranya C | 2026-02-18 20:32 | System / Access / Config | 10 | 988 | 536 | fix(hrms): fix the issue in staff screen and change into flow grid component p20-110
BE | b75dd009 | Karthick | 2026-02-19 11:23 | Communication | 16 | 12494 | 3 | fix: add test email send service for email template test P20-109
FE | d54bbbb0 | Karthick | 2026-02-19 11:37 | Communication | 6 | 518 | 2 | feat: implement test email service in email send job screen P20-109
BE | 0658757e | Karthick | 2026-02-19 14:45 | System / Access / Config | 2 | 44 | 12 | feat: remove tenant filter in getstaff endpoint for business admin P20-109
FE | 656c5ef4 | Saranya C | 2026-02-19 14:45 | System / Access / Config | 5 | 58 | 3 | fix(hrms): add companyid field based on businessadmin role in staff screen
BE | eb061577 | Saranya C | 2026-02-19 14:49 | System / Access / Config | 17 | 35942 | 24 | fix(hrms): add companyid field based on businessrole in staff screen
BE | 527c8af6 | Karthick | 2026-02-19 16:26 | System / Access / Config | 2 | 30 | 5 | fix: remove tenant filter in getstaffbyid and userrolebyuserid handler P20-109
BE | f976a25d | Karthick | 2026-02-20 12:47 | Contacts | 62 | 9611 | 0 | feat: add all the triggers and functions from database in to scripts folders
FE | aafdc3a9 | Saranya C | 2026-02-20 16:52 | Donations | 3 | 118 | 120 | fix(donation): implement the donation view page and make navigation from recent donation
FE | 674d82c2 | Saranya C | 2026-02-20 17:40 | Donations | 2 | 6 | 3 | fix(donation): update the recent donation to show only in view mode and make navigate to donation
FE | 3bcedb6b | Kavinkumar Thirumalaisamy | 2026-02-23 10:05 | System / Access / Config | 1 | 435 | 164 | fix: master dashboard changes - P20-112
BE | 63832d01 | Karthick | 2026-02-23 12:03 | System / Access / Config | 1 | 1 | 1 | fix: temp hide the user exists validation in assign user role endpoint
BE | 4549d473 | Karthick | 2026-02-23 19:25 | System / Access / Config | 20 | 12863 | 1 | feat: add staff company entity and migration P20-113
FE | 47580c59 | Karthick | 2026-02-23 19:27 | System / Access / Config | 13 | 331 | 1 | feat: add staff company screen P20-113
BE | 6baccf7b | Karthick | 2026-02-24 16:47 | System / Access / Config | 13 | 12438 | 46 | fix: change staffid to userid in staff company table P20-100
FE | 773d3bfa | Saranya C | 2026-02-25 09:56 | Communication | 18 | 878 | 18 | fix(communication): fix the issue in communication module and add companyemailconfiguration screen
BE | 2a0f90b9 | Saranya C | 2026-02-25 11:49 | Communication | 24 | 37048 | 1 | fix(communication): add the companyemailconfiguration screen through automation
FE | dafb813d | Saranya C | 2026-02-25 13:15 | Communication | 6 | 43 | 1 | fix(communication): display the emailconfiguration header and footer field in emailsendjob screen
BE | dabb304d | Saranya C | 2026-02-25 13:17 | Communication | 7 | 12093 | 2 | fix(communication): add migration of emailconfigurationid property in emailsendjobs entity
FE | d2afd80d | Saranya C | 2026-02-25 16:58 | Communication | 5 | 561 | 141 | fix(communication): Add new program in Program dropdown fields in emailsendjob screen
FE | 993f75c3 | Saranya C | 2026-02-26 13:30 | Contacts | 7 | 24 | 20 | fix(contact): fix the issue as not refreshing the page after deletion in contact screen
BE | e1d37ea1 | Saranya C | 2026-02-26 13:32 | Contacts | 13 | 48214 | 71 | fix(contact): update unique index of contactrelationship entity with migration.
BE | e112163a | Karthick | 2026-02-26 13:50 | System / Access / Config | 34 | 2636 | 232 | feat: implement tenant service with hybrid support data filtration
FE | 56538b8c | Saranya C | 2026-02-26 15:11 | System / Access / Config | 1 | 978 | 598 | fix: update the master dashboard to older version
BE | e24952fb | Karthick | 2026-02-27 11:46 | System / Access / Config | 17 | 761 | 31 | feat: implement auto scope service to decide accessible or current scope type P20-100
FE | 6be98071 | Karthick | 2026-02-27 16:44 | System / Access / Config | 12 | 741 | 314 | feat: add staff company assignment tab in staff screen P20-113
BE | e446c0d2 | Karthick | 2026-02-27 16:46 | System / Access / Config | 10 | 162 | 20 | feat: add tenant decorator for staff relevent entities P20-113
BE | a6113e8f | Karthick | 2026-02-28 09:45 | System / Access / Config | 1 | 1 | 1 | fix: apply get set to company id in staff entity P20-100
FE | d04e8f3a | Karthick | 2026-03-02 12:26 | System / Access / Config | 12 | 432 | 46 | feat: implement company switching component P20-100
BE | 17a3b046 | Karthick | 2026-03-02 12:38 | System / Access / Config | 72 | 164 | 132 | feat: implement accessspolicy in tenant filter P20-100
FE | 98be39de | Karthick | 2026-03-03 15:54 | Communication | 26 | 2147 | 281 | feat: add crud operation for email configuration in email send job screen P20-100
BE | 0db61ee3 | Karthick | 2026-03-03 15:58 | Communication | 15 | 147 | 36 | feat: implement email header and footer template service in email send job P20-100
FE | eb365391 | Karthick | 2026-03-03 18:55 | System / Access / Config | 2 | 41 | 81 | fix: apply minimal loading animation for module loader P20-99
BE | 63fe9187 | Karthick | 2026-03-03 18:59 | Contacts | 42 | 12400 | 401 | fix: apply companyid to all the db scripts and change unique index for dashboard entity based on com
FE | f042108b | Saranya C | 2026-03-03 19:07 | Reporting / Dashboard / Audit | 8 | 67 | 16 | fix(contact): fix 360 filteration dropdown issue in contact screen
FE | 63e10e90 | Karthick | 2026-03-04 14:56 | Communication | 21 | 466 | 206 | fix: improve the ux in email send job screen P20-99
FE | d5f5583e | Karthick | 2026-03-05 16:00 | Other / Shared | 32 | 771 | 235 | fix: split the advanced and 360 degree filter P20-115
BE | cfa0d964 | Karthick | 2026-03-05 16:03 | System / Access / Config | 5 | 179 | 27 | fix: split the advanced filter and 360 degree filter P20-115
FE | 8e8a3e01 | Karthick | 2026-03-10 17:17 | System / Access / Config | 6 | 62 | 17 | fix: fix the merge conflict issue in staff company screen
FE | b3875432 | Saranya C | 2026-03-11 17:30 | Other / Shared | 16 | 256 | 93 | fix(contact): set the automatic filter (isdefault=true) when loading the grid
BE | cd249d20 | Saranya C | 2026-03-11 17:35 | System / Access / Config | 8 | 12202 | 6 | fix(contact): add the migration of aggregationfilterquery in usergridfilter entity P20-116
BE | 8945878f | Karthick | 2026-03-11 21:44 | Contacts | 27 | 61218 | 38 | feat: implement family functionality P20-120
BE | 12e866b6 | Karthick | 2026-03-12 19:32 | Donations | 11 | 24809 | 11 | feat: add donation details column in contact donation purpose entity and migration P20-121
BE | 6480619e | Kavinkumar Thirumalaisamy | 2026-03-14 10:10 | Communication | 9 | 380 | 2 | add: masterdashboard feature
FE | 13769415 | Kavinkumar Thirumalaisamy | 2026-03-14 10:12 | System / Access / Config | 3 | 860 | 945 | fix: added master dashboard new deisgns
BE | 80919aa9 | Karthick | 2026-03-16 20:56 | System / Access / Config | 7 | 12324 | 0 | fix: add branch source in branch entity and migration P20-102
BE | 2716f732 | Karthick | 2026-03-17 17:52 | Donations | 61 | 14108 | 638 | fix: convert the donation table in pss1.0 donation table structure part1 P20-46
BE | c563af6a | Saranya C | 2026-03-17 18:58 | Contacts | 20 | 342 | 23 | fix(contact): to prevent the deleting of pk that is refrenced in fk of childtable and prevent the so
BE | 381ebf44 | Karthick | 2026-03-17 19:01 | Donations | 52 | 15739 | 18 | fix: convert the donation child table in globally P20-46
FE | 18f2ab10 | Karthick | 2026-03-17 19:02 | Donations | 37 | 1543 | 456 | fix: convert the donation child screens in globally P20-46
FE | bc6ead0a | Saranya C | 2026-03-17 19:06 | Contacts | 3 | 11 | 11 | fix(contact): dropdown should be searchable with dependency column P20-119
BE | 4f6590d5 | Karthick | 2026-03-17 19:46 | Donations | 14 | 13266 | 179 | fix: convert donation distribution table structure as pss1.0 P20-46
FE | 398e2823 | Karthick | 2026-03-17 19:49 | Donations | 3 | 52 | 118 | fix: convert donation distribution mutation as pss1.0 P20-46
BE | 7d7b443d | Karthick | 2026-03-18 10:40 | Donations | 19 | 14045 | 513 | fix: convert online donation table strcuture as pss1.0 P20-46
FE | 4e4a7465 | Karthick | 2026-03-18 10:42 | Donations | 3 | 218 | 254 | fix: convert online donation entity and mutation properties to pss1.0 P20-46
BE | 784196ec | Karthick | 2026-03-18 11:03 | Events & Auction | 20 | 13548 | 0 | feat: add product entity and migration P20-46
FE | e7595a62 | Karthick | 2026-03-18 11:06 | Events & Auction | 13 | 289 | 0 | feat: add product screen and mutation P20-46
BE | 6ada0ec3 | Karthick | 2026-03-18 11:44 | Reporting / Dashboard / Audit | 25 | 13725 | 1 | feat: add trackingdata entity and migration P20-46
BE | 573c9194 | Karthick | 2026-03-18 12:24 | Donations | 25 | 14058 | 0 | fix: add online donation distribution entity and migration P20-123
FE | f9bdb3ca | Karthick | 2026-03-18 12:25 | Donations | 7 | 223 | 0 | feat: add online donation distribution table mutations and queries P20-123
BE | 0b6036c1 | Karthick | 2026-03-18 13:35 | Finance / Payment / Receipt | 22 | 14515 | 458 | fix: change receipt donation entity as pss1.0 P20-46
FE | 9bc4e6f8 | Karthick | 2026-03-18 13:35 | Finance / Payment / Receipt | 3 | 286 | 187 | fix: change receipt donation field as pss1.0 P20-46
BE | 3f573570 | Karthick | 2026-03-18 13:59 | Finance / Payment / Receipt | 21 | 14027 | 0 | feat: add receipt donation entity and migration P20-124
FE | d286c51b | Karthick | 2026-03-18 14:01 | Donations | 7 | 171 | 0 | feat: add receipt donation distribution entity and mutations P20-124
BE | 1d92e9f6 | Karthick | 2026-03-18 14:48 | Donations | 24 | 14388 | 0 | feat: add secondary online donation entity and migration P20-125
FE | d4048e19 | Karthick | 2026-03-18 14:50 | Donations | 7 | 279 | 0 | feat: add secondary online donation entity and mutation P20-125
FE | 58082700 | Karthick | 2026-03-18 15:01 | Donations | 7 | 181 | 0 | feat: add secondary online donation distribution entity P20-126
BE | a2b4fbc4 | Karthick | 2026-03-18 15:03 | Donations | 21 | 14349 | 0 | feat: add secondary online donation entity and migration P20-126
FE | 67c75129 | Saranya C | 2026-03-18 18:12 | Contacts | 6 | 75 | 37 | fix(contact): implement family configuration functionality and relationship mapping p20-120
BE | 1899afdf | Karthick | 2026-03-18 19:04 | Donations | 15 | 13916 | 17 | fix: change donation mode to payment mode in donation entity P20-46
BE | d692177f | Saranya C | 2026-03-19 10:07 | Contacts | 6 | 267 | 26 | fix(contact): Implement the family screen with export P20-120
BE | 71372d8d | Karthick | 2026-03-19 12:40 | Donations | 11 | 13899 | 11 | fix: change donationpurposeid to organizationalunitid in donation distribution entity P20-46
BE | f4fae9fa | Karthick | 2026-03-19 13:42 | Donations | 6 | 13848 | 0 | fix: add pkreferenceid to online donation tables P20-46
FE | 9393889a | Saranya C | 2026-03-19 15:51 | Donations | 7 | 82 | 55 | fix(contact): fix the issues in contact screen because of donation migration
BE | 77a63fd5 | Saranya C | 2026-03-19 15:54 | Donations | 2 | 3 | 3 | fix(contact): fix the issues in contact screen because of donation migration
FE | 45702b86 | Kavinkumar Thirumalaisamy | 2026-03-19 17:12 | System / Access / Config | 2 | 537 | 0 | feat: added role viewer by staff companies - pss 2.0 hrms module
FE | fb691715 | Kavinkumar Thirumalaisamy | 2026-03-19 17:14 | System / Access / Config | 1 | 1 | 1 | fix: added styles
FE | 56538c5a | Kavinkumar Thirumalaisamy | 2026-03-19 17:28 | System / Access / Config | 1 | 63 | 22 | fix: added styles part 2
BE | 5fcac79b | Saranya C | 2026-03-19 18:53 | System / Access / Config | 5 | 13828 | 0 | fix(communication): save the field filter and aggregation filter with seperate column in saved filte
FE | a2091081 | Saranya C | 2026-03-19 18:55 | Communication | 4 | 73 | 24 | fix(communication): save field filter,aggregation filter separately in saved filter entity p20-122
BE | 7d925fda | Karthick | 2026-03-19 19:46 | Donations | 29 | 55421 | 55 | fix: remove the donationid in online donation P20-46
BE | 55d95198 | Karthick | 2026-03-20 00:55 | Donations | 27 | 69071 | 21 | fix: change proper datatypes and nullable properties in donation relevant tables P20-46
BE | 3414345f | Karthick | 2026-03-20 10:41 | Donations | 18 | 14223 | 0 | feat: add bulk donation entity and migration P20-127
FE | 5b9a3796 | Karthick | 2026-03-20 10:44 | Donations | 13 | 239 | 6 | feat: add bulkdonation screen and mutations P20-127
BE | c5362df4 | Kavinkumar Thirumalaisamy | 2026-03-20 10:54 | System / Access / Config | 1 | 46 | 1 | fix: role creation after menu access given for module,menu,rolemodule
BE | 055a07b0 | Karthick | 2026-03-20 11:00 | Donations | 22 | 14405 | 0 | feat: add bulk donation distribution entity and migration P20-127
FE | 82f556af | Karthick | 2026-03-20 11:00 | Donations | 13 | 267 | 0 | feat: add bulk donation distribution screen P20-127
BE | 5a11f866 | Karthick | 2026-03-20 12:20 | Donations | 7 | 27914 | 0 | fix: add pkreferenceid to bulkdonation entity P20-46
BE | 6e41d01f | Kavinkumar Thirumalaisamy | 2026-03-20 13:07 | System / Access / Config | 5 | 72 | 61 | fix: added new system role, commly accessing menus
FE | 9cc8d09d | Karthick | 2026-03-20 13:28 | Donations | 13 | 358 | 1 | feat: implement podtal donation batch screen P20-128
BE | 29c3a4c7 | Karthick | 2026-03-20 13:29 | Donations | 24 | 14645 | 1 | feat: add postal donation batch entity and migration P20-128
BE | 71925a12 | Karthick | 2026-03-20 13:54 | Donations | 28 | 15102 | 0 | feat: add postal donation entity and migration P20-128
FE | 80db2dd8 | Karthick | 2026-03-20 13:56 | Donations | 13 | 496 | 0 | feat: implement postal donation screen P20-128
BE | d4e39fd9 | Karthick | 2026-03-20 14:15 | Donations | 22 | 14926 | 0 | feat: add postal donation distribution entity and migration P20-128
FE | 14e42da4 | Karthick | 2026-03-20 14:15 | Donations | 7 | 212 | 0 | feat: implment postal donation distribution mutations and entity P20-128
BE | edf3743e | Karthick | 2026-03-20 17:27 | Donations | 5 | 14480 | 1 | fix: change referenceid datatype int to string in postal donation entity P20-46
BE | bc18a832 | Kavinkumar Thirumalaisamy | 2026-03-20 17:49 | System / Access / Config | 4 | 25 | 81 | fix: reverted system role
FE | f0c9bf76 | Kavinkumar Thirumalaisamy | 2026-03-20 17:54 | Donations | 2 | 75 | 55 | fix: donation screen issues
FE | 0ec27094 | Kavinkumar Thirumalaisamy | 2026-03-20 18:54 | System / Access / Config | 1 | 75 | 21 | fix: role creation of system role completed
BE | 2f4f0e02 | Karthick | 2026-03-20 21:49 | Donations | 9 | 14559 | 6 | fix: apply max lenth for prayer request property in donation entities
BE | 4308aa5f | Saranya C | 2026-03-21 12:51 | Communication | 2 | 224 | 1 | feat(donation): implement Prayer Request screen and test full flow p20-106
FE | dc0db54e | Saranya C | 2026-03-21 12:53 | Communication | 2 | 5 | 5 | feat(donation): implement Prayer Request screen and test full flow p20-106
BE | c78628f8 | Karthick | 2026-03-22 14:37 | Other / Shared | 24 | 234 | 3899 | fix: scripts cleanup
FE | f599f6d5 | Kavinkumar Thirumalaisamy | 2026-03-23 10:28 | Donations | 1 | 52 | 36 | fix: donation edit screen issues
BE | fcf586b7 | Kavinkumar Thirumalaisamy | 2026-03-23 13:37 | Donations | 8 | 62 | 12 | fix: Donation screen issue fixed
FE | 6f6f5ece | Kavinkumar Thirumalaisamy | 2026-03-23 17:17 | Donations | 4 | 73 | 41 | fix: donations screens issue fixed
FE | cecfe389 | Karthick | 2026-03-23 17:47 | Contacts | 10 | 151 | 65 | feat: implement relationship add feature in the contact relationship screen P20-130
BE | 740e0829 | Karthick | 2026-03-24 10:06 | Contacts | 13 | 27963 | 177 | fix: remove relationname and have contact in contact relationship P20-130
FE | 63202807 | Karthick | 2026-03-24 10:10 | Contacts | 3 | 8 | 18 | fix: initial data fetching while edit or view contact P20-130
BE | b1b64088 | Saranya C | 2026-03-24 13:57 | Donations | 5 | 53 | 16 | feat(contact): add donation wizard in contact menu and render the contact donation purpose details P
FE | b1d00227 | Saranya C | 2026-03-24 14:03 | Donations | 15 | 814 | 73 | feat(contact): add the donation wizard and render the donation purpose details p20-129
FE | a248be11 | Kavinkumar Thirumalaisamy | 2026-03-24 17:39 | Donations | 14 | 2338 | 260 | feat: donation collection implemented
BE | 15ad7240 | Kavinkumar Thirumalaisamy | 2026-03-24 17:40 | Contacts | 10 | 598 | 5 | feat: donation collection screen implemented
BE | c33e8c10 | Karthick | 2026-03-24 21:52 | Contacts | 28 | 15983 | 0 | feat: add duplicate contact and log entity and migration P20-146
FE | 7c4140a4 | Karthick | 2026-03-24 22:02 | Contacts | 14 | 1140 | 2 | fix: implement duplicate contact merge screen P20-146
FE | 09bbef48 | Kavinkumar Thirumalaisamy | 2026-03-25 13:12 | Donations | 2 | 5 | 6 | fix: contact query added
FE | a3268bb4 | Kavinkumar Thirumalaisamy | 2026-03-25 17:58 | Finance / Payment / Receipt | 10 | 634 | 39 | feat: receipt donations screen implemented
BE | 407be6f6 | Kavinkumar Thirumalaisamy | 2026-03-25 17:59 | Finance / Payment / Receipt | 10 | 685 | 0 | feat: receipt donations screen implemented.
FE | 0efacc65 | Kavinkumar Thirumalaisamy | 2026-03-25 22:13 | Finance / Payment / Receipt | 3 | 296 | 121 | fix: receipt donation validations fixed
BE | 93fc8373 | Kavinkumar Thirumalaisamy | 2026-03-25 22:14 | Finance / Payment / Receipt | 2 | 8 | 5 | fix: receipt donation validations fixed
FE | 8d26687a | Kavinkumar Thirumalaisamy | 2026-03-25 23:26 | Donations | 15 | 1111 | 4 | feat: dik screen implemented
BE | a58d8a3c | Kavinkumar Thirumalaisamy | 2026-03-25 23:38 | Donations | 14 | 15343 | 0 | feat: dik screen implemented
FE | ff8089e9 | Kavinkumar Thirumalaisamy | 2026-03-26 10:38 | Donations | 3 | 213 | 254 | fix: donation kind design issue fixed
FE | 6b9516d4 | Kavinkumar Thirumalaisamy | 2026-03-26 12:16 | Donations | 10 | 635 | 7 | feat: paymentmodeupload screen implemented
BE | ec1834f7 | Kavinkumar Thirumalaisamy | 2026-03-26 12:17 | Donations | 3 | 216 | 0 | feat: payment mode screen endpoints implemented
FE | 39d64362 | Karthick | 2026-03-26 12:52 | Communication | 13 | 283 | 52 | feat: implement valediction screen P20-150
BE | a6f17159 | Karthick | 2026-03-26 12:53 | Communication | 29 | 30555 | 4 | feat: add valediction entity and migration P20-150
BE | 9a0cb513 | Karthick | 2026-03-26 13:27 | Communication | 21 | 15532 | 0 | feat: add closure entity and migration P20-150
FE | ec2d2361 | Karthick | 2026-03-26 13:27 | Communication | 10 | 156 | 0 | feat: implement closure screen P20-150
BE | 3b9163a2 | Karthick | 2026-03-26 15:33 | Communication | 39 | 30794 | 0 | feat: add prayerrequestreplytype and paymentmodetransaction entity and migration P20-150
FE | f36501f3 | Karthick | 2026-03-26 15:46 | Communication | 20 | 252 | 0 | feat: implment prayerrequestreplytype and paymentmodetransaction screen P20-150
BE | 0106750e | Karthick | 2026-03-26 16:33 | Communication | 21 | 15632 | 0 | feat: add reply group entity and migration P20-150
FE | da7d3ac2 | Karthick | 2026-03-26 16:34 | Communication | 11 | 130 | 2 | feat: implement replygroup screen P20-150
FE | d5c91ca2 | Karthick | 2026-03-26 17:07 | Communication | 10 | 109 | 0 | feat: implement reply type screen P20-150
BE | 4577ea06 | Karthick | 2026-03-26 17:08 | Communication | 21 | 15661 | 0 | feat: add replytype entity and migration P20-150
FE | f6c6a5d3 | Karthick | 2026-03-26 17:33 | Communication | 10 | 89 | 0 | feat: implement enclosure screen P20-150
BE | bd82690a | Karthick | 2026-03-26 17:35 | Communication | 21 | 15671 | 0 | feat: add enclosure entity and their migration P20-150
FE | 8f224322 | Karthick | 2026-03-26 17:48 | Communication | 10 | 113 | 0 | feat: implement signatory screen P20-150
BE | e6959554 | Karthick | 2026-03-26 17:55 | Communication | 21 | 15883 | 0 | feat: add signatory entity and their migration P20-150
FE | eb719275 | Karthick | 2026-03-26 18:08 | Communication | 10 | 88 | 0 | feat: implement lettertype screen P20-150
BE | 5e9fab2f | Karthick | 2026-03-26 18:18 | Communication | 21 | 15822 | 0 | feat: add lettertype entity and their migration P20-150
FE | f88df2a9 | Karthick | 2026-03-26 18:37 | Communication | 10 | 106 | 0 | feat: implement letterhead screen P20-150
BE | f892c5e1 | Karthick | 2026-03-26 18:41 | Communication | 21 | 16034 | 0 | feat: add letterhead entity and their migration P20-150
FE | 2388d394 | Kavinkumar Thirumalaisamy | 2026-03-26 19:06 | Donations | 25 | 1459 | 70 | feat: postdatedchequecollection and prayerrequest scan screen implemented
FE | c6958fbe | Karthick | 2026-03-26 19:15 | Communication | 10 | 113 | 0 | feat: implement reply template screen P20-150
BE | 7fd5640f | Karthick | 2026-03-26 19:21 | Communication | 21 | 16182 | 0 | feat: add reply template entity and their migration P20-150
FE | 6fc37a02 | Karthick | 2026-03-26 19:46 | Communication | 12 | 243 | 0 | feat: implement reply screen P20-150
BE | 43a32aed | Karthick | 2026-03-26 19:53 | Communication | 20 | 16812 | 0 | feat: add reply entity and their migration P20-150
FE | 01d6829e | Karthick | 2026-03-27 08:49 | Donations | 10 | 133 | 0 | feat: implement partner tracing screen P20-150
BE | 3ab4a2d7 | Karthick | 2026-03-27 08:51 | Donations | 19 | 16649 | 0 | feat: add partnertracing entity and their migration P20-150
FE | d17da88e | Karthick | 2026-03-27 09:41 | Communication | 10 | 156 | 0 | feat: implement partnerprayerrequest screen P20-150
FE | 6e194894 | Karthick | 2026-03-27 10:09 | Communication | 6 | 32 | 6 | feat: convert partnerprayerrequest master grid to flow grid screen P20-150
FE | 7d322a95 | Saranya C | 2026-03-27 10:10 | Donations | 5 | 697 | 13 | feat(donation): implement bulk donation screen
BE | d93680db | Karthick | 2026-03-27 10:15 | Communication | 19 | 16895 | 0 | feat: add partnerpreayerrequest entity and their migration P20-150
BE | 17a7a39f | Saranya C | 2026-03-27 10:16 | Donations | 4 | 112 | 12 | feat(donation): implement bulk donation process
FE | b4f09410 | Karthick | 2026-03-27 10:42 | Communication | 12 | 169 | 0 | feat: implement partner prayer request pre scanned screen P20-150
BE | 3a35fef0 | Karthick | 2026-03-27 10:57 | Communication | 19 | 17038 | 0 | feat: add partner prayer request pre scanned entity and their migration P20-150
FE | bf962f05 | Karthick | 2026-03-27 11:40 | Donations | 12 | 165 | 0 | feat: implement post dated cheque collection screen P20-150
BE | 8802765f | Karthick | 2026-03-27 11:54 | Donations | 19 | 17583 | 0 | feat: add post dated cheque collection entity and their migration P20-150
FE | 9ffc170f | Karthick | 2026-03-27 12:15 | Campaigns / Crowdfund / P2P | 12 | 136 | 0 | feat: implement ambassador collection screen P20-150
BE | fc31899c | Karthick | 2026-03-27 12:24 | Campaigns / Crowdfund / P2P | 19 | 17563 | 0 | feat: add ambassador collection entity and their migration P20-150
FE | 1c9f9694 | Karthick | 2026-03-27 13:14 | Finance / Payment / Receipt | 13 | 275 | 0 | feat: implement receipt book screen P20-150
BE | 5e497dea | Karthick | 2026-03-27 13:37 | Finance / Payment / Receipt | 21 | 17925 | 9 | feat: add receipt book entity and their migration P20-150
BE | 4b1db418 | Karthick | 2026-03-27 14:07 | Finance / Payment / Receipt | 19 | 17747 | 0 | feat: add receipt book transaction entity and their migration P20-150
BE | ede19f67 | Karthick | 2026-03-27 15:14 | Communication | 62 | 20550 | 1 | feat: add donverse emailkeyword sms ambassador collection distribution entities and their migrations
FE | 65abbdf8 | Karthick | 2026-03-27 15:14 | Communication | 37 | 698 | 0 | feat: implement donverse and sms screen P20-150
FE | 4e0d2818 | Saranya C | 2026-03-28 18:09 | Contacts | 9 | 668 | 0 | feat(contact): implement ui design of certificates screen p20-147
BE | 1ed52f79 | Karthick | 2026-03-30 10:56 | Reporting / Dashboard / Audit | 21 | 18367 | 0 | feat: add file entity and their migration P20-150
BE | 527f9a41 | Karthick | 2026-03-30 11:16 | Contacts | 19 | 18590 | 0 | feat: add certificate entity and their migration P20-150
FE | aa0e0a4e | Kavinkumar Thirumalaisamy | 2026-03-31 10:51 | Donations | 2 | 67 | 70 | feat: postdated cheque collection implemented
BE | 27252067 | Saranya C | 2026-03-31 13:58 | Contacts | 7 | 155 | 12 | feat: add contactcertificate query and mutation P20-147
FE | 67e6c02a | Saranya C | 2026-03-31 14:32 | Contacts | 5 | 224 | 55 | fix: certification process P20-147
BE | 2fd2fde2 | Kavinkumar Thirumalaisamy | 2026-03-31 15:55 | Donations | 4 | 88 | 3 | fix: donation module changes of collect donations
FE | ba0da4a2 | Kavinkumar Thirumalaisamy | 2026-03-31 15:56 | Donations | 7 | 100 | 164 | fix: donation module changes of collect donation
FE | 932538b2 | Saranya C | 2026-03-31 16:09 | Contacts | 14 | 291 | 0 | feat(contact): add certificate template screen P20-147
BE | 23b7e3bb | Saranya C | 2026-03-31 16:11 | Contacts | 17 | 689 | 1 | feat: add certificatetemplate entity migration
BE | bd7d4c4f | Karthick | 2026-03-31 16:26 | Finance / Payment / Receipt | 79 | 21883 | 0 | feat: implement payment gateway service P20-149
BE | ae077b64 | Saranya C | 2026-03-31 16:29 | Contacts | 3 | 18027 | 0 | feat: add the certificate template entity and their migration P20-147
BE | bbff7be4 | Karthick | 2026-04-01 10:41 | Finance / Payment / Receipt | 15 | 1009 | 16 | feat: implement payment gateway service phase2 P20-149
BE | 1f208294 | Kavinkumar Thirumalaisamy | 2026-04-01 12:31 | Donations | 6 | 17909 | 1 | feat: product donationpurpose field newly added
BE | a070417b | Karthick | 2026-04-01 15:16 | Finance / Payment / Receipt | 15 | 19260 | 13 | fix: add payment transactionid into secondaryonlinedonation entity P20-149
BE | 6a951d34 | Karthick | 2026-04-02 11:24 | Finance / Payment / Receipt | 12 | 580 | 8 | feat: include secondary online donation mapping in recurring payment P20-149
FE | a6cba086 | Karthick | 2026-04-02 11:28 | Donations | 18 | 664 | 0 | feat: implement recurring donor screen P20-149
FE | eb751243 | Kavinkumar Thirumalaisamy | 2026-04-02 13:43 | Donations | 40 | 1822 | 198 | feat: donation screen implemented skeletons
BE | 4904c11e | Kavinkumar Thirumalaisamy | 2026-04-02 13:44 | Communication | 10 | 445 | 14 | feat: donation screen implemented skeletons
FE | 337e1c65 | Saranya C | 2026-04-02 14:42 | Contacts | 4 | 764 | 292 | feat(contact): contact management-certificates module
BE | 274ac1cc | Saranya C | 2026-04-02 14:44 | Contacts | 20 | 649 | 49 | feat(contact): contact management-certification module
FE | 525926b9 | Kavinkumar Thirumalaisamy | 2026-04-02 16:23 | Donations | 6 | 25 | 10 | feat: prayerrequest screen implemented
BE | 1c4a7eba | Kavinkumar Thirumalaisamy | 2026-04-02 16:23 | Donations | 2 | 7 | 2 | feat: prayerrequest screen implemented
FE | 99b10577 | Kavinkumar Thirumalaisamy | 2026-04-02 16:53 | Donations | 1 | 61 | 14 | fix: partner tracing changes
BE | f13149d5 | Kavinkumar Thirumalaisamy | 2026-04-02 16:54 | Donations | 1 | 2 | 0 | fix: partner tracing fixes
BE | fd2c1a4e | Karthick | 2026-04-02 17:07 | Donations | 17 | 19329 | 50 | fix: add mulitple donors in single recurring donation schedule P20-149
FE | 926e52d0 | Karthick | 2026-04-02 17:12 | Donations | 4 | 103 | 47 | fix: include recurring donation ditribution deatils in recurring donation schedule screen
BE | 720693fd | Karthick | 2026-04-03 13:47 | Donations | 2 | 3 | 3 | feat: remove companyid from create donation collection endpoint P20-st1775204023734
FE | 34e8e862 | Karthick | 2026-04-03 13:48 | Donations | 11 | 1128 | 611 | feat: improve collect donation ui and ux P20-st1775204023734
FE | a79cd9b0 | Karthick | 2026-04-04 12:39 | Donations | 37 | 1877 | 765 | fix: test and fix the save funality of bulk donation and improve ui and ux P20-st1775139658866
BE | 070d63ae | Karthick | 2026-04-04 12:41 | Donations | 10 | 19311 | 8 | fix: include the child entities collection to getbulkdonationbyid query P20-st1775139658866
FE | cb0adbf2 | Saranya C | 2026-04-04 15:56 | Contacts | 3 | 322 | 0 | feat(contact): add the certification tab in contact menu and show the certifications
BE | ab1e0a07 | Saranya C | 2026-04-04 16:02 | Contacts | 4 | 158 | 8 | feat(contact): Add the certification tab in contact menu and show the certifications
BE | d563c658 | Karthick | 2026-04-04 20:39 | Donations | 10 | 19285 | 23 | feat: implement donation upload endpoint P20-t1775314909405
FE | ee76d3d0 | Karthick | 2026-04-04 20:41 | Donations | 16 | 1282 | 953 | feat: implement donation file upload screen P20-t1775314909405
BE | b2d3d040 | Karthick | 2026-04-05 14:27 | Donations | 12 | 19604 | 0 | feat: add postaldonationid to partner tracing entity P20-t1775379396509
FE | 9c2bab41 | Karthick | 2026-04-05 14:40 | Donations | 5 | 1857 | 4 | feat: improve partner tracing screen ui and ux P20-t1775379396509
BE | 8d70062f | Karthick | 2026-04-05 15:59 | Donations | 7 | 12 | 12 | feat: update and fix the dik save fuctionality endpoint P20-t1775382211502
FE | 18492746 | Karthick | 2026-04-05 16:01 | Donations | 4 | 1103 | 572 | feat: improve donation in kind form P20-t1775382211502
FE | a48c44eb | Karthick | 2026-04-05 17:47 | Donations | 11 | 648 | 26 | feat: implement view option with valudation update functionality P20-st1775391352224
BE | eed31911 | Karthick | 2026-04-05 17:48 | Donations | 12 | 19310 | 14 | fix: update the dination in kind valuation update mutation P20-st1775391352224
BE | 8ec365f8 | Karthick | 2026-04-06 13:32 | Communication | 11 | 19115 | 14 | fix: change partnerprayerrequesttypeId as sourcetypeid in partner prayer request P20-t1775452680337
FE | 0ba082b5 | Karthick | 2026-04-06 13:33 | Communication | 34 | 519 | 185 | feat: implement prayer request entry screen P20-t1775452680337
BE | 9fb41261 | Saranya C | 2026-04-06 13:44 | Donations | 3 | 4 | 3 | fix(donation): check crud operation in donation verse screen
FE | 81775ef3 | Saranya C | 2026-04-06 13:48 | Donations | 3 | 0 | 11 | fix(donation): check crud operation in donation verse screen
FE | 673d4c41 | Karthick | 2026-04-06 14:00 | Other / Shared | 1 | 2 | 2 | fix: change the baseurl from localhost to dev api
BE | fd7621a4 | Kavinkumar Thirumalaisamy | 2026-04-06 14:12 | Finance / Payment / Receipt | 75 | 20146 | 138 | feat: ambassador receipt new context created. move the files
FE | 138df167 | Kavinkumar Thirumalaisamy | 2026-04-06 14:14 | Campaigns / Crowdfund / P2P | 46 | 748 | 43 | feat: ambassador receipt new context created. move the files
FE | 5b68c7eb | Kavinkumar Thirumalaisamy | 2026-04-06 14:16 | Other / Shared | 1 | 2 | 2 | fix: config changes
FE | 5581cc9e | Kavinkumar Thirumalaisamy | 2026-04-06 14:36 | Other / Shared | 1 | 4 | 2 | fix: service issues fixed for field
FE | eaf36249 | Kavinkumar Thirumalaisamy | 2026-04-06 16:25 | Campaigns / Crowdfund / P2P | 40 | 60 | 161 | feat: ambassador field name to fieldcolletion to changed
BE | a0208d5e | Kavinkumar Thirumalaisamy | 2026-04-06 16:39 | Finance / Payment / Receipt | 71 | 19220 | 239 | feat: field to fieldcollection names chnages for amasador entities
FE | 4a1dcc39 | Kavinkumar Thirumalaisamy | 2026-04-07 14:59 | Campaigns / Crowdfund / P2P | 1 | 954 | 0 | fix: ambasador system new approach
FE | eb8326c5 | Saranya C | 2026-04-07 17:44 | Campaigns / Crowdfund / P2P | 2 | 812 | 0 | fix: ambassador approaches version2
BE | be8fffdf | Saranya C | 2026-04-09 11:26 | Communication | 36 | 76384 | 29 | fix: remove pkreferenceid property from corg and notify schema
BE | c61e7d6f | Saranya C | 2026-04-09 12:33 | System / Access / Config | 24 | 57007 | 17 | fix: remove the pkreferenceid from app,audit,com schema entities.
BE | efb772f1 | Saranya C | 2026-04-09 13:20 | Donations | 41 | 57235 | 34 | fix: remove the pkreferenceid property from the donation, field, fund and rep schemas
FE | fced59eb | Kavinkumar Thirumalaisamy | 2026-04-09 13:44 | System / Access / Config | 23 | 9 | 363 | fix: clean for entites
BE | 4c9d265a | Kavinkumar Thirumalaisamy | 2026-04-09 15:09 | System / Access / Config | 72 | 19056 | 2068 | fix: staffcompany,branchpincode,tracking data removed
BE | cbe1adb6 | Kavinkumar Thirumalaisamy | 2026-04-09 16:43 | Contacts | 11 | 18899 | 38 | cleanup task level2
FE | 207d0275 | Kavinkumar Thirumalaisamy | 2026-04-09 16:43 | Contacts | 13 | 64 | 256 | fix: cleanup task level 2 changes
FE | b953526c | Saranya C | 2026-04-09 17:25 | Campaigns / Crowdfund / P2P | 3 | 1351 | 0 | fix: analyze the Ambassador collection and design the table
FE | 8fe7d03b | Kavinkumar Thirumalaisamy | 2026-04-09 18:49 | Contacts | 21 | 323 | 76 | fix: cleanup level script 3
BE | 4e4a94c8 | Kavinkumar Thirumalaisamy | 2026-04-09 18:51 | Contacts | 85 | 38350 | 2076 | fix: cleanup level script 3
FE | 1803bbec | Kavinkumar Thirumalaisamy | 2026-04-09 21:54 | Communication | 101 | 15 | 1808 | fix: cleanup level script 4 changes
BE | 15bf0830 | Kavinkumar Thirumalaisamy | 2026-04-09 21:54 | Communication | 202 | 18266 | 5679 | fix: cleanup level script 4 changes
BE | c3210efa | Saranya C | 2026-04-10 10:12 | Donations | 24 | 18592 | 722 | fix: cleanup the fund.CompanyDonationPurposes entity,cqrs
FE | 76152a2f | Kavinkumar Thirumalaisamy | 2026-04-10 10:14 | Contacts | 15 | 6 | 311 | fix: level 4of clean up files
FE | 2293ea8b | Saranya C | 2026-04-10 10:14 | Donations | 13 | 2 | 274 | fix: cleanup the fund.CompanyDonationPurposes frontend screen
BE | 117c413c | Saranya C | 2026-04-10 10:44 | Donations | 38 | 16490 | 1080 | fix: cleanup the onlinedonation,onlinedonationdistribution entity,cqrs
FE | 697617c3 | Saranya C | 2026-04-10 10:44 | Donations | 16 | 0 | 615 | fix: cleanup the onlinedonation,onlinedonationdistribution frontend screen
BE | 9cd3800f | Kavinkumar Thirumalaisamy | 2026-04-10 11:01 | System / Access / Config | 18 | 26 | 467 | removed [TenantScope(TenantScopeType.Dynamic)] , [AutoScope] in configured mutation and queries.
FE | 96763093 | Kavinkumar Thirumalaisamy | 2026-04-10 12:05 | Communication | 17 | 3 | 210 | fix: sms and smstemplate entites removed
BE | 0ecc0949 | Kavinkumar Thirumalaisamy | 2026-04-10 12:05 | Communication | 35 | 16149 | 1247 | fix: sms and smstemplated entites removed
BE | f90d70c8 | Saranya C | 2026-04-10 12:07 | Finance / Payment / Receipt | 42 | 16090 | 1248 | fix: cleanup the receiptdonation,receiptdonationdistribution entity , cqrs
FE | 63a9d5c8 | Saranya C | 2026-04-10 12:09 | Finance / Payment / Receipt | 15 | 1 | 678 | fix: cleanup receiptdonation, receiptdonatiodistribution frontend screen
BE | fb1865db | Saranya C | 2026-04-10 13:15 | Donations | 39 | 15657 | 1094 | fix: remove the secondaryonlinedonation, SecondaryOnlineDonationDistribution entity, cqrs
FE | 5ba43822 | Saranya C | 2026-04-10 13:22 | Donations | 10 | 0 | 454 | fix: cleanup secondaryonlinedonation, secondaryonlinedonationdistribution frontend screen
BE | a232893d | Saranya C | 2026-04-10 15:21 | Donations | 64 | 15266 | 2141 | fix: cleanup postaldonation,postaldonationbatch,postaldonationdistribution entity , cqrs files
FE | e62da874 | Saranya C | 2026-04-10 15:22 | Donations | 22 | 0 | 1047 | fix: cleanup postaldonation,postaldonationbatch,postaldonationdistribution frontend screen
FE | c7605811 | Saranya C | 2026-04-10 15:27 | Donations | 1 | 0 | 18 | fix: cleanup postaldnation file
BE | 4ba0269d | Saranya C | 2026-04-10 15:58 | Donations | 20 | 14813 | 391 | fix: cleanup partnertracing entity and cqrs files
FE | 23823ab1 | Saranya C | 2026-04-10 16:00 | Donations | 13 | 0 | 2033 | fix: cleanup partnertracing frontend screen
BE | b5f81517 | Saranya C | 2026-04-11 10:37 | Donations | 67 | 14715 | 1984 | fix: cleanup donation,donationdistribution entity,cqrs files
FE | 6ae838f1 | Saranya C | 2026-04-11 11:09 | Donations | 26 | 0 | 2967 | fix: cleanup the donation,donationdistribution frontend screen
FE | 3f761c23 | Saranya C | 2026-04-11 13:35 | Finance / Payment / Receipt | 8 | 0 | 478 | fix: cleanup receiptdonationcollection screen in frontend
BE | 714e6051 | Kavinkumar Thirumalaisamy | 2026-04-13 11:30 | System / Access / Config | 1 | 21 | 0 | fix: filter company based users
FE | c8decf44 | Kavinkumar Thirumalaisamy | 2026-04-13 13:16 | Donations | 8 | 208 | 383 | fix: build issues
BE | 7c4a8f31 | Kavinkumar Thirumalaisamy | 2026-04-13 17:06 | System / Access / Config | 8 | 14418 | 16 | import fields added
FE | 61316dec | Karthick | 2026-04-14 08:26 | System / Access / Config | 120 | 815 | 0 | feat: restructure the menu and module based global structure t1776096342418
FE | 44628527 | Karthick | 2026-04-14 12:25 | Contacts | 761 | 2710 | 1859 | fix: cleanup the files and folders based on global product structure
BE | 5460dcdf | Kavinkumar Thirumalaisamy | 2026-04-15 11:22 | System / Access / Config | 35 | 15891 | 312 | import schedule changes
FE | 629ec272 | Karthick | 2026-04-15 13:10 | Communication | 127 | 497 | 380 | feat: restructure the crm module menus
BE | 4d19e198 | Karthick | 2026-04-15 15:49 | System / Access / Config | 3 | 1178 | 1 | fix: update the db url in appsettings json
FE | 10dde215 | Kavinkumar Thirumalaisamy | 2026-04-15 18:58 | System / Access / Config | 11 | 958 | 265 | fix: import phase w implementations
BE | 8d543dda | Kavinkumar Thirumalaisamy | 2026-04-15 18:59 | System / Access / Config | 25 | 17998 | 317 | fix: import pahse 2 implementation completed
FE | 92262ce0 | Karthick | 2026-04-17 10:13 | Other / Shared | 6 | 468 | 149 | feat: implement screen header
BE | 52af8065 | Kavinkumar Thirumalaisamy | 2026-04-17 10:54 | System / Access / Config | 1 | 1 | 1 | configuration dev changes
FE | ecd4fc80 | Karthick | 2026-04-17 15:45 | Other / Shared | 11 | 376 | 55 | feat: add grid column components
BE | cc409aa7 | Karthick | 2026-04-18 12:15 | Donations | 31 | 15578 | 71 | fix: remap donation purpose and category t1776491343392
FE | cf6b55d8 | Karthick | 2026-04-18 12:24 | Donations | 23 | 376 | 315 | fix: recreate donation purpose and category screen t1776491343392
BE | d03bf821 | Karthick | 2026-04-18 14:15 | Contacts | 12 | 748 | 144 | fix: remap the contacttype entity t1776495972782
FE | 3495e3d0 | Karthick | 2026-04-18 14:19 | Contacts | 8 | 571 | 32 | fix: recreate the contact type screen t1776495972782
BE | 10f87928 | Karthick | 2026-04-18 16:25 | Contacts | 35 | 17108 | 0 | feat: add tag segmentation and contact tag entities and there migration t1776495972782
FE | 8ed5c1f1 | Karthick | 2026-04-18 16:27 | Contacts | 28 | 2470 | 3 | feat: implement tag and segmentation screen t1776495972782
BE | 1d70d185 | Karthick | 2026-04-18 17:54 | System / Access / Config | 17 | 15830 | 77 | fix: remap branch entity global perspective t1776510130277-st1776510162370
FE | fb852735 | Karthick | 2026-04-18 17:56 | System / Access / Config | 16 | 1151 | 89 | fix: recreate branch screen t1776510130277-st1776510205081
FE | be800f71 | Kavinkumar Thirumalaisamy | 2026-04-18 18:13 | System / Access / Config | 3 | 317 | 376 | fix: contact import changes fixed
BE | 4ff3de75 | Karthick | 2026-04-18 19:57 | System / Access / Config | 16 | 15373 | 33 | feat: add colorhex to staff category entity and there migration t1776510130277-st1776521452578
FE | 594f8a0d | Karthick | 2026-04-18 20:08 | System / Access / Config | 12 | 829 | 44 | feat: recreate staff category screen t1776510130277-st1776521471136
FE | 578c1bfd | Karthick | 2026-04-18 20:32 | System / Access / Config | 17 | 683 | 3 | feat: implement card view option in master and flow grid t1776523067560-st1776524390208
FE | 6d521355 | Karthick | 2026-04-19 10:38 | Communication | 23 | 1880 | 392 | fix: recreate email template entity t1776565214448-st1776565321452
BE | 2ec1464a | Karthick | 2026-04-19 10:38 | Communication | 18 | 15094 | 28 | fix: add email category to email template entity t1776565214448-st1776565250969
BE | 5cff8a61 | Karthick | 2026-04-19 12:36 | Communication | 17 | 1600 | 0 | feat: add whatsapp template relevant entities t1776565214448-st1776565274564
BE | 25405f39 | Karthick | 2026-04-19 12:38 | Communication | 14 | 1728 | 0 | feat: add sms template and sms placeholder entities t1776565214448-st1776565286466
FE | 110b5f2c | Karthick | 2026-04-19 12:44 | Communication | 20 | 3558 | 1 | feat: implement whatsapp template screen t1776565214448-st1776565343676
FE | 1ac28051 | Karthick | 2026-04-19 12:48 | Communication | 15 | 2413 | 1 | feat: implement sms template screen t1776565214448-st1776565360413
BE | b317c3c9 | Karthick | 2026-04-19 13:13 | Communication | 30 | 17965 | 8 | feat: add notification template role entity and remap notification template entity t1776565214448-st
FE | ff9753fe | Karthick | 2026-04-19 13:13 | Communication | 22 | 3353 | 1 | feat: implement notification template screen t1776565214448-st1776583270478
BE | a0f1d327 | Karthick | 2026-04-19 14:04 | Communication | 9 | 1472 | 10 | fix: add placeholder summary query t1776583188891-st1776583319363
FE | 72198958 | Karthick | 2026-04-19 14:07 | Communication | 15 | 387 | 2131 | fix: recreate placeholder screen t1776583188891-st1776583339173
BE | f0511a0c | Karthick | 2026-04-19 14:21 | Communication | 20 | 16564 | 30 | fix: add filter category to saved filter t1776583188891-st1776583363898
FE | d93c2a8d | Karthick | 2026-04-19 14:21 | Other / Shared | 20 | 1317 | 125 | fix: recreate the saved filter screen t1776583188891-st1776583381207
BE | 2abb4862 | Karthick | 2026-04-19 18:12 | Donations | 10 | 881 | 77 | fix: add donation in kind summary query t1776589168039-st1776589272930
FE | 478afb60 | Karthick | 2026-04-19 18:16 | Donations | 17 | 2783 | 1712 | fix: recreate donation in kind t1776589168039-st1776589293122
BE | bf85496c | Karthick | 2026-04-19 18:48 | Donations | 37 | 18739 | 0 | feat: add matching gift and relevant entities t1776589168039-st1776589217702
FE | fd091e7a | Karthick | 2026-04-19 18:49 | Campaigns / Crowdfund / P2P | 43 | 4382 | 7 | feat: implement matching gift screen t1776589168039-st1776589245598
FE | a03055eb | Karthick | 2026-04-19 20:21 | Contacts | 16 | 2813 | 158 | feat: recreate the family screen t1776605112373-st1776606817748
BE | d592067b | Karthick | 2026-04-19 20:22 | Contacts | 12 | 1081 | 120 | feat: add family summary query t1776605112373-st1776606797087
FE | fc18052e | Karthick | 2026-04-19 20:46 | Contacts | 39 | 2912 | 196 | feat: recreate contact screen with ux improvement t1776605112373-st1776606870908
BE | ba9d53fe | Karthick | 2026-04-19 20:46 | Contacts | 9 | 1477 | 147 | feat: add contact summary query t1776605112373-st1776609610075
FE | 9cfd2476 | Karthick | 2026-04-20 11:56 | Other / Shared | 26 | 427 | 137 | feat: upgrade next js version and dependency package
FE | 6abf1e62 | Karthick | 2026-04-20 12:47 | Other / Shared | 25 | 98 | 66 | feat: upgrade zustand t1776661435102-st1776669296521
FE | 7c8b7754 | Karthick | 2026-04-20 13:55 | System / Access / Config | 6 | 76 | 104 | feat: upgrade next-auth library t1776661435102-st1776673146471
BE | 8d465a97 | Karthick | 2026-04-20 16:58 | Other / Shared | 7 | 262 | 53 | feat: upgrade entity framework version 8 to 10 t1776676777415-st1776684266591
BE | a2a30289 | Karthick | 2026-04-20 17:29 | System / Access / Config | 20 | 136 | 163 | refactor: refactor the subscription endpoints to lastest version
FE | f7173ae3 | Karthick | 2026-04-20 17:58 | Other / Shared | 202 | 1379 | 810 | feat: upgrade apollo client and apply codemods for next js update (t1776683476193)
BE | e29860b9 | Karthick | 2026-04-20 19:25 | System / Access / Config | 731 | 11842 | 3898986 | fix: cleanup the old migrations from .net 8 version t1776676777415-st1776693105919
FE | 0fbea9e1 | Karthick | 2026-04-20 19:51 | Other / Shared | 3 | 3 | 2 | fix: gitignore updates
FE | c7c7f64d | Karthick | 2026-04-20 19:53 | System / Access / Config | 1 | 9 | 1 | fix: remove worktrees agents
FE | 759f81b5 | Karthick | 2026-04-20 20:03 | Other / Shared | 1 | 2 | 1 | chore: ignore local claude settings file
FE | 3dce460c | Karthick | 2026-04-21 09:04 | Contacts | 10 | 744 | 28 | feat: recreat the contact source screen t1776738746932-st1776738854902
BE | b4d58450 | Karthick | 2026-04-21 09:05 | Contacts | 19 | 16924 | 170 | feat: add contact source summary endpoint t1776738746932-st1776738835812
BE | acaaba72 | Karthick | 2026-04-21 09:06 | Contacts | 9 | 693 | 188 | feat: add duplicate ontact summary and update endpoints t1776738746932-st1776738934286
FE | a9da70f0 | Karthick | 2026-04-21 09:09 | Contacts | 23 | 2290 | 88 | feat: recreate the duplicate contact screen t1776738746932-st1776738963568
BE | 67599c19 | Saranya C | 2026-04-21 09:14 | Communication | 19 | 900 | 1 | feat(communication): send sms through twilio service provider and receive the response through webho
FE | c6460073 | Karthick | 2026-04-21 11:37 | Donations | 21 | 4523 | 411 | feat: recreate recurring donation screen t1776742962630-st1776750542158
FE | 86cae49b | Karthick | 2026-04-21 11:38 | Donations | 32 | 4022 | 354 | feat: create cheque donation screen t1776742962630-st1776750647840
BE | 138e33f5 | Karthick | 2026-04-21 11:39 | Donations | 22 | 18101 | 21 | feat: add recurring summary query and mutations t1776742962630-st1776750503609
BE | cdbc2195 | Karthick | 2026-04-21 11:40 | Donations | 15 | 1622 | 226 | feat: add cheque donation summary query t1776742962630-st1776750622588
BE | 706e2335 | Karthick | 2026-04-21 12:31 | Donations | 4 | 12 | 3 | fix: add cheque type properties to cheque donationschemas
BE | 2c2a842a | Karthick | 2026-04-21 13:04 | Events & Auction | 31 | 20827 | 197 | feat: add event relevant entities t1776747558685-st1776756741056
BE | e69de187 | Karthick | 2026-04-21 13:06 | System / Access / Config | 24 | 2131 | 135 | feat: remap organizational unit entity and create organizational summary query t1776747558685-st1776
FE | 4ed5f7eb | Karthick | 2026-04-21 13:13 | Events & Auction | 34 | 6001 | 1324 | feat: implement event screen t1776747558685-st1776756756447
FE | 2e096aa7 | Karthick | 2026-04-21 13:14 | System / Access / Config | 49 | 5162 | 3679 | feat: recreate organizational unit screen t1776747558685-st1776756823791
FE | 3eaf59c6 | Karthick | 2026-04-21 13:34 | Contacts | 2 | 8 | 13 | fix: change proper query name in organizational unit screen
BE | 2f603577 | Karthick | 2026-04-21 15:11 | Events & Auction | 50 | 21859 | 0 | feat: add auction relational entities and their migration t1776758214437-st1776761512916
BE | e8f1cd07 | Karthick | 2026-04-21 15:12 | Campaigns / Crowdfund / P2P | 42 | 3287 | 202 | feat: add campaign relational entities and their migration t1776758214437-st1776761512916-st17767617
FE | 5ff8ee33 | Karthick | 2026-04-21 15:20 | Events & Auction | 29 | 5195 | 2 | feat: implement auction management screen t1776758214437-st1776761545685
FE | 62d12650 | Karthick | 2026-04-21 15:23 | Campaigns / Crowdfund / P2P | 57 | 7557 | 221 | feat: recreate campaign screen t1776758214437-st1776761409645
FE | 1c857912 | Karthick | 2026-04-21 15:45 | Campaigns / Crowdfund / P2P | 5 | 8 | 26 | fix: remove unwanted export campaign router
BE | 2fb90ad4 | Karthick | 2026-04-21 16:25 | Events & Auction | 47 | 2822 | 0 | feat: add event ticket relational entities and their migration t1776766779236-st1776766861576
BE | eac6f4ba | Karthick | 2026-04-21 16:26 | Communication | 32 | 3579 | 0 | feat: add sms campaign entity and their migration t1776766779236-st1776766980347
BE | 026f9970 | Karthick | 2026-04-21 16:31 | Communication | 3 | 19245 | 0 | feat: add event ticket and sms campaign migrations
FE | a0e575a3 | Kavinkumar Thirumalaisamy | 2026-04-21 16:35 | Other / Shared | 10 | 84 | 64 | fix: whasapp tempate and import contact completed
FE | 4ad8ce03 | Karthick | 2026-04-21 16:37 | Communication | 28 | 4301 | 0 | feat: create sms campaign screen t1776766779236-st1776766997603
FE | b2082a94 | Karthick | 2026-04-21 16:38 | Events & Auction | 49 | 5633 | 3 | feat: create event ticket screen t1776766779236-st1776766923404
BE | 5a499867 | Karthick | 2026-04-21 18:35 | Pledge | 22 | 21500 | 3 | feat: add pledge and pledge payment entity and their migration t1776771104688-st1776776516414
BE | d233b48c | Karthick | 2026-04-21 18:36 | Finance / Payment / Receipt | 21 | 2425 | 0 | feat: add refund entity and their migration t1776771104688-st1776776583701
FE | a7794f98 | Karthick | 2026-04-21 18:42 | Pledge | 18 | 3786 | 3 | feat: implement pledge screen t1776771104688-st1776776547412
FE | 6a22a06c | Karthick | 2026-04-21 18:43 | Finance / Payment / Receipt | 36 | 5667 | 2 | feat: implement refund screen t1776771104688-st1776776598047
FE | 4d359a11 | Karthick | 2026-04-21 18:57 | Finance / Payment / Receipt | 1 | 2 | 4 | fix: change proper query name for refund get all query
BE | 1d9e6cf1 | Karthick | 2026-04-21 19:35 | Donations | 13 | 2421 | 0 | feat: add reconciliation queries t1776771177858-st1776778510618
BE | 4905604f | Karthick | 2026-04-21 19:37 | Communication | 18 | 20009 | 14 | feat: remap notification entity and queries t1776771177858-st1776778453000
FE | e0cca852 | Karthick | 2026-04-21 19:42 | Communication | 19 | 1464 | 2 | feat: create notification center screen t1776771177858-st1776778470912
FE | 7aebb360 | Karthick | 2026-04-21 19:43 | Donations | 32 | 3968 | 3 | feat: implement payment reconciliation screen t1776771177858-st1776778536965
FE | 56d43cc1 | Saranya C | 2026-04-21 19:48 | Contacts | 10 | 122 | 189 | fix(contact): test the family management screen and fix the issues
BE | 7e2d7ffc | Karthick | 2026-04-22 08:38 | Finance / Payment / Receipt | 17 | 20722 | 97 | feat: add staffid and branchid into receipt book entity t1776781613904-st1776825522871
BE | 4c28f712 | Karthick | 2026-04-22 08:42 | Campaigns / Crowdfund / P2P | 15 | 572 | 56 | feat: add abassador contact id into ambassador collection entity t1776781613904-st1776825450142
FE | 7dac365d | Karthick | 2026-04-22 08:44 | Finance / Payment / Receipt | 8 | 1025 | 7 | feat: implement receipt book screen t1776781613904-st1776825476144
FE | e870cd51 | Karthick | 2026-04-22 08:46 | Contacts | 19 | 2019 | 53 | feat: implement ambassador collection screen t1776781613904-st1776825476144
BE | f7f5f98d | Karthick | 2026-04-22 09:06 | Campaigns / Crowdfund / P2P | 1 | 4 | 0 | fix: add auditable columns to amabssador collection response dto
FE | 33c668ca | Karthick | 2026-04-22 09:07 | Finance / Payment / Receipt | 1 | 166 | 55 | fix: move screen header to above the kpi cards in receipt book screen
FE | 3d07629a | Kavinkumar Thirumalaisamy | 2026-04-22 09:51 | Communication | 17 | 908 | 406 | fix: whatsapp template issues fixed
FE | af195a86 | Saranya C | 2026-04-22 13:56 | Other / Shared | 5 | 26 | 7 | fix(contact): test the contacttype screen and issue fixes
BE | 335cf17d | Kavinkumar Thirumalaisamy | 2026-04-22 17:52 | Communication | 28 | 17852 | 50 | fix: whatsapp setup screen issues fixed
FE | 1beee3b0 | Kavinkumar Thirumalaisamy | 2026-04-24 10:14 | Communication | 13 | 1361 | 23 | fix: whatsapp set up screens issues
BE | 54570f29 | Karthick | 2026-04-24 12:06 | Case & Program | 23 | 22576 | 0 | feat: add program management entities and their migration
BE | 13bb7eca | Karthick | 2026-04-24 12:07 | Campaigns / Crowdfund / P2P | 39 | 2030 | 6 | feat: add ambassador list and summary queries endpoints
FE | 47482e66 | Karthick | 2026-04-24 12:11 | Case & Program | 23 | 2617 | 3 | feat: implement program management screen
FE | 8e507f40 | Karthick | 2026-04-24 12:11 | Campaigns / Crowdfund / P2P | 33 | 2841 | 40 | feat: implement ambassador list screen
FE | c1f39f73 | Karthick | 2026-04-24 13:33 | Case & Program | 33 | 4145 | 3 | feat: implement beneficiary screen t1777015354949-st1777015459500
BE | 25357abd | Karthick | 2026-04-24 13:34 | Case & Program | 26 | 3246 | 0 | feat: add beneficiary entities and their migrations with beneficiary summary query t1777015354949-st
BE | a488aad9 | Karthick | 2026-04-24 14:21 | Case & Program | 66 | 27076 | 2 | feat: add case entities and their migrations with case summary query t1777015354949-st1777015557670
FE | 4e2cb986 | Karthick | 2026-04-24 14:26 | Case & Program | 37 | 5335 | 3 | feat: implement case management screen t1777015354949-st1777015575465
BE | 58c320c6 | Karthick | 2026-04-24 15:07 | Communication | 18 | 1297 | 14 | feat: add email sending identity entity and remap company email provider entity t1777021165034-st177
FE | 794c23e2 | Karthick | 2026-04-24 15:13 | Communication | 20 | 2252 | 54 | feat: implement company email configuration screen t1777021165034-st1777021285788
BE | 198c6701 | Saranya C | 2026-04-24 16:20 | Contacts | 11 | 31905 | 81 | fix(contact): test the tags and segmentation screen and fix the issues
FE | ffb310ff | Saranya C | 2026-04-24 16:24 | Contacts | 9 | 1108 | 680 | fix(contact): test the tags and segmentation screen and fix the issues
BE | c3f618d7 | Karthick | 2026-04-24 16:31 | Volunteer | 36 | 25867 | 1 | feat: add volunteer management entity and their migration t1777021165034-st1777021335836
FE | dfcfedde | Karthick | 2026-04-24 16:31 | Volunteer | 49 | 4513 | 72 | feat: implement voulnteer managment screen t1777021165034-st1777021374961
BE | e44a2f2f | Kavinkumar Thirumalaisamy | 2026-04-24 16:44 | System / Access / Config | 2 | 3 | 24 | fix: import validation issues completed
FE | 88398660 | Kavinkumar Thirumalaisamy | 2026-04-24 17:25 | Other / Shared | 1 | 2 | 2 | fix: config changes
BE | 5af2e496 | Kavinkumar Thirumalaisamy | 2026-04-24 19:14 | Communication | 3 | 4 | 4 | fix: whatsapp version changes
BE | e4c97299 | Karthick | 2026-04-25 07:33 | Volunteer | 28 | 1998 | 1 | feat: add volunteer shift entity and their migration t1777028684603-st1777028944460
FE | ab89d7bc | Karthick | 2026-04-25 07:34 | Volunteer | 14 | 3041 | 2 | feat: implement volunteer schedule screen t1777028684603-st1777028960865
BE | 640a9d92 | Karthick | 2026-04-25 07:50 | Membership | 26 | 24811 | 2 | feat: add membership tier entity and their migration t1777028684603-st1777029138040
FE | 043a8d78 | Karthick | 2026-04-25 07:52 | Membership | 27 | 2209 | 4 | feat: implement membership tier screen t1777028684603-st1777029094046
FE | 7ed1927c | Karthick | 2026-04-25 08:44 | Volunteer | 30 | 4011 | 2 | feat: implement volunteer hrs tracking screen t1777028684603-st1777083195195
BE | 92d2f16a | Karthick | 2026-04-25 08:56 | Volunteer | 20 | 2028 | 0 | feat: add vounteer hrs tracking entities and their migration t1777028684603-st1777083175286
BE | 796aa0d8 | Karthick | 2026-04-25 08:57 | Case & Program | 31 | 25917 | 3 | feat: add membership enrollment entities and their migration t1777028684603-st1777029167572
FE | fb372c01 | Karthick | 2026-04-25 08:59 | Case & Program | 33 | 5114 | 9 | feat: implement membership enrollment screen t1777028684603-st1777029167572
FE | 7bbf1ed1 | Saranya C | 2026-04-25 12:02 | Other / Shared | 3 | 17 | 9 | fix(donation): test the donationpurpose screen and fix the issues
FE | a9d0a047 | Saranya C | 2026-04-25 12:18 | Donations | 1 | 1 | 1 | fix(donation): test the donationgroup screen and fix the issues
FE | 2a3b15ae | Saranya C | 2026-04-25 13:56 | Donations | 1 | 1 | 1 | fix(donation): test the donationcategory screen and fix the issues
BE | 791e49eb | Karthick | 2026-04-26 07:06 | Membership | 25 | 2126 | 0 | feat: add memebership renewal entities and their migration t1777167017895-st1777167066650
FE | f2cfc806 | Karthick | 2026-04-26 07:14 | Membership | 22 | 2306 | 3 | feat: implement membership renewal screen t1777167017895-st1777167128491
BE | 59301615 | Karthick | 2026-04-26 07:20 | Grants | 52 | 28194 | 31 | feat: add grant entities with mutation and queries t1777167017895-st1777168099103
FE | 823e26e9 | Karthick | 2026-04-26 07:22 | Grants | 35 | 5517 | 3 | feat: implement grant list screen t1777167017895-st1777168144659
BE | a8af00bb | Karthick | 2026-04-26 09:24 | Grants | 30 | 26823 | 0 | feat: add grant report entities and their migration t1777085323564-st1777169024625
FE | 145e48a0 | Karthick | 2026-04-26 09:24 | Grants | 34 | 4764 | 2 | feat: implement grant report screen t1777085323564-st1777169042545
BE | fdc4515f | Karthick | 2026-04-27 09:51 | Contacts | 10 | 78 | 35 | feat: remap contact endpoints t1777175881482-st1777263607566
FE | a246391d | Karthick | 2026-04-27 09:53 | Contacts | 38 | 4045 | 340 | feat: recreate contact screen part1 t1777175881482-st1777263772503
FE | 1b3d0d23 | Karthick | 2026-04-27 09:55 | Other / Shared | 1 | 1 | 0 | feat: add isomorphic-dompurify lib
FE | bd4fbb3c | Karthick | 2026-04-27 14:31 | Communication | 87 | 2733 | 1223 | fix: build the application and fix the types error t1777277417111-st1777277620832
FE | df9b33dd | Divya S | 2026-04-27 18:02 | Other / Shared | 2 | 1 | 1 | fix: upgrade the node version
FE | 58dd460f | Saranya C | 2026-04-27 18:58 | Donations | 6 | 39 | 16 | fix(donation): test the donationinkind screen and fix the issues
BE | ca3870ab | Saranya C | 2026-04-27 18:59 | Donations | 4 | 139 | 65 | fix(donation): test the donationinkind screen and fix the issues
BE | eefffef6 | Kavinkumar Thirumalaisamy | 2026-04-27 20:14 | Contacts | 1 | 0 | 1 | fix: contact isrefferal issues
BE | 79b69ba3 | Saranya C | 2026-04-27 20:50 | Donations | 6 | 16151 | 7 | fix(donation): remove the instrumentno,instrumentdate and add globaldonationid in donationinkind ent
BE | 39d911d5 | Saranya C | 2026-04-27 21:12 | Donations | 5 | 16154 | 1 | fix(donation): set the donnationamount, netamount, feeamount as 0 by default in globaldonationentit
FE | 9ef2b149 | Saranya C | 2026-04-28 10:33 | Other / Shared | 3 | 19 | 14 | fix(donation): fetch the selected value in edit screen
FE | 39409dd7 | Kavinkumar Thirumalaisamy | 2026-04-28 13:34 | Contacts | 17 | 110 | 23 | fix: contact screen relevant issues
BE | f966cbff | Kavinkumar Thirumalaisamy | 2026-04-28 13:35 | Contacts | 7 | 145 | 42 | fix: contact screen relevant issues
FE | 1dacbe7a | Kavinkumar Thirumalaisamy | 2026-04-28 13:55 | Contacts | 4 | 145 | 113 | fix: completed the filter issue
FE | 451c1fd6 | Kavinkumar Thirumalaisamy | 2026-04-28 15:17 | Contacts | 8 | 394 | 204 | fix: relationship isses fixed and then design changes
FE | a1902c40 | Kavinkumar Thirumalaisamy | 2026-04-28 15:27 | Contacts | 1 | 10 | 0 | fix: replation ship issue fixed
BE | 6a8b7a75 | Kavinkumar Thirumalaisamy | 2026-04-28 15:28 | Contacts | 1 | 1 | 0 | fix: relationship issue fixed
FE | 5e164078 | Kavinkumar Thirumalaisamy | 2026-04-28 17:14 | Communication | 6 | 1286 | 1216 | fix: notification template completed full and fixed issues
BE | be210c97 | Kavinkumar Thirumalaisamy | 2026-04-28 17:44 | Communication | 1 | 7 | 2 | fix: endpoint error fixed
FE | 1fc2c1cb | Kavinkumar Thirumalaisamy | 2026-04-28 18:38 | System / Access / Config | 3 | 594 | 580 | fix: oraganizanal unit design changes froms and list
FE | 0465054d | Karthick | 2026-04-28 19:01 | Other / Shared | 23 | 1095 | 74 | fix: apply navigation funationality to contact source t1777259720009
FE | 8e0b68dd | Karthick | 2026-04-28 19:05 | Contacts | 1 | 4 | 4 | fix: build and fix the type issue
BE | ab172c40 | Karthick | 2026-04-28 19:13 | Contacts | 7 | 27 | 38 | fix: apply proper filter conditions and form schema for contact source t1777259720009
BE | d1e4779c | Karthick | 2026-04-28 19:46 | Reporting / Dashboard / Audit | 5 | 24755 | 0 | feat: add menuid to dashboard entity t1777370063482-st1777385255189
BE | ed0b7cbf | Karthick | 2026-04-28 21:17 | Case & Program | 18 | 2731 | 0 | feat: add case management dashboard db scripts and widget functions t1777385981430-st1777386235966
FE | dac22f6d | Karthick | 2026-04-28 21:19 | Reporting / Dashboard / Audit | 5 | 418 | 12 | feat: impleemnt case management dashboard and required widgets t1777385981430-st1777386142539
BE | 02ae66e2 | Saranya C | 2026-04-29 09:42 | System / Access / Config | 14 | 24857 | 3 | fix(organization): test the branch screen with full workflow
FE | 5fcab4d7 | Saranya C | 2026-04-29 09:43 | System / Access / Config | 7 | 71 | 40 | fix(organization): test the branch screen with full workflow
BE | 8dc10a75 | Karthick | 2026-04-29 11:10 | Reporting / Dashboard / Audit | 4 | 91 | 4 | feat: implement getdashboardbymoduleandcode query t1777385981430-st1777440949791
FE | e5ac4d72 | Karthick | 2026-04-29 11:15 | Reporting / Dashboard / Audit | 9 | 94 | 434 | feat: render case dashboard and implement menudashboard component t1777385981430-st1777429508259
BE | 1a3ad34e | Kavinkumar Thirumalaisamy | 2026-04-29 12:01 | System / Access / Config | 6 | 24816 | 0 | fix: location and contact of organizal unit changes
FE | a8a7717f | Karthick | 2026-04-29 12:09 | Reporting / Dashboard / Audit | 13 | 1808 | 77 | fix: test case dashboard widgets t1777441414341-st1777441445122
BE | a1974e8a | Karthick | 2026-04-29 12:39 | Case & Program | 18 | 2169 | 521 | feat: add casemanagement widget functions t1777385981430
FE | 9544f29c | Karthick | 2026-04-29 14:24 | Case & Program | 21 | 5425 | 423 | feat: implement kpi widgets for case dashboard t1777441414341-st1777444714150
BE | 21875e75 | Karthick | 2026-04-29 14:29 | Case & Program | 3 | 129 | 32 | feat: implement kpi widgets for case dashboard t1777441414341-st1777444714150
BE | 41090a83 | Kavinkumar Thirumalaisamy | 2026-04-29 16:51 | System / Access / Config | 14 | 25236 | 8 | fix: organizational complete issues fixes
FE | ea9971d7 | Kavinkumar Thirumalaisamy | 2026-04-29 16:54 | System / Access / Config | 19 | 1690 | 487 | fix: organizational unit issues fixes
FE | 73effaa0 | Kavinkumar Thirumalaisamy | 2026-04-29 17:07 | Contacts | 2 | 9 | 9 | fix: build issue fixed
BE | a2b5e559 | Kavinkumar Thirumalaisamy | 2026-04-29 18:53 | Campaigns / Crowdfund / P2P | 5 | 38 | 19 | fix: campaign screen issues
BE | 582fdd44 | Karthick | 2026-04-29 20:47 | Contacts | 17 | 4018 | 0 | feat: add contact dashboard widget functions t1777462487134-st1777462551910
FE | 1478638e | Karthick | 2026-04-29 20:55 | Contacts | 22 | 4355 | 8 | feat: implement contact dashboard screen t1777462487134-st1777462512016
FE | 91b26fc5 | Karthick | 2026-04-30 09:09 | Donations | 66 | 4555 | 12 | feat: implement donation dashboard screen t1777515350310-st1777515426325
BE | 002e20b4 | Karthick | 2026-04-30 09:28 | Donations | 18 | 3920 | 0 | feat: add donation dashboard widget functions t1777515350310-st1777515449770
BE | 979ee289 | Karthick | 2026-04-30 10:10 | Volunteer | 12 | 1615 | 0 | feat: add volunteer dashboard widgets functions t1777521695634-st1777522404607
FE | aa12467e | Karthick | 2026-04-30 10:13 | Volunteer | 16 | 1534 | 7 | feat: implement volunteer dashboard t1777521695634-st1777522371938-st1777522500851
BE | cceaa7e4 | Karthick | 2026-04-30 11:47 | Campaigns / Crowdfund / P2P | 15 | 3276 | 0 | feat: add ambassador dashboard widgets functions t1777524370409-st1777524437189
FE | 5f8985a4 | Kavinkumar Thirumalaisamy | 2026-04-30 11:55 | Campaigns / Crowdfund / P2P | 28 | 4620 | 591 | fix: campaign and organization issue resloved
FE | a6997fe8 | Karthick | 2026-04-30 12:00 | Campaigns / Crowdfund / P2P | 52 | 4163 | 3 | feat: implement ambassador dashboard screen t1777524370409-st1777524406330-st1777524469468
BE | dce364b7 | Saranya C | 2026-04-30 12:33 | Other / Shared | 23 | 99711 | 52 | fix: update the address fields with globalized approach
FE | 309df3b1 | Saranya C | 2026-04-30 12:34 | Other / Shared | 16 | 281 | 83 | fix: update the address fields with globalized approach
BE | 4c21d139 | Karthick | 2026-04-30 13:20 | Communication | 18 | 4091 | 0 | feat: add communication dashboard widgets functions t1777530771064-st1777530829512
FE | 1ce79075 | Karthick | 2026-04-30 13:27 | Communication | 65 | 4158 | 3 | feat: implement communication dashboard screen t1777530771064-st1777530800308-st1777530851709
BE | d5fe8bf5 | Kavinkumar Thirumalaisamy | 2026-04-30 13:28 | Events & Auction | 4 | 4 | 9 | fix: event screen issue fixes
FE | fdf40ebf | Kavinkumar Thirumalaisamy | 2026-04-30 13:30 | Events & Auction | 14 | 1363 | 311 | fix: event screen issue fixes
FE | 9d89a12d | Saranya C | 2026-04-30 14:00 | Donations | 2 | 4 | 3 | fix(donation): test the donationcategory screen
BE | 92681e2c | Saranya C | 2026-04-30 14:02 | Donations | 2 | 9 | 1 | fix(donation): test the donationcategory screen
FE | 07d155f1 | Kavinkumar Thirumalaisamy | 2026-04-30 15:16 | Other / Shared | 3 | 28 | 13 | fix: district branch issues
BE | c13a93f0 | Saranya C | 2026-04-30 15:43 | Donations | 3 | 11 | 3 | fix(donation): test the donation group screen
FE | 16ec0f32 | Saranya C | 2026-04-30 15:44 | Donations | 1 | 2 | 2 | fix(donation): test the donation group screen
BE | 7e80e918 | Kavinkumar Thirumalaisamy | 2026-04-30 16:33 | System / Access / Config | 8 | 24968 | 8 | fix: changes of brach entites
BE | a4b935f8 | Kavinkumar Thirumalaisamy | 2026-04-30 16:53 | System / Access / Config | 8 | 25065 | 25 | fix: branch issues fixes
FE | e0bfd786 | Saranya C | 2026-04-30 17:36 | Donations | 1 | 2 | 2 | fix(donation): test the donation purpose screen
BE | 0c23f16b | Saranya C | 2026-04-30 17:37 | Donations | 2 | 9 | 1 | fix(donation): test the donation purpose screen
BE | 2cf04f7f | Kavinkumar Thirumalaisamy | 2026-04-30 18:17 | System / Access / Config | 10 | 24997 | 9 | branch issue fixed
FE | 8e88bd72 | Kavinkumar Thirumalaisamy | 2026-04-30 18:45 | Other / Shared | 8 | 794 | 61 | fix: changes in branch and branch user screen
FE | 14e58a06 | Kavinkumar Thirumalaisamy | 2026-04-30 18:49 | System / Access / Config | 2 | 62 | 5 | fix: branch user staff details issue fixed
BE | 25dd9536 | Karthick | 2026-04-30 19:12 | Donations | 2 | 161 | 0 | feat: add donation summary query t1777259211571-st1777553096773
BE | ffac6041 | Karthick | 2026-04-30 21:34 | Donations | 28 | 51118 | 64 | fix: create global donation mutation t1777259211571-st1777557271352
FE | 563dfb31 | Karthick | 2026-04-30 21:39 | Donations | 17 | 1454 | 56 | fix: test global donation online donation mode t1777259211571-st1777555121312
FE | ce00fe5d | Karthick | 2026-04-30 21:41 | Donations | 16 | 3790 | 109 | feat: implement donation summary widgets t1777556597321-st1777555121312
BE | 8ced8762 | Karthick | 2026-05-01 12:51 | System / Access / Config | 10 | 26598 | 0 | feat: implement company configuration settings entities t1777607932251-st1777611479355
BE | 68045f77 | Karthick | 2026-05-01 12:53 | System / Access / Config | 20 | 1533 | 1 | feat: implement company configuration settings relevant mutation and queries t1777607932251-st177761
BE | 7fa76d06 | Karthick | 2026-05-01 12:54 | System / Access / Config | 1 | 690 | 0 | feat: add company settingd db scripts t1777607932251-st1777611590797
FE | 5c867eac | Karthick | 2026-05-01 12:55 | System / Access / Config | 31 | 3986 | 1 | feat: implement company setting screen t1777607932251-st1777611547730
BE | 4a485d05 | Karthick | 2026-05-01 18:09 | Finance / Payment / Receipt | 33 | 27704 | 195 | fix: remapped currency conversion table t1777631122466-st1777631504185
FE | ecfdac0d | Karthick | 2026-05-01 18:10 | Finance / Payment / Receipt | 9 | 996 | 108 | feat: implement currency conversion screen t1777631122466-st1777631524617
FE | ed3ca9e5 | Karthick | 2026-05-01 21:21 | System / Access / Config | 21 | 747 | 177 | feat: add company currency to donation screen t1777556597321-st1777620408346
BE | d3c11617 | Karthick | 2026-05-02 09:09 | Finance / Payment / Receipt | 18 | 25895 | 19 | fix: update global donation query and include child entities details t1777650892421-st1777691020255
FE | 2f2f90c7 | Karthick | 2026-05-02 09:10 | Finance / Payment / Receipt | 23 | 1350 | 326 | fix: test receipt donation and implement receipt generation feature t1777650892421-st1777691029818
BE | 419775af | Karthick | 2026-05-02 11:22 | System / Access / Config | 10 | 26232 | 0 | feat: implement numbersequenceentitytype and numbersequenceconfig entity t1777696647706-st1777696703
BE | 642faf6a | Karthick | 2026-05-02 11:23 | Donations | 6 | 352 | 78 | feat: implement number sequence generator service t1777696647706-st1777696750602
BE | 93b993de | Karthick | 2026-05-02 12:47 | Donations | 1 | 166 | 10 | fix: handle null exception error in donation response t1777650892421-st1777706018331
BE | b093682c | Karthick | 2026-05-02 15:42 | Donations | 17 | 52477 | 40 | fix: update dik mutations and entities t1777712502194
FE | 44af9865 | Karthick | 2026-05-02 15:49 | Donations | 10 | 1052 | 82 | fix: update donation view form and dik dunationalit t1777712502194
BE | 00ab4dcc | Karthick | 2026-05-02 16:16 | Donations | 1 | 31 | 0 | fix: restrict recurring donation creation in globaldonation create muation t1777717071379-st17777171
FE | 8d6693a5 | Karthick | 2026-05-02 16:17 | Donations | 1 | 16 | 1 | fix: restrict recurring donation creation in donation form t1777717071379-st1777717102711
FE | d970065d | Kavinkumar Thirumalaisamy | 2026-05-02 16:22 | Volunteer | 12 | 680 | 286 | fix: volunteer changes
FE | 4eafd66b | Kavinkumar Thirumalaisamy | 2026-05-02 16:36 | Other / Shared | 1 | 2 | 2 | fix: config url changes
BE | 410d7734 | Saranya C | 2026-05-02 17:04 | Donations | 3 | 14 | 48 | fix(donation): test the donationinkind screen
FE | e20f2964 | Saranya C | 2026-05-02 17:25 | Donations | 12 | 338 | 113 | fix(donation): test the donationinkind screen
BE | 44da2d82 | Kavinkumar Thirumalaisamy | 2026-05-02 17:28 | Volunteer | 7 | 25960 | 12 | fix: volunteer page issues
FE | 4463a81d | Kavinkumar Thirumalaisamy | 2026-05-02 17:28 | Volunteer | 6 | 176 | 75 | fix: vounteer screen issue fixed
BE | dfe8a803 | Saranya C | 2026-05-02 19:30 | Donations | 2 | 4 | 0 | fix: upload the receipt img in donationinkind
FE | ef3a5526 | Saranya C | 2026-05-02 19:32 | Donations | 2 | 27 | 26 | fix: upload the receipt img in donationinkind
BE | e71e97b5 | Kavinkumar Thirumalaisamy | 2026-05-04 11:54 | Volunteer | 2 | 2 | 2 | fix: volunteer screen issues
FE | 4fc9bf68 | Kavinkumar Thirumalaisamy | 2026-05-04 11:54 | Volunteer | 17 | 1942 | 498 | fix: volunteer screen issue fixes
FE | bd3d6d57 | Kavinkumar Thirumalaisamy | 2026-05-04 14:49 | Volunteer | 12 | 1499 | 389 | fix: volunteer shift screen changes
FE | a5a278fa | Saranya C | 2026-05-04 14:57 | Communication | 2 | 31 | 10 | fix(communication): test the Email Template screen and fix the issues
BE | 1f887d4d | Karthick | 2026-05-04 16:58 | Pledge | 4 | 238 | 0 | feat: refactor pledge schemas t1777717071379-st1777719019840
FE | 94d9e8a2 | Karthick | 2026-05-04 17:02 | Pledge | 4 | 773 | 11 | feat: display pledge details in donation form t177771707139-st1777717130897
FE | 4cbc1352 | Kavinkumar Thirumalaisamy | 2026-05-04 17:05 | Volunteer | 10 | 131 | 48 | fix: vounteer screen changes
BE | e4824421 | Karthick | 2026-05-04 17:06 | Pledge | 4 | 289 | 5 | fix: refactor globaldonation create mutation and include pledge donation type flow t1777894359282
FE | fe6de7b9 | Karthick | 2026-05-04 17:06 | Donations | 7 | 406 | 1 | fix: refactor donation form and include pledge donation type flow t1777894359282
BE | ebf06fcc | Kavinkumar Thirumalaisamy | 2026-05-04 17:18 | Other / Shared | 10 | 339 | 24 | fix: volunteer screen full flow completed
FE | d64113d0 | Kavinkumar Thirumalaisamy | 2026-05-04 17:59 | Communication | 1 | 1 | 1 | fix: notification screen issues
FE | d39bd2ab | Karthick | 2026-05-04 18:13 | Donations | 4 | 429 | 143 | fix: refactor donation summary widgets in global donation screen t1777894359282-st1777894674772
BE | 0bb95654 | Karthick | 2026-05-04 18:14 | Donations | 2 | 294 | 96 | fix: refactor donation summary widgets queries t1777894359282
FE | 5717c5d6 | Kavinkumar Thirumalaisamy | 2026-05-04 18:45 | Volunteer | 6 | 149 | 55 | fix: volunteer screen issues
BE | 40018cda | Kavinkumar Thirumalaisamy | 2026-05-04 18:48 | Communication | 1 | 34 | 19 | fix: notitfication template issue fixed
FE | 9c8be3b2 | Saranya C | 2026-05-04 19:31 | Other / Shared | 3 | 32 | 3 | fix(communication): test the placeholderdefinition screen
FE | 5cd394b9 | Karthick | 2026-05-04 22:02 | Donations | 9 | 95 | 1516 | fix: test recurring donation screen t1777259485934
FE | 224a005f | Kavinkumar Thirumalaisamy | 2026-05-04 22:21 | Other / Shared | 1 | 2 | 3 | fix: notification template changes
BE | 61be40a1 | Kavinkumar Thirumalaisamy | 2026-05-05 09:17 | Communication | 1 | 1 | 1 | fix: the template issue resolved
BE | 2f116d9b | Karthick | 2026-05-05 09:26 | Donations | 10 | 1017 | 48 | fix: apply utc time filter in recurring donation schedule summary and failed query t17772594855934
FE | 22f34dae | Karthick | 2026-05-05 09:29 | Other / Shared | 10 | 109 | 38 | fix: fix the component rendering issue in recurring grid and view t17772594855934
FE | f5f4cb4e | Kavinkumar Thirumalaisamy | 2026-05-05 12:15 | Campaigns / Crowdfund / P2P | 10 | 1124 | 94 | fix: ambassador screen issues
FE | 7b078805 | Karthick | 2026-05-05 12:35 | Donations | 13 | 1063 | 1358 | fix: test cheque donation screen flow t1777259308586
FE | bbad4e85 | Saranya C | 2026-05-05 12:40 | Communication | 5 | 175 | 186 | fix(communication): test the savedfilter screen
BE | 767a4ebd | Karthick | 2026-05-05 12:50 | Donations | 1 | 57 | 2 | fix: handle payment status in cheque donation mutation t1777259308586
BE | 69973792 | Kavinkumar Thirumalaisamy | 2026-05-05 12:59 | Volunteer | 6 | 40 | 12 | fix: ambaasaor screen issues
FE | 769b9196 | Karthick | 2026-05-05 13:19 | Other / Shared | 2 | 62 | 62 | fix: build and fix types issue
BE | be0f4ce9 | Kavinkumar Thirumalaisamy | 2026-05-05 14:42 | Other / Shared | 1 | 1 | 1 | fix: decorator changes
FE | 737f5840 | Saranya C | 2026-05-05 15:24 | Communication | 6 | 898 | 118 | fix: change the placeholderdefinition screen into flowgrid with customized form
BE | ed955017 | Kavinkumar Thirumalaisamy | 2026-05-05 16:22 | Campaigns / Crowdfund / P2P | 1 | 1 | 1 | fix: summary card issues
FE | 6e397031 | Kavinkumar Thirumalaisamy | 2026-05-05 16:23 | Communication | 64 | 886 | 1316 | fix: ambaasor and collection list issue fixes
BE | 0b15e86d | Karthick | 2026-05-05 16:26 | Other / Shared | 5 | 9 | 56 | chore: change dev pulish profile
FE | b0100de6 | Kavinkumar Thirumalaisamy | 2026-05-05 18:38 | Campaigns / Crowdfund / P2P | 15 | 579 | 462 | fix: ambassador screen changes
BE | 7d869512 | Karthick | 2026-05-05 21:59 | Finance / Payment / Receipt | 15 | 1012 | 10 | chore: refactor the refund entities t1777260505103-st1777998378530
FE | dd7b32e7 | Karthick | 2026-05-05 22:02 | Finance / Payment / Receipt | 14 | 1713 | 81 | chore: refactor the refund screen t1777260505103-st1777988735490
FE | 2e1cc9e1 | Kavinkumar Thirumalaisamy | 2026-05-06 10:00 | Contacts | 1 | 4 | 4 | fix: collection form changes
FE | e3382804 | Kavinkumar Thirumalaisamy | 2026-05-06 10:01 | Other / Shared | 1 | 1 | 1 | fix: api url changes of dev
BE | 024e9bef | PW Data Solutions | 2026-05-06 07:14 | Other / Shared | 1 | 24 | 0 | Added Dockerfile
FE | 43f34333 | Kavinkumar Thirumalaisamy | 2026-05-06 13:07 | Contacts | 10 | 161 | 132 | fix: changes of collection list
FE | 49d3b8af | Kavinkumar Thirumalaisamy | 2026-05-06 13:14 | Volunteer | 1 | 3 | 4 | fix: build issue fixed
BE | 40803484 | Kavinkumar Thirumalaisamy | 2026-05-06 13:16 | Campaigns / Crowdfund / P2P | 1 | 19 | 11 | fix: ambaasador list issue fixed
FE | e232ab7b | Kavinkumar Thirumalaisamy | 2026-05-06 13:41 | Communication | 7 | 20 | 14 | fix: build issue fixed
FE | e79dfe2e | Kavinkumar Thirumalaisamy | 2026-05-06 15:20 | Other / Shared | 9 | 225 | 161 | fix: notification template issues
FE | f64a0fe6 | Saranya C | 2026-05-06 15:36 | Communication | 7 | 81 | 50 | fix(communication): test the email campaign screen,email configuration and fix the issues
FE | 5a037417 | Karthick | 2026-05-06 16:35 | Reporting / Dashboard / Audit | 62 | 380 | 98 | feat: add missing routing pages
BE | 6002814b | Karthick | 2026-05-06 17:49 | Other / Shared | 5 | 0 | 117 | fix: remove publish profile
BE | 8cd7feed | Kavinkumar Thirumalaisamy | 2026-05-06 17:57 | System / Access / Config | 8 | 25979 | 0 | fix: contact import changes
FE | 1d36c176 | Karthick | 2026-05-07 12:32 | Other / Shared | 6 | 299 | 429 | feat: move global search dropdown to modal t1778084517173-st1778136872279
FE | 6c95b76d | Saranya C | 2026-05-07 12:40 | Contacts | 5 | 275 | 139 | fix(contact): test the family management screen and update the address section fields
BE | e31ecd36 | Saranya C | 2026-05-07 13:54 | Contacts | 1 | 37 | 19 | fix(contact): test the tags and segmentation screen
FE | 182265df | Kavinkumar Thirumalaisamy | 2026-05-07 17:13 | Campaigns / Crowdfund / P2P | 42 | 1955 | 51 | fix: ambassador performance issue resolved
BE | 1a771a64 | Karthick | 2026-05-07 19:53 | Finance / Payment / Receipt | 7 | 444 | 6 | fix include payment gateway details in global donation query t1777260505103
BE | 07fe66e4 | Karthick | 2026-05-07 19:55 | Finance / Payment / Receipt | 5 | 25185 | 0 | feat: add payment tracking columns in refund entity t1778163784989-st1778163855018
BE | 21704e0b | Karthick | 2026-05-07 20:00 | Finance / Payment / Receipt | 6 | 177 | 5 | feat: implement currency fx rate endpoint and update refund entitye schemas t1778163784989-st1778164
BE | 956a199f | Karthick | 2026-05-07 20:03 | Finance / Payment / Receipt | 1 | 63 | 0 | feat: add refund relevant scripts t1778163784989-st1778164178535
FE | 50d520d5 | Karthick | 2026-05-07 22:07 | Finance / Payment / Receipt | 8 | 534 | 128 | fix: create refund form t1778164312311-st1778171592861
BE | 0100203e | Karthick | 2026-05-08 08:30 | Contacts | 1 | 2 | 13 | fix: remove forpicker condiion in contacts query
BE | 20390740 | Karthick | 2026-05-08 11:50 | Finance / Payment / Receipt | 14 | 26190 | 133 | fix: replace refund type code to refunfundtypeid in refund entity t1778164312311-st1778219675522
FE | 0c4a99a4 | Karthick | 2026-05-08 11:54 | Finance / Payment / Receipt | 9 | 122 | 141 | fix: replace refundtypecode to refundtype foreignkey relation t1778164312311-st1778219923660
FE | 8216214f | Kavinkumar Thirumalaisamy | 2026-05-08 12:35 | Campaigns / Crowdfund / P2P | 30 | 359 | 123 | fix: issues fixes of screens
BE | 5c426fb9 | Karthick | 2026-05-08 12:56 | Finance / Payment / Receipt | 10 | 26075 | 39 | feat: add refund amount and refund date to global donation entity t1778219954820-st1778224960201
FE | b6ea2b8a | Kavinkumar Thirumalaisamy | 2026-05-08 16:51 | Other / Shared | 4 | 29 | 19 | fix: completed receipt book issues
BE | b62cb052 | Kavinkumar Thirumalaisamy | 2026-05-08 16:51 | Finance / Payment / Receipt | 6 | 116 | 141 | fix: pledge issues completed
FE | d952613d | Karthick | 2026-05-08 17:09 | Finance / Payment / Receipt | 18 | 761 | 627 | fix: restructure the refund form and manual payout flow testing
BE | 342dddbd | Karthick | 2026-05-08 17:19 | Finance / Payment / Receipt | 2 | 61 | 17 | fix: update global donation in the refund donation t1778219954820-st1778240492105
BE | 01c41927 | Karthick | 2026-05-08 17:23 | Finance / Payment / Receipt | 1 | 74 | 0 | feat: add refund db script t1778241107072
BE | 0e7626f0 | Karthick | 2026-05-08 18:53 | Communication | 26 | 2168 | 0 | feat: implement sms setup relevant entities and their migration t1778245274203-st1778246452317
FE | f7eac434 | Karthick | 2026-05-08 18:57 | Communication | 22 | 4667 | 0 | feat: implement sms setup screen t1778245274203-st1778246469915
FE | 40df7d48 | Kavinkumar Thirumalaisamy | 2026-05-08 19:08 | Communication | 41 | 6726 | 13 | feat: whatsapp campign screen implemented
BE | b1f23c01 | Kavinkumar Thirumalaisamy | 2026-05-08 19:08 | Communication | 38 | 30920 | 0 | feat: whatsapp campign screen implemented
FE | c3fdf3a5 | Karthick | 2026-05-08 20:41 | Donations | 54 | 5951 | 11 | feat: implement online donation setup screen t1778228873202-st1778228959077
BE | 52738a9c | Karthick | 2026-05-08 20:41 | Donations | 42 | 30827 | 0 | feat: implement online donation relevant entities and their migration t1778228873202-st1778228959077
FE | 57e486fc | Kavinkumar Thirumalaisamy | 2026-05-09 11:05 | Communication | 16 | 316 | 241 | fix: whatsapp campaign and template issue fixed
FE | 50f7161b | Saranya C | 2026-05-09 12:28 | Communication | 14 | 1240 | 413 | fix: test the tags and segmentation screen and check the emalcampaign for segment bulder recipient
BE | 809c33bb | Saranya C | 2026-05-09 12:55 | Communication | 11 | 26115 | 45 | fix: test the tags and segmentation screen and check the email campaign for segment builder recipien
BE | 1fcaaa7e | Kavinkumar Thirumalaisamy | 2026-05-09 13:32 | Campaigns / Crowdfund / P2P | 7 | 542 | 4 | fix: export and flag and approve process completed
FE | f8a786f1 | Kavinkumar Thirumalaisamy | 2026-05-09 14:10 | Campaigns / Crowdfund / P2P | 7 | 449 | 27 | fix: ambassador issues fixes
BE | ac7301d6 | Kavinkumar Thirumalaisamy | 2026-05-09 14:53 | Campaigns / Crowdfund / P2P | 14 | 26500 | 22 | fix : vulnerablitites issues
FE | 2309fce1 | Saranya C | 2026-05-09 17:52 | Communication | 3 | 28 | 49 | fix: fix the action field issue in contacttype index grid
FE | 35b70082 | Saranya C | 2026-05-09 19:04 | Communication | 4 | 14 | 11 | fix: merge the conflicts
BE | 1a15fa15 | Karthick | 2026-05-10 08:36 | Campaigns / Crowdfund / P2P | 65 | 34997 | 0 | feat: implement p2p campaign entities and their mutation and queries t1778326144645-st1778326219088
FE | ff8e036c | Karthick | 2026-05-10 13:06 | Campaigns / Crowdfund / P2P | 69 | 10752 | 3 | feat: implement p2p campaign setup page t1778326144645-st1778326245456
BE | 7d7228de | Karthick | 2026-05-10 13:25 | Communication | 51 | 33498 | 0 | feat: implement prayer request page setup entities and their mutation and queries t1778398787761-st1
BE | 50cb95d3 | Karthick | 2026-05-11 10:38 | Communication | 6 | 361 | 411 | fix: update prayer request page mutation response format
FE | dbafb10a | Saranya C | 2026-05-11 10:59 | System / Access / Config | 3 | 127 | 1 | fix: test the staffcategory screen and refresh the staffcategorysummary after creation
FE | 70d43909 | Karthick | 2026-05-11 11:04 | Communication | 45 | 7187 | 3 | feat: implement prayer request page setup screen t1778398787761-st1778398861036
BE | 2b0a4a43 | Karthick | 2026-05-11 14:29 | Volunteer | 36 | 31986 | 0 | feat: implement volunteer registration page setup relevant entities and their mutation and queries t
BE | 36e8ed7a | Karthick | 2026-05-11 14:34 | Volunteer | 1 | 5 | 5 | feat: update volunteer registration page scripts
FE | 5004f07c | Karthick | 2026-05-11 16:26 | Volunteer | 50 | 6286 | 3 | feat: implement volunteer registration page setup screen t1778479372731-st1778479497191
BE | e8c9bb4f | Karthick | 2026-05-11 16:29 | Volunteer | 2 | 56 | 0 | fix: volunteer schema rendering
BE | 0ef00864 | Karthick | 2026-05-11 17:31 | Donations | 2 | 29 | 3 | fix: update global donation query to include reconcilied for donation retrival t1777260525047-st1778
BE | 488f4331 | Karthick | 2026-05-11 19:56 | Donations | 9 | 965 | 58 | fix: update auto donation suggestion endpoint and reconciliation schema t1777260525047
FE | 86b17eb8 | Karthick | 2026-05-11 20:01 | Donations | 14 | 404 | 271 | feat: test and fix the issues in reconcilation flow t177726052504-st1778502332223
BE | 909c195a | Karthick | 2026-05-12 10:16 | Donations | 3 | 1437 | 0 | feat: add bulk donation import relevant db script t1778559776201-st1778561086761
FE | 7b348c40 | Karthick | 2026-05-12 10:18 | Donations | 5 | 5 | 1657 | feat: implement bulk donation screen t1778559776201-st1778561111931
FE | f84cea82 | Karthick | 2026-05-12 14:09 | Communication | 12 | 2279 | 9 | feat: implement prayer request entry screen t1777260096561-st1778566163296
FE | 645c692b | Karthick | 2026-05-12 14:12 | Communication | 7 | 511 | 4 | feat: implement prayer request queue tab t1777260096561-st1778566206202
BE | 8b827a4a | Karthick | 2026-05-12 15:06 | Events & Auction | 7 | 603 | 5 | feat: update aution item create mutation t1777260096561- st1778578492575
FE | 6dcf3e06 | Karthick | 2026-05-12 15:07 | Events & Auction | 25 | 1296 | 948 | feat: test aution ui flow 1777260096561- st1778578508854
BE | 85878bd7 | Karthick | 2026-05-12 16:15 | Communication | 42 | 62355 | 17 | feat: refactor the prayer request entity and add prayer request reply entity t1778561509712-st177856
FE | 3a297c8d | Karthick | 2026-05-12 16:16 | Communication | 22 | 4603 | 18 | feat: implement prayer request reply tab t1778561509712-st1778566233313
BE | bba5e52c | Karthick | 2026-05-12 16:53 | Campaigns / Crowdfund / P2P | 8 | 890 | 0 | feat: implement p2p campaign summary query t1778581182720-st1778584886691
FE | 66a89bb1 | Karthick | 2026-05-12 16:55 | Campaigns / Crowdfund / P2P | 23 | 2568 | 8 | feat: implement p2p campaign screen t1778581182720- st1778584907736
BE | 10c2cc1c | Karthick | 2026-05-12 19:48 | Events & Auction | 15 | 1995 | 1 | feat: add event analytics widgets functions t1778585325062-st1778585435936
BE | 6da2aa15 | Karthick | 2026-05-12 19:49 | System / Access / Config | 1 | 1 | 1 | fix: replace localhost url
FE | b733c02a | Karthick | 2026-05-12 19:52 | Events & Auction | 21 | 2242 | 6 | feat: implement event analytics dashboard t1778585325062-st1778585455721
BE | d1f7f085 | Karthick | 2026-05-12 20:01 | Communication | 10 | 2136 | 0 | feat: implement email analytics queries t1778585325062-st1778585367496
FE | 6e8cab70 | Karthick | 2026-05-12 20:03 | Reporting / Dashboard / Audit | 34 | 4213 | 4 | feat: implement email analytics screen t1778585325062-st1778585428507
FE | 39c226bb | Karthick | 2026-05-13 12:02 | System / Access / Config | 10 | 558 | 3 | feat: implement number sequence tab in company setting screen t1777696647706-st1777696793413
BE | d53b6939 | Karthick | 2026-05-13 12:07 | System / Access / Config | 5 | 353 | 0 | feat: add number sequence confguration mutation and query t1777696647706-st1778654023650
BE | f5c7e7db | Karthick | 2026-05-13 12:40 | Campaigns / Crowdfund / P2P | 16 | 30310 | 0 | feat: implement p2p fundraiser query and invite mutations t1778649129452
FE | e4fe4fa7 | Karthick | 2026-05-13 12:43 | Campaigns / Crowdfund / P2P | 31 | 3626 | 3 | feat: implement p2p fundraiser screen t1778649129452-st1778654759769
BE | a25e501e | Karthick | 2026-05-13 15:17 | Campaigns / Crowdfund / P2P | 32 | 31737 | 2 | feat: implement crowdfunding entities and their queries and mutation t1778654608479-st1778654923717
FE | 4ce27773 | Karthick | 2026-05-13 15:25 | Campaigns / Crowdfund / P2P | 32 | 4740 | 3 | feat: implement crowdfund screen t1778654608479-st1778654963217
FE | 16e2804c | Karthick | 2026-05-13 16:35 | Reporting / Dashboard / Audit | 8 | 7 | 69 | feat: implement generate report screen t1778660832638-st1778660862924
BE | 052cac01 | Karthick | 2026-05-13 17:58 | Campaigns / Crowdfund / P2P | 15 | 1968 | 0 | feat: implement crowd funding page setup relevant query and mutation t1778654608479-st1778654832630
FE | 5bb06e60 | Karthick | 2026-05-13 18:02 | Campaigns / Crowdfund / P2P | 55 | 5774 | 0 | feat: implement crowd funding page setup screen t1778654608479-st1778654859569
FE | 9a3337d5 | Karthick | 2026-05-13 18:14 | Reporting / Dashboard / Audit | 30 | 3473 | 4 | feat: implement custom builder screen t1778660832638-st1778671563139
BE | 1876e762 | Karthick | 2026-05-13 18:15 | Reporting / Dashboard / Audit | 28 | 31778 | 1 | feat: implement custom builder relevant entities t1778660832638-st1778671505368
BE | ca959014 | Karthick | 2026-05-13 19:24 | Reporting / Dashboard / Audit | 16 | 30031 | 24 | feat: implement reportcatalog relevant entities and their mutation and queries t1778671393041-st1778
FE | e20ebde7 | Karthick | 2026-05-13 19:25 | Reporting / Dashboard / Audit | 19 | 1611 | 3 | feat: implement reportcatalog screen t1778671393041-st1778680365929
BE | b33f45ba | Karthick | 2026-05-13 19:52 | Events & Auction | 28 | 32549 | 0 | feat: implement event registration page entities and their mutation and queries t1778675890340-st177
FE | 4e007533 | Karthick | 2026-05-13 19:55 | Events & Auction | 45 | 6442 | 3 | feat: implement event registration page setup screen t1778675890340-st1778677089409
FE | c6b26f1c | Karthick | 2026-05-14 11:10 | Reporting / Dashboard / Audit | 24 | 2021 | 4 | feat: implement html report screen t1778730294280-st1778731143944
BE | 57ef1d53 | Karthick | 2026-05-14 11:11 | Reporting / Dashboard / Audit | 19 | 30456 | 9 | feat: create html report get all query and remap report entity t1778730294280
FE | d2390750 | Karthick | 2026-05-14 11:30 | Membership | 44 | 3257 | 4 | feat: implement member portal setup screen t1778730476482-st1778731206351
BE | 7a7da206 | Karthick | 2026-05-14 11:32 | Membership | 23 | 30646 | 1 | feat: implement member portal config entity and their mutation and queries t1778730476482-st17787311
FE | 5b88da9e | Karthick | 2026-05-14 12:22 | Reporting / Dashboard / Audit | 47 | 3366 | 4 | feat: implement donor retention dashboard and widgets t1778730335002-st1778738673511
BE | e78d2d77 | Karthick | 2026-05-14 12:23 | Reporting / Dashboard / Audit | 13 | 2373 | 0 | feat: create donor retention dashboard and widgets pg functions t1778730335002-st1778738641768
BE | 9f37eade | Karthick | 2026-05-14 15:02 | Grants | 20 | 30766 | 1 | feat: implement grant calendar event configuration entity and their mutation and queries t1778730476
BE | e040dec1 | Karthick | 2026-05-14 15:05 | Grants | 1 | 5 | 17 | fix: remove grant calendar grid insertion in db script
FE | 60526aa2 | Karthick | 2026-05-14 15:08 | Grants | 32 | 3309 | 3 | feat: implement grant calendar screen t1778730476482-st1778731310131
FE | c2d65293 | Karthick | 2026-05-14 16:15 | Reporting / Dashboard / Audit | 20 | 2199 | 7 | feat: implement power bi report viewer screen t1778743837963-st1778751724305
BE | f1a2cc76 | Karthick | 2026-05-14 16:17 | Reporting / Dashboard / Audit | 17 | 30410 | 29 | feat: refactored power bi report entity and added required mutation and queries t1778743837963
FE | ad074a1b | Karthick | 2026-05-14 16:28 | Reporting / Dashboard / Audit | 20 | 2276 | 12 | fix: duplicate code
BE | e29ad45a | Karthick | 2026-05-14 18:52 | Reporting / Dashboard / Audit | 1 | 707 | 0 | feat: add power bi master db scripts t1778743837963-st1778759154186
FE | 7f4c88ca | Karthick | 2026-05-14 18:55 | Reporting / Dashboard / Audit | 12 | 410 | 150 | feat: implement power bi master screen t1778743837963-st1778759174180
BE | aed8addc | Karthick | 2026-05-14 19:23 | System / Access / Config | 19 | 31482 | 244 | fix: refactor the staff entity and endpoints t177878808437-st1778759007365
FE | 26baa8a4 | Karthick | 2026-05-14 19:25 | System / Access / Config | 37 | 3621 | 2906 | feat: refactor staff screen t177878808437-st1778759014827
BE | 26aba765 | Karthick | 2026-05-14 22:16 | Contacts | 16 | 30398 | 20 | fix: refactor certificate template entity and their mutation t1778767132377-st1778767217937
FE | 72238b79 | Karthick | 2026-05-14 22:17 | Contacts | 31 | 2373 | 44 | fix: refactor certificate template screen t1778767132377-st1778767247182
BE | 7934c430 | Karthick | 2026-05-14 22:34 | Communication | 39 | 33341 | 0 | feat: implement whatsapp conversation related entities and their migration t1778767171624-st17787754
FE | 4340f4b5 | Karthick | 2026-05-14 22:35 | Communication | 36 | 4267 | 3 | feat: implement whatsapp conversation screen t1778767171624-st1778775462938
BE | 40c8c1c3 | Karthick | 2026-05-15 08:58 | Communication | 4 | 94 | 11 | fix: refactored company email provider mutation and queries t1778811882325-st1778811994964
FE | 29052f20 | Karthick | 2026-05-15 08:59 | Communication | 1 | 42 | 30 | fix: refactored company email provider screen t1778811882325- st1778812017722
BE | 11f50ee3 | Karthick | 2026-05-15 09:13 | Contacts | 1 | 114 | 0 | fix: add certificate template process db script t17787767132377- st1778811954297
FE | 00b68ac0 | Karthick | 2026-05-15 09:15 | Contacts | 18 | 1633 | 1032 | fix: convert print and process certificate as single screen t1778767132377-st1778811954297
FE | 35418d19 | Saranya C | 2026-05-15 11:26 | Case & Program | 13 | 2207 | 515 | fix: test the beneficiary screen and fix the issues
BE | b21a1652 | Saranya C | 2026-05-15 11:48 | Case & Program | 25 | 114105 | 78 | fix: test the beneficiary screen and fix the issues
FE | 7eeafb05 | Karthick | 2026-05-15 12:33 | Campaigns / Crowdfund / P2P | 55 | 2913 | 3 | feat: implement ambassador performance dashboard t1778817799793-st1778828487330
BE | bb20dfc8 | Karthick | 2026-05-15 12:36 | Campaigns / Crowdfund / P2P | 9 | 1170 | 1 | feat: implement ambassador performance get query t1778817799793-st1778828466408
BE | 0ed2eb13 | Karthick | 2026-05-15 13:31 | Reporting / Dashboard / Audit | 29 | 33454 | 1 | feat: implement schedule report entities and required mutation and queries t1778817935028-st17788303
FE | 807f0de4 | Karthick | 2026-05-15 13:33 | Reporting / Dashboard / Audit | 22 | 2679 | 4 | feat: implement schedule report screen t1778817935028-st1778830407332
BE | edc8e34e | Karthick | 2026-05-15 14:11 | Finance / Payment / Receipt | 11 | 30688 | 0 | feat: refactor company payment gateway and create payment gateway getall query t1778817799793-st1778
FE | d52b8ef7 | Karthick | 2026-05-15 14:13 | Finance / Payment / Receipt | 19 | 734 | 6 | feat: implemented company payment gateway screen t1778817799793-st1778830614075
BE | b04ed7c6 | Karthick | 2026-05-15 16:07 | System / Access / Config | 13 | 1154 | 1 | fix: refactor organization setting mutations t1778834762016-st1778834818175
FE | db65ecbd | Karthick | 2026-05-15 16:10 | System / Access / Config | 20 | 1377 | 9 | fix: refactor organization screen t1778834762016-st1778834838802
FE | be516f50 | Karthick | 2026-05-15 17:59 | Reporting / Dashboard / Audit | 38 | 5316 | 25 | feat: implement dashboard setup screen t1778730393914-st1778832971053
BE | a18fa91d | Karthick | 2026-05-15 18:11 | Reporting / Dashboard / Audit | 31 | 32375 | 44 | feat: implement dashboard role entity and their widget role mutations t1778730393914-st1778832954486
BE | c9929b76 | Karthick | 2026-05-16 10:45 | Reporting / Dashboard / Audit | 30 | 34072 | 4 | feat: implement audit log entity and their mutation and queries t1778901378899-st1778905415836
FE | 6831fedb | Karthick | 2026-05-16 10:46 | Reporting / Dashboard / Audit | 23 | 2696 | 4 | feat: implement audit log screen t1778901378899-st1778905489790
BE | 3addac7b | Karthick | 2026-05-16 11:33 | Finance / Payment / Receipt | 24 | 32206 | 43 | feat: extend currency entity to include dkisplay fields and update curreny mutation and queries t177
FE | d69dc129 | Karthick | 2026-05-16 11:34 | Finance / Payment / Receipt | 16 | 1049 | 31 | feat: refactored currency screen t1778832445036-st1778908869052
BE | a8a99b95 | Karthick | 2026-05-16 13:20 | System / Access / Config | 12 | 1342 | 1 | feat: update grid mutations and queries for grid config screen t1778730393914
FE | 79e37a88 | Karthick | 2026-05-16 13:22 | System / Access / Config | 27 | 2113 | 7 | feat: implement grid configuration screen t1778730393914
BE | 9da2660b | Karthick | 2026-05-16 15:04 | Finance / Payment / Receipt | 61 | 36132 | 19 | feat: add receipt relvant entities and mutation and queries t1778912171669
FE | 1cea7c54 | Karthick | 2026-05-16 15:09 | Finance / Payment / Receipt | 39 | 4238 | 3 | feat: implement receipt and tax screen t1778912171669
FE | 9839da90 | Karthick | 2026-05-16 16:32 | System / Access / Config | 17 | 2856 | 49 | feat: refactor menu screen and display in tree view t1778924522901-st1778924720787
BE | 9faa4500 | Karthick | 2026-05-16 16:33 | System / Access / Config | 19 | 32871 | 92 | feat: refactor menu entity and their mutations and create menuadmintree query t1778924522901-st17789
FE | a7395fba | Karthick | 2026-05-16 17:29 | System / Access / Config | 24 | 3080 | 1 | feat: implement region hierarchy screen t1778924562477-st1778924626984
BE | 1f4b9c26 | Karthick | 2026-05-16 17:31 | Other / Shared | 10 | 1964 | 0 | feat: implement region hierarchy mutations and queries t1778924562477-st1778932829171
FE | d1715f54 | Karthick | 2026-05-16 22:09 | Other / Shared | 28 | 1310 | 5 | feat: refactor document type screen t1778948062862-st1778948145604
BE | b0d43d27 | Karthick | 2026-05-16 22:10 | Other / Shared | 15 | 32269 | 66 | feat: refactor document type entity and update muations and queries t1778948062862-st1778948130120
BE | c74d5043 | Karthick | 2026-05-16 23:13 | System / Access / Config | 38 | 33937 | 172 | feat: implement user login history and required mutations and queries t1778925318868-st1778949752839
FE | d9db445f | Karthick | 2026-05-16 23:14 | System / Access / Config | 29 | 3324 | 25 | feat: implement user management screen t1778925318868-st1778949877100
FE | cc834bdf | Saranya C | 2026-05-18 11:35 | Communication | 6 | 127 | 198 | fix(communication): test the SMS Template Screen and fix the issues
BE | 9a9373d8 | Saranya C | 2026-05-18 11:36 | Communication | 15 | 28600 | 53 | fix(communication): test the smstemplate screen and fix the issues
FE | 869aeb55 | Karthick | 2026-05-18 13:14 | System / Access / Config | 43 | 3365 | 5 | feat: impleemnt role management screen t1778925318868-st1779089638478
BE | eeade29a | Karthick | 2026-05-18 13:14 | System / Access / Config | 30 | 33518 | 49 | feat: implement role matrix and comparision query t1778925318868-st1779089622678
BE | c2765fc1 | Karthick | 2026-05-18 15:42 | Reporting / Dashboard / Audit | 11 | 31767 | 54 | fix: move auditlog entity to audit schema
FE | 9e2b18d7 | Karthick | 2026-05-18 16:08 | Other / Shared | 25 | 4566 | 3 | feat: implement automation workflow screen t1779075198828
BE | 0551720b | Karthick | 2026-05-18 16:12 | Communication | 30 | 34303 | 0 | feat: implement automation workflow entities and their mutation and queries t1779075198828-st1779094
BE | 5d2fe29d | Karthick | 2026-05-18 18:28 | System / Access / Config | 43 | 34625 | 0 | feat: implement api key and webhook entities and their mutations and queries t1779102095649
FE | e5081187 | Karthick | 2026-05-18 18:31 | System / Access / Config | 33 | 4035 | 4 | feat: implement api key management screen t1779102095649-st1779102218316
BE | 53d9bb5a | Karthick | 2026-05-19 09:41 | AI / AIDA | 56 | 34500 | 0 | feat: implement ai chat system required entities and their migration t1779163437351
FE | 0129c8c6 | Saranya C | 2026-05-19 11:56 | Communication | 9 | 147 | 64 | fix(communication): test the SMS Campaign Screen
BE | 33d451d5 | Saranya C | 2026-05-19 11:58 | Communication | 3 | 99 | 12 | fix(communication): test the SMS Campaign screen
FE | c8e612b6 | Karthick | 2026-05-19 12:51 | System / Access / Config | 25 | 1971 | 4 | feat: implement integration apps screen t1779160887994-st1779161256630
BE | a6ef8972 | Karthick | 2026-05-19 12:55 | System / Access / Config | 22 | 1716 | 0 | feat: implement apps integration entities and their mutations and queries t1779160887994-st177916123
FE | 206378c2 | Karthick | 2026-05-19 13:09 | System / Access / Config | 34 | 3747 | 67 | feat: implement accounting integration screen t1779160934055-st1779161777744
BE | 135fc56a | Karthick | 2026-05-19 13:12 | System / Access / Config | 42 | 36720 | 35 | feat: implement accounting integration related entities and mutations queries t1779160934055
FE | 0a3a5138 | Karthick | 2026-05-19 15:52 | System / Access / Config | 26 | 2630 | 4 | feat: implement social media integration screen t1779160991878-st1779162071371
BE | 46c1a1c9 | Karthick | 2026-05-19 15:54 | System / Access / Config | 33 | 2554 | 1 | feat: implement social media integration required entities and mutations and queries t1779160991878
FE | f42dfa94 | Karthick | 2026-05-19 17:16 | Campaigns / Crowdfund / P2P | 4 | 581 | 8 | feat: implement ambassador collection screen
FE | 2f78be31 | Karthick | 2026-05-19 20:06 | Other / Shared | 250 | 1509 | 276 | feat: integrate company configuration based login ui t1779187830491
BE | 906a54aa | Karthick | 2026-05-19 20:45 | System / Access / Config | 9 | 68062 | 1 | feat: add subdomain and customdomain to company create company login templates details retrival quer
BE | 2cb9f279 | Karthick | 2026-05-19 20:51 | System / Access / Config | 26 | 471 | 334 | feat: include companyid to org setting and user setting entity t1779200746492-st1779203879802
FE | 769cdf7f | Karthick | 2026-05-20 10:51 | System / Access / Config | 17 | 1780 | 522 | feat: create login templates t1779247834804
BE | 9e3602d1 | Karthick | 2026-05-20 10:59 | System / Access / Config | 6 | 447 | 46 | fix: include organization settings to tenant settings retrival query
FE | d24e05c0 | Karthick | 2026-05-20 12:46 | Other / Shared | 9 | 268 | 87 | feat: update theme customizer to include user settings
BE | a790f146 | Karthick | 2026-05-20 13:10 | System / Access / Config | 1 | 8 | 3 | fix: include usersettings in the setting groupbycode query
BE | 8c5d30a7 | Karthick | 2026-05-20 15:15 | Other / Shared | 12 | 2311 | 51 | feat: add crm overview widgets pg functions t1779261114057-st1779261151462
FE | 070d8922 | Karthick | 2026-05-20 15:17 | Reporting / Dashboard / Audit | 23 | 2142 | 136 | feat: implement crm overview dashboard t1779261114057-st1779261223047-st1779261241313
BE | 3a6fabe5 | Karthick | 2026-05-20 15:51 | Other / Shared | 13 | 600 | 60 | feat: Implement timezone helper method t1779261114057-st1779270191634
FE | 9b79075e | Karthick | 2026-05-20 15:53 | Reporting / Dashboard / Audit | 3 | 42 | 28 | fix: handle currency in crm main dashboard t1779261114057-st1779270177587
FE | 5c3cc175 | Karthick | 2026-05-20 19:27 | System / Access / Config | 23 | 2654 | 1520 | feat: improve master dashboard ui and ux t1779187654013
BE | dfcf9da2 | Karthick | 2026-05-20 19:30 | System / Access / Config | 7 | 285 | 30 | feat: add timezone db scripts t1779187654013-st1779285545202
FE | 5a24bad6 | Karthick | 2026-05-20 22:25 | Other / Shared | 19 | 242 | 77 | fix: improve app layout ui t1779187795640-st1779295952692
BE | 078d742a | Karthick | 2026-05-20 22:26 | System / Access / Config | 1 | 8 | 1 | fix: add companyid filteration to the setting group by code query
FE | 9ee7e0c7 | Karthick | 2026-05-21 10:28 | Other / Shared | 1 | 20 | 19 | fix: fix type issue in sidebar logo
BE | 9647c035 | Saranya C | 2026-05-21 12:41 | Communication | 31 | 64266 | 219 | fix: test the SMS Campaign screen
FE | c91aa10e | Saranya C | 2026-05-21 12:45 | Communication | 3 | 24 | 43 | fix: test the SMS Campaign Screen
FE | b1d96f51 | Saranya C | 2026-05-21 17:27 | Membership | 4 | 12 | 7 | fix: test the membershiptier screen
BE | ecd70a05 | Saranya C | 2026-05-21 17:36 | Membership | 3 | 12 | 3 | fix: test the membershipTier screen
FE | 41d2ee4f | Karthick | 2026-05-21 18:58 | Other / Shared | 22 | 221 | 75 | fix: buid and fix type issues t1778210678617-st1779365753332
FE | e525686d | Karthick | 2026-05-21 20:14 | System / Access / Config | 16 | 142 | 149 | fix: buid and fix type issues t1778210678617-st1779365753332
FE | 4fe92d07 | Karthick | 2026-05-21 20:19 | Other / Shared | 7 | 87 | 128 | fix: improve topbar and global search t1779187795640-st1779360737807
FE | 06af49f3 | Karthick | 2026-05-21 22:04 | Other / Shared | 8 | 878 | 1 | feat: add branch test cases and helper functions t1779370445272-st1779370479747-st1779372241550
FE | d767647e | Karthick | 2026-05-22 12:53 | System / Access / Config | 5 | 256 | 17 | fix: update branch screen test cases t1779370445272-st1779431157464
BE | ddd878d5 | Karthick | 2026-05-22 14:30 | System / Access / Config | 3 | 109 | 78 | fix: map staffcategory as nullable in branch query t1779434730064-st1779440299392
FE | fa9a057b | Karthick | 2026-05-22 14:30 | System / Access / Config | 6 | 168 | 62 | fix: test branch screen t1779434730064
FE | 51e31fef | Karthick | 2026-05-25 07:38 | System / Access / Config | 2 | 8 | 18 | fix: change color in branch widgets
BE | 5bf15e15 | Karthick | 2026-05-25 07:39 | System / Access / Config | 1 | 58 | 36 | fix: handle null exception in branchbyid query
BE | a2e8d9dd | Karthick | 2026-05-25 11:39 | Donations | 16 | 34027 | 34 | fix: add pagetype to online donation page and update mutations and queries t1779433870253-st17796867
FE | 2af16379 | Karthick | 2026-05-25 13:17 | Donations | 22 | 2068 | 292 | feat: add donation page types in online donation screen t1779433870253-st1779686752502
BE | f50d03cd | Saranya C | 2026-05-25 15:53 | Case & Program | 3 | 66 | 50 | fix: test the member enrollment screen
FE | 6ca12aa6 | Saranya C | 2026-05-25 15:55 | Case & Program | 10 | 197 | 81 | fix: test the member enrollment screen and fix the issues
FE | eb71b091 | Karthick | 2026-05-25 21:16 | Donations | 10 | 555 | 88 | fix: handle braintree payment gateway drop in ui t1779695336714
BE | bfbdf507 | Karthick | 2026-05-25 21:18 | Donations | 6 | 651 | 82 | fix: handle braintree payment gateway initiate and confirm payment t1779695336714-st1779716942560
BE | 97b3a52f | Karthick | 2026-05-26 13:23 | Finance / Payment / Receipt | 6 | 33979 | 0 | feat: create company payment gateway methods t1779781058806-st1779781966250
BE | 8072fc6c | Karthick | 2026-05-26 15:11 | Donations | 7 | 34445 | 0 | feat: create online donation staging entity t1779781058806-st1779787141540
BE | bb4cbe1d | Karthick | 2026-05-26 15:27 | Finance / Payment / Receipt | 5 | 34121 | 0 | fix: add fk relation to donation purpose and payment gateway in online donation staging
BE | 46aac4a3 | Karthick | 2026-05-26 15:39 | Donations | 6 | 227 | 180 | fix: configured the online donation staging and payment methods in initiate and confirm online donat
FE | 8c12fd9b | Karthick | 2026-05-26 15:43 | Donations | 8 | 84 | 47 | feat: integrate braintree web ui and enable payment methods t1779771312014-st1779790055438
FE | 18a5086e | Karthick | 2026-05-26 19:16 | Donations | 11 | 1789 | 24 | feat: implement online donation page tempates t1779796433141-st1779796463587
FE | fb47cb29 | Karthick | 2026-05-26 19:39 | System / Access / Config | 3 | 13 | 11 | fix: cleanup company configuration entity details t1779794524834-st1779804541865
BE | a60166c2 | Karthick | 2026-05-26 19:41 | System / Access / Config | 13 | 33988 | 483 | fix: cleanup company configuration entity and their child details t1779794524834-st1779803407199
FE | fe4e853d | Karthick | 2026-05-26 19:46 | Donations | 12 | 892 | 920 | fix: handle currency disable multi currency in online donation page t1779771312014-st1779790531344
BE | fa677cdc | Karthick | 2026-05-26 19:47 | System / Access / Config | 26 | 1240 | 682 | fix: handle currency and payment methods in online donation mutation t1779771312014-st1779805021998
BE | 2c556e77 | Karthick | 2026-05-27 14:38 | Finance / Payment / Receipt | 24 | 2885 | 195 | feat: implement razorpayment gateway service implementation t1779850312310-st1779850375902
FE | d3e09b71 | Karthick | 2026-05-27 14:41 | Donations | 5 | 259 | 31 | feat: implement razor pay service in online donation page t1779850312310-st1779865725156
FE | 012fc16c | Karthick | 2026-05-27 15:47 | Donations | 12 | 1088 | 23 | feat: implement online donation page thanks template t1779796433141-st1779802548372
FE | 386b61b1 | Karthick | 2026-05-27 16:43 | Donations | 1 | 474 | 140 | fix: improve online donationpage setup screen ui t1779796433141-st1779877121986
FE | 294eaa1f | Karthick | 2026-05-27 19:53 | Donations | 3 | 62 | 19 | feat: inlclueded contact code field to all the template t1779796433141-st1779882982346
BE | 6875daf9 | Karthick | 2026-05-27 20:12 | Donations | 8 | 33953 | 11 | feat: add frequencyid to online donation staging entity t1779796433141
BE | bcdad493 | Karthick | 2026-05-27 20:32 | Finance / Payment / Receipt | 5 | 66 | 7 | feat: implement recurring donation with braintree payment gateway t1779876140176-st1779876188731
FE | aee648fc | Karthick | 2026-05-27 20:34 | Donations | 6 | 172 | 83 | feat: implement recurring donation with braintree payment gateway t1779876140176-st1779876217715
BE | d809d14b | Saranya C | 2026-05-28 13:00 | Membership | 24 | 34658 | 111 | fix(communication): test the membership renewal screen and fix the issues
FE | 1816593a | Saranya C | 2026-05-28 13:04 | Membership | 14 | 122 | 68 | fix(communication): test the membership renewal screen and fix the issues
BE | 0219b4e0 | Karthick | 2026-05-28 14:38 | Other / Shared | 24 | 35094 | 15 | feat: implement slautation entity and query mutations t1779953094949-st1779955469575
FE | 7be3445a | Karthick | 2026-05-28 14:40 | Other / Shared | 12 | 66 | 45 | feat: implement slautation screen t1779953094949-st1779953546549
FE | 030943ed | Karthick | 2026-05-28 14:46 | Other / Shared | 1 | 1 | 1 | fix: start script in package json
BE | 3888efd2 | Saranya C | 2026-05-28 15:42 | Finance / Payment / Receipt | 5 | 34105 | 1 | fix: remove receiptbookid1 field from receiptbooktransaction entity
FE | 712ef6a4 | Saranya C | 2026-05-28 16:58 | Campaigns / Crowdfund / P2P | 5 | 9 | 32 | fix(organization): fix the build error issue
BE | 4d4c84ae | Saranya C | 2026-05-28 17:47 | Communication | 1 | 8 | 12 | fix: fix the build error
FE | 84472626 | Karthick | 2026-05-28 22:43 | Communication | 8 | 205 | 65 | fix: handle currency and updata company email provider query t1777259576854
BE | 96c7c542 | Karthick | 2026-05-29 08:52 | Communication | 3 | 71 | 19 | fix: include monthly email cost property in email provider state dto
FE | 7a29c1d2 | Karthick | 2026-05-29 10:52 | Donations | 36 | 2066 | 921 | fix: improve ui and ux in online donation page setup t1779941811059-st1779973040798
BE | 666165ef | Karthick | 2026-05-29 11:43 | Finance / Payment / Receipt | 6 | 723 | 18 | feat: implement dynamic recurring plan creation endpoint in razor pay t1779941811059-st1780035145406
BE | cf276230 | Karthick | 2026-05-29 14:16 | Donations | 12 | 2048 | 0 | feat: implement online donation getall queries and mutations t1780040858789-st1780040895437
FE | d07e8132 | Karthick | 2026-05-29 14:17 | Donations | 23 | 2944 | 1 | feat: implement online donation inbox t1780040858789-st1780040915155
BE | a332a49b | Karthick | 2026-05-30 13:42 | Donations | 30 | 34641 | 210 | feat: implement online donation map and automap endpint with functionality t1780032265464
FE | a31892d8 | Karthick | 2026-05-30 13:43 | Donations | 18 | 194 | 185 | feat: implement donation ampping functionality t1780032265464-st1780032329753
BE | b2068f68 | Karthick | 2026-05-30 16:04 | Donations | 9 | 34440 | 0 | feat: implement online donation map job entity t1780129328635-st1780136949145
BE | 198e9a5a | Karthick | 2026-05-30 16:05 | Donations | 12 | 903 | 260 | feat: implement online donation auto map job service t1780129328635-st1780136995542
BE | c1871c1e | Karthick | 2026-05-30 20:14 | Donations | 7 | 130 | 21 | feat: add audit log to online donation page setup endpoints t1778209964083-st1780152206726
FE | 2eebd2f3 | Karthick | 2026-05-30 20:16 | Donations | 13 | 915 | 63 | feat: implement donation map job and job progress panel t1780129328635
BE | 043c5e02 | Saranya C | 2026-06-01 13:40 | Membership | 18 | 35220 | 37 | fix(communication): fix the upgrade tier and sendcard issues in memberenrollment
FE | 9a583b45 | Saranya C | 2026-06-01 13:44 | Case & Program | 8 | 480 | 114 | fix(communication): fix the upgrade tier and sendcard issues in member enrollment screen
BE | 2c23801d | Karthick | 2026-06-01 15:11 | Finance / Payment / Receipt | 13 | 1680 | 6 | feat: implement payu payment gateway service t1780129603034-st1780299820974
FE | 425ebc23 | Karthick | 2026-06-01 15:11 | Donations | 16 | 430 | 61 | feat: integrate payu payment gateway to od page t1780129603034-st1780299851493
BE | 65c34ee1 | Karthick | 2026-06-01 17:16 | Finance / Payment / Receipt | 9 | 640 | 28 | feat: implement recurring donation method with payu t1780306405016-st1780311439208
FE | 0401b653 | Karthick | 2026-06-01 17:17 | Donations | 3 | 11 | 4 | feat: include recurring donation configuration with payu t1780306405016-st1780311439208
BE | f5f17a5c | Karthick | 2026-06-01 17:56 | Donations | 4 | 137 | 8 | chore: add audit track to payu payment service t1780306405016-st1780312149705
BE | 449b790f | Karthick | 2026-06-01 18:36 | Donations | 1 | 17 | 0 | fix: handle onlinedonationpageid in auto donation mapping t1780318114260-st1780318163779
FE | c59cb85a | Karthick | 2026-06-01 18:38 | Donations | 1 | 55 | 13 | fix: improve onlinedonation job confirmation modal t1780318114260-st1780319025730
FE | d46a0ef7 | Karthick | 2026-06-02 11:06 | Other / Shared | 3 | 11 | 7 | fix: build and fix type issue
FE | 3f45923e | Karthick | 2026-06-02 11:32 | Communication | 3 | 46 | 8 | fix: command localhost baseurl
FE | 9da092c6 | Karthick | 2026-06-02 16:16 | Other / Shared | 18 | 28 | 3238 | fix: add payu redirect url to redirect dev
BE | 53b25e03 | Saranya C | 2026-06-02 17:00 | Case & Program | 18 | 69420 | 137 | fix(communication): fix the system and manual approval for membership tiers
FE | ba5d4528 | Saranya C | 2026-06-02 17:55 | Case & Program | 9 | 354 | 92 | fix(communication): fix the system and manual approval for membership tiers
FE | 90658212 | Karthick | 2026-06-02 18:01 | Contacts | 3 | 37 | 11 | fix: handle querystring filter in contact screen t1780398469416-st1780403373645
FE | 9920f319 | Karthick | 2026-06-02 19:18 | Events & Auction | 9 | 168 | 737 | feat: change cutom to flow datatable and handle currency t1780404282254-st1780404631567-st1780407846
BE | 5ba53e69 | Karthick | 2026-06-03 12:18 | Events & Auction | 6 | 287 | 11 | fix: include organizational unit crud opertion in event mutations t1780404282254-st1780469156870
FE | c589f920 | Karthick | 2026-06-03 12:25 | Events & Auction | 5 | 33 | 18 | fix: include parent organizational unit in event sscreen t1780404282254-st1780469193245
BE | e725c42c | Karthick | 2026-06-03 14:38 | Events & Auction | 36 | 35834 | 370 | feat: add event registration page entity and remove registration fields in event entity t17804736593
FE | 61e8c8d4 | Karthick | 2026-06-03 15:14 | Events & Auction | 16 | 194 | 162 | fix: remove event registration page fields in event form t1780473265934-st1780476458124
FE | 95895c60 | Karthick | 2026-06-03 16:11 | Events & Auction | 2 | 31 | 9 | feat: test event creation t1780469671734-st1780469841967
BE | fe718d71 | Karthick | 2026-06-03 16:12 | Events & Auction | 3 | 194 | 52 | feat: include org insertion in event creation t1780469671734-st1780469841967
FE | 2114b733 | Karthick | 2026-06-03 18:18 | Events & Auction | 2 | 119 | 9 | fix: test event creation and child creation flow t1780469671734
FE | da487a89 | Karthick | 2026-06-03 19:04 | Events & Auction | 6 | 185 | 145 | chore: improve event screen index and form ui t1780490712327-st1780490850225
BE | f4f44211 | Karthick | 2026-06-03 19:04 | Events & Auction | 6 | 34429 | 3 | chore: remove string length in banner image and event gallery image in event entity t1780469671734-s
FE | c8d0267b | Karthick | 2026-06-04 13:44 | Events & Auction | 8 | 482 | 486 | Fix: test event ticket creation t1777260070046
FE | 8f00148d | Karthick | 2026-06-04 14:49 | Events & Auction | 1 | 52 | 1 | chore: test duplicate ticket creation flow t1777260070046-st1780562599601
BE | 3df5c98d | Karthick | 2026-06-04 14:50 | Events & Auction | 1 | 4 | 1 | chore: clear benefits before add benefits t1777260070046-st1780562599601
FE | 540b582e | Saranya C | 2026-06-04 15:05 | Case & Program | 10 | 404 | 199 | fix(communication): add Approve, Reject, Suspend, and Cancel buttons to the Action field
BE | 198f6656 | Karthick | 2026-06-04 15:53 | Events & Auction | 32 | 34448 | 586 | fix: remove event setting suggested amount and ticket type entities t1779794524834-
FE | e9591796 | Karthick | 2026-06-04 16:03 | Events & Auction | 28 | 173 | 2261 | fix: remove event setting suggested amount and ticket type t1779794524834-st1780566605197
FE | 65b2abc3 | Karthick | 2026-06-04 16:26 | Events & Auction | 7 | 83 | 80 | feat: improve event ticket screen ui and ux t1780567665246-st1780570239505
FE | 69b69e4f | Karthick | 2026-06-04 16:41 | Events & Auction | 8 | 57 | 57 | feat: improve event ticket screen ui and ux t1780567665246-st1780570239505
BE | 77d37c38 | Karthick | 2026-06-04 18:33 | Events & Auction | 5 | 34422 | 16 | feat: add company payment gateway to event registration page entity t1779434117745-st1780573207827
FE | 0df62571 | Karthick | 2026-06-04 19:01 | Events & Auction | 18 | 1963 | 360 | chore: include payment gateway template and gallery to event reg form t1779434117745
BE | 00f46b6a | Karthick | 2026-06-04 19:04 | Events & Auction | 16 | 258 | 124 | chore: updated event registration page mutation to include event speakers and gallery crud t17794341
FE | 7295257d | Saranya C | 2026-06-04 22:52 | Case & Program | 4 | 366 | 42 | fix: upload the document in beneficiary screen
BE | d9b61a56 | Saranya C | 2026-06-04 22:53 | Case & Program | 2 | 169 | 0 | fix: upload the document in beneficiary screen
FE | 2d0e3ac6 | Saranya C | 2026-06-05 11:59 | Other / Shared | 1 | 9 | 1 | fix: check the index grid design when navigating from one menu to other menu
FE | c9bdc9f9 | Karthick | 2026-06-05 12:34 | Events & Auction | 17 | 132 | 158 | feat: include comapany currency and improve ui in event registration page t1780640240191-st178064066
FE | dd83c134 | Karthick | 2026-06-05 15:47 | Events & Auction | 20 | 2331 | 614 | feat: implement registration templates t1780640240191-st1780640333791
FE | 210fcd58 | Saranya C | 2026-06-05 16:15 | Membership | 6 | 231 | 26 | fix: check the membershiprenewal filteration issue and fix the issues
BE | a254cb79 | Saranya C | 2026-06-05 16:15 | Membership | 2 | 26 | 9 | fix: check the membership filteration issue and fix the issues
FE | 01f84504 | Karthick | 2026-06-05 17:35 | Events & Auction | 17 | 853 | 393 | feat: add festival page template t178653404757
BE | 563b5b9c | Karthick | 2026-06-05 19:16 | Events & Auction | 4 | 34254 | 0 | feat: add currency and enableads tto event registration page t1780659382926-st1780659414425
BE | 891f66b8 | Karthick | 2026-06-05 22:59 | Events & Auction | 19 | 35319 | 177 | feat: add event registration payment entity and handle payment initiate in event registration t17806
FE | 1176e07d | Karthick | 2026-06-08 13:00 | Events & Auction | 8 | 742 | 119 | fix: handle payment gateway in the registration button
BE | d3413b36 | Karthick | 2026-06-08 17:26 | Communication | 7 | 34462 | 0 | feat: add issystem and remainder fields in emailsendjob and eventregistrationpage entities t17808979
BE | b7e4907d | Karthick | 2026-06-08 21:45 | Events & Auction | 32 | 70742 | 94 | feat: implement email communication for event creation
FE | 10ec3ece | Karthick | 2026-06-08 21:49 | Events & Auction | 6 | 709 | 28 | feat: integrate saved filter and email template in event registration setup
BE | b99935c1 | Karthick | 2026-06-09 08:49 | Communication | 5 | 34406 | 8 | fix: change contactid as nullable in email send queue t178091566425-st1780974704268
BE | e78dcef0 | Karthick | 2026-06-09 10:42 | Events & Auction | 19 | 35377 | 0 | feat: implement event ticket template entity t1780976840822-st1780980210358
FE | 2d580849 | Saranya C | 2026-06-09 10:57 | Membership | 3 | 76 | 2 | fix: test the email service in membership renewal screen
BE | 1dd16998 | Saranya C | 2026-06-09 11:20 | Membership | 3 | 209 | 106 | fix: test the email service in membership renewal screen
FE | 58200974 | Karthick | 2026-06-09 12:12 | Events & Auction | 20 | 1359 | 14 | featL: implement event ticket template screen t1780976840822-st1780980236189
BE | 59ab213a | Karthick | 2026-06-09 12:15 | Events & Auction | 4 | 66 | 124 | fix: handle event template as nullable in event ticket mutaions
BE | 72e9d6e9 | Karthick | 2026-06-09 13:37 | Events & Auction | 11 | 34531 | 0 | feat: include event ticket template into event ticketing entity t1780567665246-st1780987439389
FE | efc4b2c9 | Karthick | 2026-06-09 13:40 | Events & Auction | 9 | 486 | 253 | feat: include event ticket template into event ticketing screen t1780567665246-st1780987466894
BE | a1657da7 | Karthick | 2026-06-09 16:48 | Events & Auction | 11 | 35189 | 30 | feat: include payment success and ticket templates and include ticket file attachement logics in ema
FE | f6fa8735 | Karthick | 2026-06-09 16:56 | Events & Auction | 6 | 270 | 37 | feat: include payment success and ticket email configuration
BE | 6c89701b | Karthick | 2026-06-09 17:34 | System / Access / Config | 1 | 1 | 1 | fis: update dev fe url in appsettings
BE | 448e0046 | Karthick | 2026-06-10 15:30 | Events & Auction | 3 | 54 | 17 | fix: update event properties if handle null t1781074633244-st1781085574624
FE | e193972f | Karthick | 2026-06-10 15:33 | Events & Auction | 37 | 419 | 673 | feat: merge event ticket and reagitration into event screen t1781074633244
BE | a07996bd | Shyam Prakash J | 2026-06-10 17:19 | Grants | 4 | 33 | 31 | fix: resolve grant grid fields loading and fix module decorator for all grants
FE | f3b6a746 | Shyam Prakash J | 2026-06-10 17:20 | Grants | 4 | 103 | 37 | fix: align grant mutations and form with BE contract for all grant
BE | 3b6f21bc | Shyam Prakash J | 2026-06-10 17:58 | Grants | 2 | 20 | 19 | fix: revert grant decorator to match renamed menu code for all grants
FE | 56854be6 | Shyam Prakash J | 2026-06-10 17:58 | Grants | 2 | 3 | 1 | fix: fix stage filter id fields and align grant menu code for all grants to fix action column issue
BE | 7ef5754f | Shyam Prakash J | 2026-06-11 06:39 | Grants | 3 | 24 | 21 | fix(grant-report): fix seed script and Mapster mappings for grant reporting
FE | a1ac4a5c | Shyam Prakash J | 2026-06-11 06:46 | Grants | 10 | 158 | 111 | fix(grant-report): funder reporting testing fixes
BE | 177f4590 | Karthick | 2026-06-11 06:50 | Events & Auction | 10 | 319 | 13 | fix: handle ready to publish functionality in event t178105947617-st1781140786254
FE | 44289b04 | Karthick | 2026-06-11 06:53 | Events & Auction | 24 | 836 | 896 | fix: integrate publish and validation functionality to event t178105947617-st1781140943490
FE | d5a81451 | Shyam Prakash J | 2026-06-11 06:57 | Other / Shared | 1 | 6 | 6 | fix: change base url config
BE | fbaae83d | Karthick | 2026-06-11 06:58 | Events & Auction | 2 | 116 | 26 | fix: include event reagitration details into event dashboard and event summary endpoint t17810594761
FE | c6795d9a | Karthick | 2026-06-11 07:01 | Events & Auction | 1 | 130 | 142 | fix: include event reagitration details into event dashboard and event summary endpoint t17810594761
FE | cd62bb2f | Shyam Prakash J | 2026-06-11 07:22 | Grants | 1 | 83 | 26 | feat(grant-detail): wire Reports tab to live data for screen #62
BE | 378707c7 | Shyam Prakash J | 2026-06-11 08:47 | Grants | 2 | 2 | 2 | fix: auth error and calendar event mutations issue in GrantCalendar
FE | 01f6cb44 | Saranya C | 2026-06-11 10:49 | Membership | 5 | 114 | 75 | fix(communication): assign the benefits for Tiers & plans
BE | 9885e5b0 | Saranya C | 2026-06-11 10:49 | Membership | 2 | 16 | 16 | fix(communication): assign the benefits for Tiers & plans
FE | eb94e926 | Shyam Prakash J | 2026-06-11 11:09 | Grants | 2 | 26 | 12 | fix(GrantCalendar): fix bugs found during business flow testing
BE | 61287700 | Karthick | 2026-06-11 13:01 | Events & Auction | 18 | 34906 | 49 | feat: add registrationform fields into registration entity t1781160386780-st1781160428770
FE | 747e8c10 | Ganesh | 2026-06-11 13:15 | System / Access / Config | 3 | 262 | 0 | feat(custom-components): add reusable MasterDataFilterChipsBar
FE | bdfd0ebf | Ganesh | 2026-06-11 13:15 | Case & Program | 2 | 124 | 39 | fix(case-service): align mutations to BaseApiResponse envelope
FE | 5a5466e5 | Ganesh | 2026-06-11 13:15 | Case & Program | 6 | 27 | 530 | refactor(case-list): drop bespoke advanced filter and quick-add modal
FE | c615485b | Ganesh | 2026-06-11 13:16 | Case & Program | 2 | 34 | 27 | fix(case-form): surface BE errors and normalize date payloads
FE | 85f1ca59 | Ganesh | 2026-06-11 13:16 | Case & Program | 2 | 20 | 8 | fix(case-modals): surface BE errors on reassign and status update
FE | 16d99c9e | Ganesh | 2026-06-11 13:16 | Case & Program | 1 | 202 | 39 | feat(case-notes-tab): add per-note edit and delete
FE | 49d22a50 | Ganesh | 2026-06-11 13:17 | Case & Program | 1 | 201 | 22 | feat(case-action-plan-tab): add per-item edit and delete
FE | 711ea0eb | Ganesh | 2026-06-11 13:18 | Case & Program | 1 | 242 | 95 | feat(case-referrals-tab): add per-referral edit and delete
FE | 85f1914e | Ganesh | 2026-06-11 13:18 | Case & Program | 5 | 27 | 293 | refactor(beneficiary-list): remove inline filters and register shortcut
FE | c0bd4382 | Karthick | 2026-06-11 13:48 | Events & Auction | 19 | 584 | 434 | fix: handle registration form fields in to the registration page setup
BE | f8c206cc | Karthick | 2026-06-11 13:50 | Events & Auction | 2 | 126 | 0 | feat: implement unpublish event endpoint t1781160386780-st1781163269229
FE | df2709d7 | Karthick | 2026-06-11 15:53 | Events & Auction | 14 | 573 | 156 | fix: improve ui and ux in event screen
FE | 3ee42bbd | Ganesh | 2026-06-11 16:10 | Case & Program | 2 | 73 | 7 | fix(beneficiary-service): align toggle envelope and add cases query
FE | a795efae | Ganesh | 2026-06-11 16:11 | Case & Program | 8 | 1606 | 1050 | refactor(beneficiary-detail): modularize layout and add Cases tab
FE | 67d5f8d3 | Ganesh | 2026-06-11 16:11 | Case & Program | 2 | 91 | 73 | refactor(beneficiary-modals): use shared form fields in modals
BE | 7aabb98a | Karthick | 2026-06-11 16:12 | Events & Auction | 3 | 143 | 20 | fix: include event registration details in the event getall handler
BE | 97c09edc | Karthick | 2026-06-11 17:57 | Events & Auction | 6 | 34689 | 15 | feat: handle contactcode to communication in the event registration t1781166550213-st1781174139660
BE | d2dd5f4e | Shyam Prakash J | 2026-06-11 18:42 | Grants | 4 | 577 | 8 | feat(grant-report): wire transactional emails on status transitions
BE | 5457908a | Karthick | 2026-06-11 18:54 | Events & Auction | 3 | 645 | 0 | feat: create script for sample data insertion for event t1781166550213-st1781183313574
BE | bd88f6ba | Karthick | 2026-06-11 19:59 | Events & Auction | 5 | 384 | 0 | feat: add auction items winner query t1781068479186-st1781188078053
FE | a90fe6c0 | Karthick | 2026-06-11 20:01 | Events & Auction | 19 | 1151 | 1180 | feat: convert custom grid to flow grid for auction items winner grid t1781068479186-st1781188107464
FE | 5ccb80d7 | Karthick | 2026-06-12 09:01 | Events & Auction | 4 | 167 | 35 | fix: handle event completion flow
BE | 38c0d7f4 | Karthick | 2026-06-12 09:05 | Events & Auction | 3 | 59 | 19 | fix: handle close bidding functionality t1781068479186-st1781234262793
FE | b3ef9fce | Karthick | 2026-06-12 09:06 | Other / Shared | 12 | 184 | 161 | fix: convert flow grid ti adv grid auction
BE | 6297792c | Shyam Prakash J | 2026-06-12 10:25 | Grants | 3 | 37 | 11 | fix(grant-report): resolve email send failures and missing template placeholders
FE | ee5c723d | Shyam Prakash J | 2026-06-12 12:02 | Grants | 3 | 16 | 8 | feat(grant-report): pre-populate grant field from URL and mark executive summary required
BE | 2e5d3721 | Karthick | 2026-06-12 12:13 | Events & Auction | 3 | 147 | 29 | fix: handle status based reserve price t1781068479186-st1781246470195
BE | 792cb226 | Karthick | 2026-06-12 12:16 | Events & Auction | 1 | 21 | 4 | fix: handle event summary data retrval based status t1781232005864-st1781246715226
FE | aa91744c | Shyam Prakash J | 2026-06-12 12:23 | Grants | 2 | 114 | 6 | feat(grant-report): wire Accept and Request Revision actions on detail view
FE | 49cfd40d | Ganesh | 2026-06-12 12:53 | Case & Program | 2 | 5 | 5 | fix(program-service): align with BE rename and LocalDate scalar
FE | c0989c99 | Ganesh | 2026-06-12 12:54 | Case & Program | 3 | 461 | 495 | refactor(program-form): use shared form fields and add load skeleton
FE | ae920b2e | Ganesh | 2026-06-12 12:54 | Case & Program | 2 | 20 | 2 | feat(case-dashboard): open scoped to a program from the program card
FE | 5996bce5 | Shyam Prakash J | 2026-06-12 13:25 | Grants | 3 | 25 | 15 | fix(grant): rejected stage missing from kanban, dialog cut-off, executive summary UX
FE | 94ee9ac6 | Ganesh | 2026-06-12 13:47 | Case & Program | 4 | 191 | 26 | feat(case-and-beneficiary-detail): layout-matching loading skeletons
BE | 6c304fd3 | Karthick | 2026-06-12 13:55 | Events & Auction | 15 | 404 | 141 | fix: update event analytics widgets to include status t1781246931573-st1781247250962
FE | 0a8d489e | Karthick | 2026-06-12 13:56 | Events & Auction | 12 | 288 | 233 | fix: test event analytics widgets t1781246931573-st1781247208723
BE | 8b288d13 | Shyam Prakash J | 2026-06-12 17:24 | Grants | 15 | 35037 | 1 | feat(grant): implement GrantExpense entity and expense logging commands (#62 sub-feature)
FE | 20f75206 | Ganesh | 2026-06-12 17:40 | Reporting / Dashboard / Audit | 2 | 23 | 0 | fix(dashboards): coerce numeric responses and drop unresolved params
FE | 6bdba391 | Ganesh | 2026-06-12 17:40 | Case & Program | 18 | 419 | 190 | feat(case-dashboard-widgets): standardize data wiring and visual polish
FE | 67b50dd0 | Karthick | 2026-06-12 19:02 | Events & Auction | 1 | 10 | 3 | fix: include language in the donation page url
BE | be143ae2 | Karthick | 2026-06-12 19:05 | Events & Auction | 3 | 1149 | 8 | fix: add domain retrival functionality
FE | 1eb89c31 | Ganesh | 2026-06-15 12:10 | Case & Program | 2 | 25 | 5 | fix: case Mutation fix gql querires
BE | c12e5313 | Ganesh | 2026-06-15 12:14 | Case & Program | 10 | 272 | 93 | feat: add beneficiary cases query and compute active case count
FE | ef9912fc | Shyam Prakash J | 2026-06-15 12:29 | Grants | 5 | 365 | 14 | feat(grant): expense logging UI — modal, list, delete confirm (#62 sub-feature)
BE | 2379066e | Karthick | 2026-06-15 13:26 | System / Access / Config | 12 | 34804 | 7 | feat: include landing url in role entity and add into login mutation reponse t1781507761032-st178150
FE | fefae76e | Shyam Prakash J | 2026-06-15 13:46 | Grants | 7 | 29 | 97 | fix(grant): standardise currency via companySettingsFormatters
FE | 4f1f9935 | Ganesh | 2026-06-15 13:46 | Case & Program | 6 | 545 | 264 | feat(case-module): refresh KPI widgets and hide inline row actions
FE | 2e09211e | Ganesh | 2026-06-15 14:22 | Other / Shared | 1 | 24 | 0 | fix: avanced filter in the searchable select issue
BE | f1f0ff3c | Shyam Prakash J | 2026-06-15 14:31 | Grants | 3 | 7 | 0 | feat(grant-report): propagate grant currency code through report DTOs
FE | cd0e9316 | Shyam Prakash J | 2026-06-15 14:32 | Grants | 7 | 33 | 17 | feat(grant-report): display financial amounts in grant's own currency
BE | e07ba328 | Karthick | 2026-06-15 15:31 | Contacts | 8 | 34793 | 8 | fix: replace staffuserid to userid in contact entity t1781507761032-st1781517573395
BE | a9acf171 | Karthick | 2026-06-15 15:31 | Contacts | 8 | 34793 | 8 | fix: replace staffuserid to userid in contact entity t1781507761032-st1781517573395
BE | 1714900d | Karthick | 2026-06-15 16:35 | System / Access / Config | 4 | 322 | 17 | feat: Add member portal menus scripts and settings t1781500294620-st1781521464390
BE | c01d97c8 | Karthick | 2026-06-15 20:08 | Membership | 1 | 9 | 9 | fix: update membership screen urls
BE | 993e3b41 | Shyam Prakash J | 2026-06-16 09:41 | Grants | 3 | 8 | 2 | fix(grant-report): add grant awarded amount and dates to report response DTO
FE | dd166bb7 | Shyam Prakash J | 2026-06-16 09:43 | Grants | 3 | 16 | 4 | fix(grant-report): populate context card in edit mode and fix silent submit failure
BE | 8d73feca | Saranya C | 2026-06-16 10:50 | Membership | 30 | 71283 | 194 | fix: implement the auto-renewal process in membershiprenewal
FE | 2d53f7fc | Saranya C | 2026-06-16 10:54 | Membership | 7 | 1533 | 321 | fix: implement the auto-renewal process in the membershiprenewal screen
BE | 5138ebeb | Karthick | 2026-06-16 14:47 | System / Access / Config | 3 | 1114 | 0 | feat: add db script for mock data insertion t1781592970996-st1781593293984
FE | 155673ed | Shyam Prakash J | 2026-06-16 14:48 | Grants | 3 | 82 | 31 | feat(grant-widgets): render per-currency KPI totals with overflow tooltip
BE | a53d4aaf | Karthick | 2026-06-16 14:48 | Case & Program | 11 | 39 | 35 | feat: update master data status to uppercase in db script and case muations and queries t17815929709
BE | 1661b9a8 | Shyam Prakash J | 2026-06-16 14:52 | Grants | 2 | 21 | 12 | feat(grant-summary): group KPI funded totals by currency instead of blind sum
BE | e4176326 | Karthick | 2026-06-16 17:02 | System / Access / Config | 5 | 343 | 8 | feat: implement program code auto generation t1777260165048-st1781606464796
FE | 9cecf0d6 | Karthick | 2026-06-16 17:03 | Case & Program | 9 | 241 | 193 | feat: implement program code auto generation t1777260165048-st1781606464796
FE | e2f9e618 | Shyam Prakash J | 2026-06-16 17:27 | Grants | 2 | 6 | 6 | fix(grant): fix info tooltip overlap and remove hardcoded currency from amount filter
BE | 39c490f2 | Shyam Prakash J | 2026-06-16 17:28 | Grants | 1 | 2 | 2 | fix(grant): clear ParentObject for Funder and Branch GridFields
FE | a099d9bb | Karthick | 2026-06-16 18:38 | Case & Program | 12 | 82 | 47 | fix: test program screen and fix ui bugs t1777260165048-st1781615244464
BE | dc9f09d4 | Karthick | 2026-06-16 18:45 | Case & Program | 6 | 8 | 6 | fix: test program screen and fix bugs t1781615202007-st1781615706859
FE | f2cf4c11 | Karthick | 2026-06-17 12:19 | Case & Program | 6 | 270 | 120 | feat: improve ux and ui t1781615922663-st1781678917490
BE | b5036ffa | Karthick | 2026-06-17 13:58 | Case & Program | 13 | 35227 | 44 | feat: change relation fk in beneficiary entities and include squence generation t178165922663-st1781
FE | 8215a271 | Karthick | 2026-06-17 14:03 | Case & Program | 8 | 188 | 100 | feat: handle beneficiary status and codes t178165922663-st1781679936460
BE | b2169111 | Karthick | 2026-06-17 17:15 | Case & Program | 7 | 35115 | 0 | feat: include case into beneficiary service andmilestone t1781685242462-st1781696242464
FE | 0788db28 | Karthick | 2026-06-17 17:37 | Case & Program | 15 | 549 | 143 | feat: test beneficiary lifecycle t1781685242462-st1781690125461
BE | 758272f9 | Karthick | 2026-06-17 17:38 | Case & Program | 5 | 68 | 0 | feat: test beneficiary lifecycle t1781685242462-st1781690125461
BE | 8130f90c | Shyam Prakash J | 2026-06-18 09:18 | Campaigns / Crowdfund / P2P | 2 | 56 | 8 | fix: resolve P2P campaign FK columns dynamically instead of hardcoded values
FE | 41107a69 | Shyam Prakash J | 2026-06-18 09:21 | Campaigns / Crowdfund / P2P | 4 | 169 | 67 | feat: P2P campaign create opens blank form instead of auto-creating draft
FE | d7014d72 | Shyam Prakash J | 2026-06-18 09:41 | Campaigns / Crowdfund / P2P | 2 | 17 | 4 | fix: correct null select values and DateTime format in P2P campaign editor
FE | ae0c7e86 | Shyam Prakash J | 2026-06-18 10:32 | Campaigns / Crowdfund / P2P | 1 | 2 | 2 | fix: Organizational Unit render issue
FE | 997f7dac | Shyam Prakash J | 2026-06-18 10:59 | Campaigns / Crowdfund / P2P | 4 | 16 | 8 | fix: replace hardcoded currency with goalCurrencyCode across P2P editor tabs and live preview
BE | 95518a9c | Shyam Prakash J | 2026-06-18 15:57 | Campaigns / Crowdfund / P2P | 2 | 45 | 1 | fix: populate display name fields in GetP2PCampaignPageById response
FE | a2a3ec7a | Shyam Prakash J | 2026-06-18 15:57 | Campaigns / Crowdfund / P2P | 5 | 61 | 6 | fix: P2P campaign page editor — create flow, currency display, template dropdowns
BE | 6f3a9dbb | Shyam Prakash J | 2026-06-18 19:30 | Campaigns / Crowdfund / P2P | 1 | 2 | 1 | fix(p2p): include Currency and OrganizationalUnit in list query
FE | 10c6c8be | Shyam Prakash J | 2026-06-18 19:32 | Campaigns / Crowdfund / P2P | 2 | 41 | 23 | fix(p2p-crm): currency symbol display in CRM grid and detail sheet
FE | 7ca20ecd | Shyam Prakash J | 2026-06-19 09:04 | Campaigns / Crowdfund / P2P | 3 | 59 | 12 | fix(p2p): pagination, KPI currency format and progress bar fix
FE | c9321c07 | Karthick | 2026-06-19 10:26 | Case & Program | 8 | 577 | 702 | feat: implement timeline for service and milestones
BE | 7f6cd657 | Karthick | 2026-06-19 10:27 | System / Access / Config | 5 | 1326 | 0 | fix: handle beneficiary enroll status in create beneficiary
BE | e8e9a34e | Karthick | 2026-06-19 13:58 | Case & Program | 14 | 35695 | 47 | feat: include program type and approval fields in program t1781850235342-st1781850280330
FE | 5bbaa941 | Karthick | 2026-06-19 14:00 | Case & Program | 6 | 289 | 155 | feat: include program type and approval fields in program form t1781850235342-st1781857811690
BE | 4703d71e | Karthick | 2026-06-19 14:20 | Case & Program | 9 | 35354 | 2 | feat: include verfication method and required document in program eligibility criterion t17818502353
BE | 2b3d81bf | Karthick | 2026-06-19 17:13 | Case & Program | 11 | 35568 | 20 | feat: include service type and provider type into program service t1781858797568-st1781865032754
FE | 1653cb92 | Karthick | 2026-06-19 17:15 | Case & Program | 6 | 485 | 177 | feat: include service type and provider type into program form t1781858797568-st1781865068134
BE | da5f263a | Shyam Prakash J | 2026-06-19 17:45 | Campaigns / Crowdfund / P2P | 2 | 37 | 10 | fix: InviteP2PFundraiser — resolve FK fields + fix P2PF_ACTIONS FieldKey collision
FE | f7797eaa | Shyam Prakash J | 2026-06-19 17:50 | Campaigns / Crowdfund / P2P | 3 | 33 | 32 | fix: P2PFundraiser — invite modal UX fixes + actions cell Row<any> pattern
BE | 5d26ddd9 | Karthick | 2026-06-19 19:34 | Case & Program | 14 | 35420 | 17 | feat: implement program funding source t1781876709886-st1781876949278
FE | cd06f87b | Karthick | 2026-06-19 19:35 | Case & Program | 7 | 483 | 22 | feat: integrate program funding source to program form t1781876709886-st1781876980208
BE | 8cf2b92d | Shyam Prakash J | 2026-06-21 16:46 | Campaigns / Crowdfund / P2P | 2 | 57 | 38 | fix(p2pfundraiser): refactor KPI summary to per-currency grouping
FE | 10309e95 | Shyam Prakash J | 2026-06-21 16:50 | Campaigns / Crowdfund / P2P | 3 | 68 | 24 | fix(p2pfundraiser): currency-aware KPI widgets
BE | 7f054b2a | Karthick | 2026-06-22 09:12 | Case & Program | 14 | 35739 | 8 | feat: add program funding transaction entity and their mutation t1782096930533-st1782097008337
BE | 8f8f5439 | Karthick | 2026-06-22 10:08 | Case & Program | 8 | 35361 | 9 | feat: include expected amount in funding source t1782096930533-st1782103020355
FE | 3f52565f | Karthick | 2026-06-22 10:09 | Case & Program | 5 | 646 | 133 | feat: add program funding transaction entity and amount fields in program funding t1782096930533-st1
BE | 42ed394b | Karthick | 2026-06-22 10:46 | Case & Program | 11 | 35904 | 20 | feat: refactor the program outcome metric t1782104687120-st1782104771872
FE | acf4e418 | Karthick | 2026-06-22 11:51 | Case & Program | 6 | 311 | 101 | feat: refactored program outcome metrics t1782104687120-st1782104803464
FE | 9ac24aa4 | Shyam Prakash J | 2026-06-22 12:37 | Campaigns / Crowdfund / P2P | 5 | 163 | 105 | feat(p2p): wire send-message, fix preview, remove coming-soon stubs
BE | e4dbb8f0 | Karthick | 2026-06-22 13:22 | Case & Program | 14 | 35816 | 4 | feat: implement beneficiary enrollment service entity and their mutation t178204687120-st17821109765
FE | 6c295153 | Karthick | 2026-06-22 13:24 | Case & Program | 8 | 420 | 16 | feat: include beneficiary enrollment into beneficiary form t178204687120-st1782111136626
BE | 6ed199f8 | Karthick | 2026-06-22 16:09 | Case & Program | 41 | 37312 | 27 | feat: implement beneficiary eligibility verification entity and mutations t1782115454586
FE | a47784fd | Karthick | 2026-06-22 17:24 | Case & Program | 23 | 2059 | 940 | feat: include service log and milestone into case screen t1782115454586
FE | 30b86ef5 | Karthick | 2026-06-22 17:24 | Case & Program | 3 | 50 | 8 | feat: include service log and milestone into case screen t1782115454586
FE | 24a3d37b | Shyam Prakash J | 2026-06-22 19:13 | Campaigns / Crowdfund / P2P | 4 | 199 | 8 | feat(p2p): add Edit Fundraiser modal wired to UpdateP2PFundraiserAdmin
BE | d07dcc60 | Shyam Prakash J | 2026-06-22 19:14 | Campaigns / Crowdfund / P2P | 2 | 68 | 1 | feat(p2p): extend UpdateP2PFundraiserAdmin to support name, phone and greeting edits
BE | 14307824 | Shyam Prakash J | 2026-06-23 13:33 | Campaigns / Crowdfund / P2P | 2 | 2 | 2 | fix: correct CrowdFund decorator MenuCode and empty-list resolver guard
FE | f10bbe08 | Shyam Prakash J | 2026-06-23 13:36 | Campaigns / Crowdfund / P2P | 2 | 27 | 19 | fix: crowdfund dialogs — DialogBody padding and SelectContent z-index
FE | e5f8f111 | Karthick | 2026-06-23 13:53 | Case & Program | 7 | 29 | 1 | feat: implement program approval t1782200160858-st1782200393716
BE | 3aa64caa | Karthick | 2026-06-23 13:57 | Case & Program | 2 | 134 | 0 | feat: add db scripts for program approval and fund allocation t1782200160858-st1782200309056-st17822
BE | 608cd464 | Karthick | 2026-06-23 14:19 | Case & Program | 8 | 629 | 68 | feat: implement fund allocation mutations and getall queries t1782200160858-st1782200250124
FE | 5a2580d4 | Karthick | 2026-06-23 14:20 | Case & Program | 9 | 920 | 3 | feat: implement fund allocation screen t1782200160858-st1782200269426
BE | b4c88d28 | Karthick | 2026-06-23 16:48 | Case & Program | 11 | 35688 | 182 | feat: include payment status into program funding transaction and their schemas t1782211473146-st178
FE | b66a4db5 | Karthick | 2026-06-23 17:19 | Case & Program | 6 | 85 | 230 | fix: handle single and multiple transaction t1782211473146-st1782211544572
BE | b5702e57 | Karthick | 2026-06-23 18:06 | Case & Program | 15 | 35922 | 0 | feat: include program service into beneficiary service t1782211473146-st1782217671316
FE | 9e867d16 | Karthick | 2026-06-23 18:24 | Case & Program | 6 | 348 | 7 | feat: restrict fund allocation in program service log t1782211473146-st1782211819259
BE | 344e4098 | Karthick | 2026-06-23 20:49 | Case & Program | 7 | 1019 | 1 | feat: add program dashboard widgets funtions t1782219360013-st1782227900708
FE | b543e5a2 | Karthick | 2026-06-23 20:50 | Case & Program | 10 | 1140 | 12 | feat: implement program dashboard t1782219360013-st1782227918821
FE | 02d414c4 | Shyam Prakash J | 2026-06-23 21:36 | Campaigns / Crowdfund / P2P | 4 | 53 | 33 | fix(crowdfunding): fix quick-edit save, date format, double toast, archive modal
FE | cfee9c51 | Shyam Prakash J | 2026-06-24 09:12 | Campaigns / Crowdfund / P2P | 4 | 96 | 59 | fix(crowdfunding): replace raw ID inputs with dropdowns, dynamic currency, dialog alignment
FE | 3aa9bbf8 | Shyam Prakash J | 2026-06-24 10:26 | Campaigns / Crowdfund / P2P | 4 | 176 | 51 | fix(crowdfunding): replace hardcoded currency with searchable API-backed select
BE | 098b923e | Karthick | 2026-06-24 12:04 | Case & Program | 4 | 183 | 79 | fix: refactor case dashboard widget pf functions t1782219360013-st1782281846028
FE | 91c5429d | Karthick | 2026-06-24 12:05 | Case & Program | 9 | 373 | 138 | fix: refactor case dashboard widget t1782219360013-st1782281941802-st1782281963069
BE | 7ccbde55 | Shyam Prakash J | 2026-06-24 12:34 | Campaigns / Crowdfund / P2P | 1 | 51 | 0 | seed(crowdfunding): add CROWDFUNDCATEGORY MasterDataType and 6 category rows (STEP 6)
BE | 6b5915bd | Karthick | 2026-06-24 12:57 | Case & Program | 7 | 367 | 295 | fix: data rendering issue in case dashboard widgets functions t1782284999232-st1782285947539
FE | 5ac0ca3c | Karthick | 2026-06-24 12:57 | Case & Program | 4 | 20 | 18 | fix: data rendering issue in case dashboard widgets functions t1782284999232-st1782285947539
FE | cf49a69e | Shyam Prakash J | 2026-06-24 13:51 | Campaigns / Crowdfund / P2P | 3 | 57 | 17 | fix(crowdfunding): wire CampaignCategory to CROWDFUNDCATEGORY master data API and fix Radix Select f
BE | eb7268e8 | Karthick | 2026-06-24 14:37 | System / Access / Config | 7 | 716 | 2114 | feat: generate mock data script t1782284999232
FE | 2995fac5 | Karthick | 2026-06-24 14:38 | Case & Program | 4 | 96 | 41 | feat: render completed and ongoing program t1782284999232
FE | f3c012b5 | Karthick | 2026-06-24 16:03 | Case & Program | 4 | 61 | 28 | fix: disable beneficiary and case form fields
BE | c39e99d9 | Karthick | 2026-06-24 16:04 | Case & Program | 3 | 20 | 14 | fix: not valid data rendered in program dashboard widgets
FE | 058c9783 | Karthick | 2026-06-24 17:28 | Case & Program | 7 | 1458 | 517 | fix: improve program form chils section ui and ux t1782301155308-st1782301202080
BE | dd4b837d | Karthick | 2026-06-24 19:12 | Case & Program | 3 | 467 | 0 | fix: create url based document verification endpoint t1782301701265-st1782308090326
FE | 81df77f6 | Karthick | 2026-06-24 19:13 | Case & Program | 8 | 669 | 85 | fix: create url based document verification endpoint t1782301701265-st1782308090326
FE | d9217fa4 | Shyam Prakash J | 2026-06-24 19:27 | Campaigns / Crowdfund / P2P | 1 | 194 | 138 | fix(crowdfundingpage): rewrite quick-create modal with API-backed dropdowns
FE | 63a87249 | Karthick | 2026-06-25 09:53 | Case & Program | 3 | 105 | 41 | fix: build and fix type issues t1779965918662
FE | bf178812 | Shyam Prakash J | 2026-06-25 11:54 | Campaigns / Crowdfund / P2P | 1 | 16 | 3 | fix(matching-gift): strip response-only fields from UpdateMatchingCompany payload and silence abort
FE | 0139fb56 | Karthick | 2026-06-25 13:19 | Case & Program | 8 | 0 | 17 | fix: remove unused columns in case management t1782373338787-st1782373404816
BE | 980549fa | Karthick | 2026-06-25 13:25 | Case & Program | 17 | 35706 | 33 | fix: remove unused columns in case management t1782373338787-st1782373404816
BE | 5b0f32dc | Shyam Prakash J | 2026-06-25 14:13 | Donations | 3 | 5 | 4 | fix(matching-gift): fix empty-grid error response and status badge seed
FE | e3a9dffd | Shyam Prakash J | 2026-06-25 14:14 | Campaigns / Crowdfund / P2P | 2 | 20 | 7 | fix(matching-gift): matching tracker tab bug fixes
BE | 74ef1205 | Karthick | 2026-06-25 17:20 | Case & Program | 17 | 36027 | 2 | feat: include sponsor contact and fund allocaion status into program and program fund tracking t1782
FE | 1b9340c9 | Karthick | 2026-06-25 17:50 | Case & Program | 9 | 336 | 18 | feat: track sponsor contact in funding modal t1782379747085-st1782379777424
BE | 4b142a2c | Karthick | 2026-06-25 18:08 | Case & Program | 11 | 35697 | 58 | feat: remove sponsorship field in program entity and their mutations t1782301701265-st1782390038122
FE | 9eb642a0 | Karthick | 2026-06-25 18:08 | Case & Program | 7 | 3 | 67 | feat: remove sponsorship field in program form t1782301701265-st1782390038122
FE | 3fc562d8 | Karthick | 2026-06-25 18:59 | Case & Program | 1 | 194 | 118 | fix: ui improvement for funding modal
FE | 89919fbb | Karthick | 2026-06-26 11:52 | Case & Program | 3 | 238 | 79 | fix: move program funding allocation from program to fund allocation t1782383924968-st1782451736129
BE | 2539314d | Karthick | 2026-06-26 12:58 | Case & Program | 16 | 36885 | 877 | fix: move fun source approval and status to program funding t1782383924968-st1782451736129
FE | f7b3624d | Karthick | 2026-06-26 12:59 | Case & Program | 5 | 278 | 141 | fix: implement fund source approval and status to fund allocation t1782383924968-st1782451736129
FE | 07a9f146 | Karthick | 2026-06-26 13:46 | Case & Program | 4 | 294 | 80 | fix: update demo js functions
BE | 2b31c25c | Karthick | 2026-06-29 10:45 | System / Access / Config | 2 | 565 | 430 | feat: update menu orders
BE | d229b478 | Karthick | 2026-06-29 12:12 | System / Access / Config | 1 | 22 | 18 | fix: update menus based on funding sources
FE | 3043137e | Karthick | 2026-06-29 13:12 | Campaigns / Crowdfund / P2P | 1 | 15 | 16 | fix: build and fix type issue
FE | a66ddc02 | Karthick | 2026-06-29 15:07 | Campaigns / Crowdfund / P2P | 27 | 0 | 0 | feat: move crowdfunding from setting to crm t1782724665732-st1782724697811
FE | 9b643408 | Karthick | 2026-06-29 15:07 | Campaigns / Crowdfund / P2P | 12 | 19 | 18 | feat: move crowdfunding from setting to crm t1782724665732-st1782724697811
FE | 9068f5d5 | Karthick | 2026-06-29 15:13 | Campaigns / Crowdfund / P2P | 28 | 0 | 0 | feat: move p2pcampaign page from setting to crm t1779433907393-st1782724741056
FE | 617dc7f6 | Karthick | 2026-06-29 15:13 | Campaigns / Crowdfund / P2P | 17 | 26 | 25 | feat: move p2pcampaign page from setting to crm t1779433907393-st1782724741056
FE | 4cfda07e | Karthick | 2026-06-29 15:51 | Campaigns / Crowdfund / P2P | 4 | 0 | 152 | fix: remove crowd funding page
FE | 7bb1d3e2 | Karthick | 2026-06-29 15:52 | Campaigns / Crowdfund / P2P | 7 | 39 | 28 | fix: remove crowd funding page
FE | 9f8b42be | Karthick | 2026-06-29 16:40 | Campaigns / Crowdfund / P2P | 4 | 0 | 964 | fix: combine crowdfunding and page into single screen t1782724665732-st1782731335745
FE | ae22179c | Karthick | 2026-06-29 16:48 | Campaigns / Crowdfund / P2P | 9 | 917 | 272 | fix: combine crowdfunding and page into single screen t1782724665732-st1782731335745
FE | ee2f2aff | Karthick | 2026-06-29 17:01 | Campaigns / Crowdfund / P2P | 6 | 534 | 763 | fix: replicate ui and ux from event screen ui into crowdfunding st1782732617082
FE | 5a5cb30c | Karthick | 2026-06-29 17:13 | Campaigns / Crowdfund / P2P | 13 | 456 | 2174 | fix: combine p2p campaign and campaign page as single screen t1779433907393-st1782731511953
BE | 2d7ad1d2 | Karthick | 2026-06-29 18:07 | Campaigns / Crowdfund / P2P | 2 | 72 | 8 | fix: update p2p campaign scripts for combining screens
BE | fc2d534d | Karthick | 2026-06-29 18:08 | Donations | 1 | 127 | 0 | feat: add pg scripts for combining donation purpose and their relations
FE | c07f9475 | Karthick | 2026-06-29 18:09 | Donations | 6 | 0 | 72 | fix: remove donation purpose and their relation routing pages t1782734720607-st1782734849833
FE | 94333480 | Karthick | 2026-06-29 18:09 | Donations | 8 | 188 | 6 | fix: convert donation purpose and their parent screens into single screen t1782734720607-st178273484
FE | ef11d54f | Karthick | 2026-06-29 18:10 | Campaigns / Crowdfund / P2P | 12 | 1013 | 605 | fix: replicate event screen ui into p2p campaign t1779433907393-st1782731511953
FE | ed7b12cb | Karthick | 2026-06-30 11:51 | Campaigns / Crowdfund / P2P | 13 | 575 | 290 | fix: convert all the configuration tab as single tab in crowdfunding setupt2782724665732-st178279903
BE | 8a9cb98f | Karthick | 2026-06-30 11:52 | Campaigns / Crowdfund / P2P | 12 | 35929 | 7 | feat: include donation form field json and communication templates configuration t1782724665732-st17
FE | 0b793e69 | Karthick | 2026-06-30 12:41 | Campaigns / Crowdfund / P2P | 15 | 1192 | 861 | feat: include page tempalate t1782724665732
BE | 9a3fdf9a | Karthick | 2026-06-30 13:02 | Campaigns / Crowdfund / P2P | 10 | 35788 | 0 | feat: include page tempalate to crowdfunding t1782724665732
FE | ed6df88c | Karthick | 2026-06-30 13:22 | Campaigns / Crowdfund / P2P | 12 | 733 | 171 | feat: include donation purpose and page template property to p2pcampaign t1779433907393-st1782805090
BE | 70db97ad | Karthick | 2026-06-30 13:26 | Campaigns / Crowdfund / P2P | 12 | 35989 | 30 | feat: include donation purpose and page template property to p2pcampaign t1779433907393-st1782805009
FE | 7fbd5b4c | Karthick | 2026-06-30 17:02 | Campaigns / Crowdfund / P2P | 12 | 450 | 240 | fix: test crowdfund configuration t1782800503275-st1782809539800
BE | 5d8aa0b8 | Karthick | 2026-06-30 17:35 | Campaigns / Crowdfund / P2P | 3 | 255 | 9 | fix: test crowdfund publish t1782800503275-st1782809539800
FE | 8b70781c | Karthick | 2026-06-30 17:35 | Campaigns / Crowdfund / P2P | 10 | 350 | 107 | fix: test crowdfund publish t1782800503275-st1782809539800
FE | 5bd5a93f | Karthick | 2026-07-01 12:44 | Campaigns / Crowdfund / P2P | 22 | 785 | 162 | fix: test p2p publish flow t1782804927737-st1782822209645
BE | ecf6d6d3 | Karthick | 2026-07-01 12:44 | Campaigns / Crowdfund / P2P | 10 | 263 | 54 | fix: make required fields validations and development handling for public page t1782888408003-st1782
BE | e6e0a618 | Karthick | 2026-07-01 16:30 | Donations | 15 | 37773 | 100 | feat: implement payment gateway intiate and confirm endpoint t1782888408003-st1782889700000
FE | 6388df97 | Karthick | 2026-07-01 16:30 | Campaigns / Crowdfund / P2P | 17 | 1872 | 571 | feat: integrate payment gateway to p2p campaign public page t1782888408003-st1782889700000
FE | 463b2fe8 | Karthick | 2026-07-01 16:48 | Campaigns / Crowdfund / P2P | 12 | 361 | 115 | feat: improve p2p fundraiser grid and grid actions t1782891138729
BE | f9d4b3cc | Karthick | 2026-07-01 16:54 | Campaigns / Crowdfund / P2P | 4 | 115 | 9 | fix: implement p2p fundraiser mutations t1782891138729
FE | 65bab26b | Karthick | 2026-07-01 17:11 | Campaigns / Crowdfund / P2P | 2 | 11 | 47 | fix: include currency in p2p fundraiser widgets
BE | 872f09b1 | Karthick | 2026-07-01 17:39 | Campaigns / Crowdfund / P2P | 4 | 1667 | 216 | feat: implement initiate and confirm payment endpoint for crowdfunding t1781073942897-st178289377515
FE | 5cac7a5a | Karthick | 2026-07-01 17:39 | Campaigns / Crowdfund / P2P | 7 | 612 | 137 | feat: integrate payment gateway to crowdfunding t1781073942897-st1782893775156
FE | 075bee4a | Karthick | 2026-07-01 18:11 | Campaigns / Crowdfund / P2P | 9 | 1093 | 184 | feat: implement fundraiser configuration page t1782891138729-st1782908305422
BE | 276bd319 | Karthick | 2026-07-01 18:11 | Campaigns / Crowdfund / P2P | 5 | 526 | 0 | feat: implement fundraiser add member mutations and queries t1782891138729-st1782908305422
FE | def140ac | Karthick | 2026-07-02 11:51 | Campaigns / Crowdfund / P2P | 7 | 346 | 205 | feat: implement p2p fundraiser invite funationality
BE | 1217537d | Karthick | 2026-07-02 13:47 | Campaigns / Crowdfund / P2P | 5 | 35932 | 0 | feat: include invite template and audience filter to p2p campaign t1782972935734-st1782977737814
BE | cc6d0624 | Karthick | 2026-07-02 14:09 | Campaigns / Crowdfund / P2P | 7 | 644 | 56 | feat: implement invite fundraiser service t1782972935734-st1782974401355
FE | effc3b88 | Karthick | 2026-07-02 14:41 | Campaigns / Crowdfund / P2P | 2 | 6 | 4 | feat: implement fundraiser page routing path t1782983343268-st1782983353264
BE | cf06c271 | Karthick | 2026-07-02 14:42 | Campaigns / Crowdfund / P2P | 2 | 50 | 14 | fix: handle localhost and hostname based fundraiser page details retrival t1782983343268-st178298335
FE | 8626e0ff | Karthick | 2026-07-02 15:00 | Campaigns / Crowdfund / P2P | 8 | 46 | 17 | feat: integrate payment gateway to p2pfundraiser public page t1782983343268-st1782983713198
FE | 15c98c51 | Karthick | 2026-07-02 15:45 | Campaigns / Crowdfund / P2P | 2 | 33 | 2 | feat: fundraiser page ui improvement
BE | 2dd07718 | Karthick | 2026-07-02 16:20 | Campaigns / Crowdfund / P2P | 3 | 23 | 0 | fix: include invitetemplate and audience filter to p2pcampaign endpoints t17829716260614-st178297773
FE | 75f47cf1 | Karthick | 2026-07-02 16:21 | Campaigns / Crowdfund / P2P | 3 | 88 | 2 | fix: include invitetemplate and audience filter to p2pcampaign form t17829716260614-st1782977737814
FE | 5d844573 | Karthick | 2026-07-02 17:17 | Campaigns / Crowdfund / P2P | 18 | 801 | 7 | feat: Include beneficiary json to crowdfund form and improve crowdfund page ui t1782893743043-st1782
BE | bcf3008b | Karthick | 2026-07-02 17:27 | Campaigns / Crowdfund / P2P | 10 | 35844 | 9 | feat: Include beneficiary json to crowdfund entity and their mutations t1782893743043-st178299216658
BE | b6de2daa | Karthick | 2026-07-02 18:29 | Campaigns / Crowdfund / P2P | 19 | 36567 | 45 | feat: implement bulk email send service for p2pcampaign t1782977955109-st1782991404737
FE | 8e7b4c53 | Karthick | 2026-07-02 18:29 | Campaigns / Crowdfund / P2P | 8 | 957 | 26 | feat: integrate bulk email send service endpoint t1782977955109-st1782991763851
FE | ec5337f3 | Karthick | 2026-07-03 10:46 | Campaigns / Crowdfund / P2P | 1 | 5 | 0 | fix: property name missing in p2pcampaign
BE | d3bd2426 | Karthick | 2026-07-03 10:46 | Communication | 1 | 4 | 2 | fix: change p2pcampaign job type
FE | e16b52b6 | Karthick | 2026-07-03 12:01 | Campaigns / Crowdfund / P2P | 14 | 1534 | 19 | feat: integrate email communication service to crowdfund t1783055961413-st1783056063027
BE | 26c64496 | Karthick | 2026-07-03 12:04 | Campaigns / Crowdfund / P2P | 5 | 35935 | 0 | feat: include invitation fields and audience filter fields to crowd funding t1783055961413-st1783056
BE | d489b004 | Karthick | 2026-07-03 12:06 | Campaigns / Crowdfund / P2P | 17 | 1082 | 1 | feat: implement email communication service for crowdfund t1783055961413-st1783056007878
BE | 21f829f6 | Karthick | 2026-07-03 12:40 | Campaigns / Crowdfund / P2P | 1 | 7 | 4 | feat: implement crowdfunding unpublish endpoint
FE | 8c83b4dc | Karthick | 2026-07-03 12:42 | Campaigns / Crowdfund / P2P | 1 | 2 | 1 | feat: implement crowdfunding unpublish feature
BE | 1b684f8d | Karthick | 2026-07-03 13:06 | Campaigns / Crowdfund / P2P | 2 | 27 | 17 | feat: implement test email mode for p2pcampaign t1782977955109-st1782991763851
FE | f63df8ef | Karthick | 2026-07-03 13:07 | Communication | 2 | 85 | 15 | feat: implement test email mode feature t1782977955109-st1782991763851
BE | 41110d20 | Karthick | 2026-07-03 13:36 | Campaigns / Crowdfund / P2P | 2 | 27 | 18 | feat: implement test email mode endpoint for crowdfund t1783055961413-st1783056063027
FE | 52702a5c | Karthick | 2026-07-03 13:36 | Communication | 2 | 89 | 18 | feat: implement test email mode feature for crowdfund t1783055961413-st1783056063027
BE | 4e20f5e4 | Karthick | 2026-07-03 14:23 | Communication | 12 | 247 | 20 | feat: implement uniform job code generator extension t182977955109-st1783063034041
BE | ab942f30 | Karthick | 2026-07-03 17:16 | System / Access / Config | 33 | 1295 | 812 | feat: implement entity code generation service t1783073121616
FE | 96233acf | Karthick | 2026-07-03 17:21 | Communication | 9 | 42 | 76 | fix: remove code auto generation in whatsapp and ambassador
BE | 834ca314 | Karthick | 2026-07-06 14:19 | Case & Program | 5 | 35896 | 0 | feat: include funding sourceid into beneficiary service log t1783326992051-st1783327027114
BE | 8a7c9d3d | Karthick | 2026-07-06 14:22 | Case & Program | 12 | 343 | 12 | feat: refactor grant managment tracking entity and their mutations t1779433985797-st1783325648144
FE | 87a84c7f | Karthick | 2026-07-06 14:27 | Case & Program | 11 | 458 | 11 | feat: refactor grant managment screen t1779433985797-st1783325697747
BE | cd4f29b5 | Karthick | 2026-07-06 17:12 | Grants | 11 | 175 | 5 | fix: grant flow mutation update t1783325730653-st1783338057887
FE | abbf8208 | Karthick | 2026-07-06 17:13 | Grants | 7 | 422 | 40 | fix: grant flow crud operations t1783325730653-st1783326767883
BE | 6942badc | Karthick | 2026-07-06 18:14 | Grants | 9 | 36016 | 10 | feat: handle grant staging in grant processing mutations t1783338297262-st1783339641407
FE | 1ce155f6 | Karthick | 2026-07-06 18:16 | Grants | 7 | 210 | 55 | feat: handle grant staging in grant processing t1783338297262-st1783340881930
BE | 01dc13f9 | Karthick | 2026-07-07 10:43 | Grants | 7 | 36416 | 0 | feat: implement organization bank and grantfundreport entity and their mutations t1783399840530-st17
BE | f0861d33 | Karthick | 2026-07-07 11:30 | Grants | 28 | 1198 | 42 | feat: implement organization bank and grantfundreport entity and their mutations t1783399840530-st17
FE | 944786d8 | Karthick | 2026-07-07 11:36 | Grants | 23 | 1818 | 93 | feat: integrate account and fund history into grant t1783399840530-st1783404296878
FE | 478200a4 | Karthick | 2026-07-07 13:07 | Grants | 12 | 833 | 18 | feat: integrate communication service for grant t1783340818276-st1783404543278
BE | 5fa9584e | Karthick | 2026-07-07 14:33 | Grants | 32 | 38123 | 32 | feat: implement grant communication and service for grant t1783340818276-st1783405470298
BE | 6a03df47 | Karthick | 2026-07-07 17:53 | Grants | 12 | 378 | 6 | feat: restrict and test full flow of grant apllication staging t1783338297262-st1783339641407
FE | dc08acf6 | Karthick | 2026-07-07 17:57 | Grants | 10 | 600 | 168 | feat: restrict and test full flow of grant apllication staging t1783338297262-st1783339641407
BE | 30df66a2 | Karthick | 2026-07-07 19:06 | Donations | 4 | 444 | 18 | feat: create get donation purpose details query t1783429483107-st1783429522169
FE | 47f1e6f6 | Karthick | 2026-07-07 19:13 | Donations | 8 | 711 | 4 | feat: implement donation purpose details view page t1783429483107-st1783429540141
BE | 70601887 | Karthick | 2026-07-08 12:50 | Case & Program | 5 | 36240 | 0 | feat: include allocateamount field to program fund source entity t1783429483107-st1783493678730
BE | c9ba69f3 | Karthick | 2026-07-08 14:37 | Grants | 12 | 485 | 9 | feat: implement case management and grant integration relevant endpoint t1783487916193-st17834937376
FE | 6fba5dbf | Karthick | 2026-07-08 14:38 | Grants | 13 | 796 | 31 | feat: implement program fund allocation flow with grant t1783487916193-st1783493737612
BE | 8dbc67c8 | Karthick | 2026-07-08 16:39 | Grants | 7 | 36494 | 0 | feat: include payment mode to payment fund transfer and grant expance t1783501783655-st1783506996358
BE | 17eb386f | Karthick | 2026-07-08 17:49 | Grants | 11 | 326 | 22 | feat: implement mutation and queries for payment log into program fund allocation and grant expance
FE | 5607583e | Karthick | 2026-07-08 17:49 | Grants | 11 | 889 | 118 | feat: implement payment tracking into program fund allocation and grant expance tracking t1783501783
BE | ce79ff3b | Karthick | 2026-07-08 21:40 | Case & Program | 13 | 36564 | 2 | feat: include payment log fields into beneficiary service log entity and respective mutations and qu
FE | 2e48b5cc | Karthick | 2026-07-08 21:54 | Case & Program | 3 | 367 | 0 | feat: include payment log into beneficiary service log t1783515596457-st1783515679324
BE | 6a46e1d8 | Karthick | 2026-07-09 12:16 | Grants | 4 | 101 | 1 | fix: add proper fund calculation to grant summary widgets t1783513248585-st1783579435623
FE | a0e85336 | Karthick | 2026-07-09 12:18 | Grants | 7 | 255 | 60 | fix: render grant document dynamically t1783513248585-st1783579470011
FE | b3eb8d3c | Karthick | 2026-07-09 15:06 | Grants | 5 | 246 | 81 | feat: implement pogram period based fund allocation
BE | 82920b95 | Karthick | 2026-07-09 15:06 | Grants | 4 | 71 | 5 | feat: handle pogram period based fund allocation in fund allocation endpoint
FE | 6e97aa5c | Karthick | 2026-07-09 15:49 | Campaigns / Crowdfund / P2P | 1 | 8 | 1 | fix: fix type issues
FE | be238c83 | Karthick | 2026-07-09 21:36 | Donations | 12 | 1551 | 83 | feat: implement donation fund allocation screen T1783593926215-st1783594051568
BE | 8d3cdcc4 | Karthick | 2026-07-09 21:39 | Case & Program | 20 | 37254 | 13 | feat: implement donation fund allocation relevant endpoint and queries T1783593926215-st178359402345
FE | e14911be | Karthick | 2026-07-10 07:27 | Communication | 5 | 340 | 112 | feat: impleemnt inapp notitifcation t178648452405-st1783648564284
BE | 341b4ea9 | Karthick | 2026-07-10 09:03 | Communication | 31 | 38129 | 94 | feat: implement notificationjob entity and their mutations t178648452405-st1783648531988
BE | 11104453 | Karthick | 2026-07-10 09:39 | Donations | 5 | 206 | 37 | feat: implement funding details get all query for donation purpose t1783656215918-st1783656307717
FE | 59135933 | Karthick | 2026-07-10 09:39 | Donations | 6 | 581 | 110 | feat: implement funding details tabs t1783656215918-st1783656307717
FE | 8fc38592 | Karthick | 2026-07-10 13:00 | Grants | 17 | 956 | 410 | fix: minor bug fix in the grant donationpurpose and corwdfunding t1783593639106-st1783668524240
BE | f557be65 | Karthick | 2026-07-10 13:01 | Campaigns / Crowdfund / P2P | 4 | 69 | 11 | fix: minor bug fix in the grant donationpurpose and corwdfunding endpoints t1783593639106-st17836685
BE | 53d7d365 | Karthick | 2026-07-10 15:03 | Finance / Payment / Receipt | 2 | 119 | 0 | fix(online-donation-page): env-gate test webhook + donation MasterData seed - t1783675815197
FE | eb95349d | Karthick | 2026-07-10 15:22 | Donations | 1 | 16 | 4 | fix(online-donation-page): prevent Published-page slug link-rot on title edit t1783675815197
BE | 2dcba20d | Karthick | 2026-07-10 15:30 | Donations | 1 | 38 | 0 | fix(online-donation-page): audit all one-time gateway branches t1783675815197-st1783677587874
BE | 33b6f56a | Karthick | 2026-07-10 15:48 | Campaigns / Crowdfund / P2P | 14 | 446 | 238 | fix(crowdfunding): money-truth goal-enforcement anti-abuse and lifecycle-guard audit fixes t17836780
FE | c564aa6f | Karthick | 2026-07-10 15:51 | Campaigns / Crowdfund / P2P | 1 | 1 | 1 | fix(crowdfunding): transmit honeypot field on public donate form t1783648452405
BE | ca242be9 | Karthick | 2026-07-10 16:58 | Grants | 22 | 36925 | 48 | fix(grant): stabilize financial engine — double-spend guard utc dates fx normalization t178368261696
FE | 7e1e41a5 | Karthick | 2026-07-10 16:59 | Grants | 11 | 460 | 77 | fix(grant): wire dead lifecycle actions fx warning chips dto and contract fixes t1783682616960
BE | 5f0bc240 | Karthick | 2026-07-10 17:20 | Campaigns / Crowdfund / P2P | 2 | 5 | 1 | fix(crowdfunding): expose RobotsIndexable on public dto so live pages are indexable t1783678077422
FE | 5e0cd351 | Karthick | 2026-07-10 17:20 | Campaigns / Crowdfund / P2P | 3 | 39 | 3 | fix(crowdfunding): expose RobotsIndexable on public dto so live pages are indexable t1783678077422
BE | ef2edaaf | Karthick | 2026-07-10 18:02 | Finance / Payment / Receipt | 4 | 12 | 5 | fix: online donation page payment webhook condition fix
BE | edbad304 | Karthick | 2026-07-10 18:05 | Campaigns / Crowdfund / P2P | 2 | 50 | 23 | fix(crowdfunding): resolve public stats tenant by hostname to match page query t1783678077422
FE | d15a75db | Karthick | 2026-07-10 18:06 | Campaigns / Crowdfund / P2P | 4 | 57 | 9 | fix(crowdfunding): resolve public stats tenant by hostname to match page query t1783678077422
BE | f5875192 | Karthick | 2026-07-10 19:10 | Grants | 7 | 857 | 0 | feat(grant): add grant report generation queries and mutations t1783682616960-st1783690630560
FE | ea129a11 | Karthick | 2026-07-10 19:11 | Grants | 19 | 1812 | 556 | feat(grant): add grant report generation feature t1783682616960-st1783690630560
FE | 17ce188b | Karthick | 2026-07-13 11:09 | Other / Shared | 3 | 139 | 13 | fix: surface payu payment failures to the donor instead of dead-ending
FE | b1f3991d | Karthick | 2026-07-13 11:21 | Campaigns / Crowdfund / P2P | 4 | 133 | 36 | fix(crowdfunding): remove dead cover-fees toggle and wire crm lifecycle actions/refetch
FE | 15d6892f | Karthick | 2026-07-13 13:16 | Grants | 3 | 208 | 15 | feat(grant): currency thousand-separator formatting on blur
FE | bc04264f | Karthick | 2026-07-13 13:36 | Grants | 2 | 56 | 13 | fix(grant): tenant-aware currency input grouping to match footer total
BE | 72fa39fb | Karthick | 2026-07-13 13:55 | Campaigns / Crowdfund / P2P | 3 | 15 | 0 | fix(donation): persist razorpay subscription id at Initiate to prevent orphaned recurring subscripti
BE | 119167da | Karthick | 2026-07-13 14:11 | Donations | 4 | 385 | 0 | fix(online-donation): mark pending staging row failed on donor cancel/gateway failure
FE | 92d6f9a9 | Karthick | 2026-07-13 14:11 | Donations | 3 | 75 | 1 | fix(online-donation): report cancel/failure outcome to the staging row
FE | 9d76db81 | Karthick | 2026-07-13 14:33 | Other / Shared | 4 | 71 | 9 | fix(onlinedonationpage): add frame-ancestors csp clickjacking boundary
BE | dd3e3a69 | Karthick | 2026-07-13 14:40 | Campaigns / Crowdfund / P2P | 8 | 63 | 22 | fix(crowdfund): roll up campaign totals in base currency with direct-pair fx
BE | e7ca45b2 | Karthick | 2026-07-13 15:56 | Finance / Payment / Receipt | 7 | 0 | 447 | chore(donation): remove dead legacy Braintree credential path
BE | 8402650a | Karthick | 2026-07-13 16:19 | Grants | 8 | 85 | 0 | fix(grant): refresh cached Grant rollup columns on every report state change
BE | 9084db56 | Karthick | 2026-07-13 16:44 | Campaigns / Crowdfund / P2P | 1 | 11 | 0 | fix(crowdfund): public page resilience + story XSS hardening
FE | cf00bf95 | Karthick | 2026-07-13 16:44 | Campaigns / Crowdfund / P2P | 3 | 128 | 28 | fix(crowdfund): public page resilience + story XSS hardening
FE | efa7c1f6 | Karthick | 2026-07-13 16:53 | Donations | 10 | 253 | 2 | fix(onlinedonationpage): add seo og robots editor card + honor robotsIndexable
BE | c7d6fce7 | Karthick | 2026-07-13 17:07 | Campaigns / Crowdfund / P2P | 1 | 57 | 6 | fix(crowdfund): Goal-Met chip filter matches its count and row badge
FE | 8e3f217f | Karthick | 2026-07-13 17:07 | Campaigns / Crowdfund / P2P | 1 | 4 | 3 | fix(crowdfund): goal met chip filter matches its count and row badge
BE | 5beb02c8 | Karthick | 2026-07-13 17:32 | Case & Program | 16 | 534 | 83 | fix(casemanagement): production-readiness audit remediation partial changes
FE | 2e22e8d7 | Karthick | 2026-07-13 17:35 | Case & Program | 4 | 190 | 10 | fix(casemanagement): production-readiness audit remediation
FE | 95666958 | Karthick | 2026-07-14 12:18 | Campaigns / Crowdfund / P2P | 3 | 68 | 20 | fix(crowdfund): filtered-empty list state and thank-you receipt/a11y
BE | 0d7c3871 | Karthick | 2026-07-14 12:19 | Campaigns / Crowdfund / P2P | 8 | 132 | 4 | fix(crowdfund): harden public donation flow lifecycle re-check, donation cap, PII masking, cache inv
BE | e7411596 | Karthick | 2026-07-14 12:26 | Case & Program | 9 | 121 | 31 | fix(casemanagement): production-readiness remediation for beneficiary, program & document flows
FE | 6ad90542 | Karthick | 2026-07-14 12:27 | Case & Program | 8 | 81 | 97 | fix(casemanagement): production-readiness remediation for case and program ui
FE | 7336debe | Karthick | 2026-07-14 13:11 | Grants | 4 | 34 | 16 | feat(grant): rich-text narrative fields on grant install dompurify
BE | 266dddd7 | Karthick | 2026-07-14 13:14 | Campaigns / Crowdfund / P2P | 5 | 19 | 5 | feat: add cache for crowdfund mutations and queries
BE | 59786747 | Karthick | 2026-07-14 14:22 | Donations | 18 | 1664 | 481 | fix(online-donation): auto-promote captured payment to globaldonation
BE | bdeb41c5 | Karthick | 2026-07-14 18:16 | Grants | 3 | 26 | 3 | fix: convert stageid as nullable and handle in fluent validation
BE | 1c0363de | Karthick | 2026-07-14 18:16 | Donations | 1 | 224 | 0 | feat: add cleanup script for donation purpose

## Remaining (Estimation)
PSS 2.0 — REMAINING SCOPE TO PRODUCTION (estimation)
Source: PSS-2.0-DEVELOPMENT-ESTIMATION.xlsx. PM forward estimate by workstream, in THREE bands: Dev/build h = build only; Dev-side test h = the SAME developer's post-build test pass before QA (bulk-data, cross-module, business-flow, UX fix) at 30% of build; QA/UAT h = the later independent QA / user-acceptance pass. Total h = sum of the three. Excludes 15% PM buffer. Excludes 'DevOps & Delivery' (separate infra owner); Azure Front Door retained.
Workstream group | Est. sheet | Items | Dev/build h | Dev-side test h | QA / UAT h | Total h | P1 (critical) h
Platform Services | 4. System, Roles & Platform | 11 | 132 | 39.6 | 48 | 219.6 | 93.8
Config & Roles | 4. System, Roles & Platform | 10 | 112 | 33.6 | 52 | 197.6 | 106.4
Donations | 1. Business Modules | 13 | 99 | 29.7 | 41.5 | 170.2 | 128.2
Architecture & Services | 6. Engineering & Platform Found | 8 | 108 | 32.4 | 27 | 167.4 | 110.6
Predictive | 3. AI Features | 5 | 92 | 27.6 | 28 | 147.6 | 32
Onboarding | 5. Client Onboarding, Comms & L | 6 | 86 | 25.8 | 29 | 140.8 | 88.2
Release Readiness | 4. System, Roles & Platform | 7 | 74 | 22.2 | 28 | 124.2 | 69
Data & Persistence | 6. Engineering & Platform Found | 5 | 78 | 23.4 | 21 | 122.4 | 60.4
Scale & Reliability | 6. Engineering & Platform Found | 6 | 72 | 21.6 | 19 | 112.6 | 78
Finance & Accounting | 4. System, Roles & Platform | 5 | 62 | 18.6 | 22 | 102.6 | 40.2
Quality Engineering | 6. Engineering & Platform Found | 4 | 66 | 19.8 | 15 | 100.8 | 76
Security & Compliance | 4. System, Roles & Platform | 4 | 60 | 18 | 22 | 100 | 100
Assistants | 3. AI Features | 3 | 58 | 17.4 | 17 | 92.4 | 47
Integrations | 4. System, Roles & Platform | 4 | 50 | 15 | 17 | 82 | 0
Volunteer | 2. Volunteer & Membership | 3 | 48 | 14.4 | 17 | 79.4 | 58.8
Communication | 1. Business Modules | 6 | 44.5 | 13.3 | 18.5 | 76.3 | 46.8
Leads | 5. Client Onboarding, Comms & L | 3 | 44 | 13.2 | 15 | 72.2 | 58.8
Frontend Engineering | 6. Engineering & Platform Found | 3 | 44 | 13.2 | 10 | 67.2 | 0
AI Platform | 3. AI Features | 3 | 40 | 12 | 13 | 65 | 51.6
Intelligence | 3. AI Features | 2 | 38 | 11.4 | 13 | 62.4 | 0
Membership | 2. Volunteer & Membership | 3 | 36 | 10.8 | 13 | 59.8 | 23.2
Observability | 6. Engineering & Platform Found | 3 | 32 | 9.6 | 8 | 49.6 | 49.6
Security Engineering | 6. Engineering & Platform Found | 3 | 30 | 9 | 8 | 47 | 47
Reporting | 4. System, Roles & Platform | 3 | 28 | 8.4 | 10 | 46.4 | 0
Engagement | 2. Volunteer & Membership | 2 | 28 | 8.4 | 9 | 45.4 | 0
Events | 1. Business Modules | 4 | 24.5 | 7.3 | 10.5 | 42.4 | 5.2
Grants | 1. Business Modules | 3 | 15.5 | 4.6 | 11.5 | 31.6 | 31.6
Case Management | 1. Business Modules | 3 | 15.5 | 4.6 | 10 | 30.1 | 16.1
Contacts | 1. Business Modules | 4 | 13.5 | 4 | 8.5 | 26.1 | 0
Dashboards | 1. Business Modules | 1 | 14.5 | 4.3 | 5 | 23.9 | 23.9
Client Comms | 5. Client Onboarding, Comms & L | 1 | 12 | 3.6 | 4 | 19.6 | 0
TOTAL REMAINING |  | 141 | 1657 | 497.1 | 570.5 | 2724.6 | 1442.5

## Estimation Detail
PSS 2.0 — REMAINING SCOPE, LINE-ITEM DETAIL
Every work-package behind the remaining estimate, across all 6 workstreams — shown at SOURCE granularity (Dev/build + QA/UAT). The dev-side testing band (+30% of Dev/build) is applied at roll-up, not per line — see reconciliation row and the Summary / Remaining sheets. Source: PSS-2.0-DEVELOPMENT-ESTIMATION.xlsx.
# | Workstream | Group | Work Item | Detail | Cx | Pri | Dev/build h | QA / UAT h | Total h | Days
1 | 1 Business | Contacts | Contact Import | Re-test end-to-end and harden — field mapping, dedupe on import, error-row report, large-file handling. | M | P2 | 5 | 2.5 | 7.5 | 1
2 | 1 Business | Contacts | Family | Re-test relationships, primary contact and merge behaviour. | S | P2 | 2.5 | 2 | 4.5 | 1
3 | 1 Business | Contacts | Duplicate Detection | Re-test match rules, merge and survivorship. | M | P2 | 3 | 2 | 5 | 1
4 | 1 Business | Contacts | Certificate Processing | Re-test generation, print and template binding. | S | P2 | 3 | 2 | 5 | 1
5 | 1 Business | Donations | Multi-currency completion | Finish contact-level currency + every amount surface (grids, tiles, receipts, drawers) still showing raw/base amounts. | L | P1 | 9.5 | 3.5 | 13 | 2
6 | 1 Business | Donations | Currency conversion coverage | Apply direct-pair FX consistently across dashboards, reports and reconciliations. | M | P1 | 7 | 3 | 10 | 1.5
7 | 1 Business | Donations | Currency decimal formatting | Standardise precision, grouping and symbol placement from the currency master. | S | P2 | 3.5 | 2 | 5.5 | 1
8 | 1 Business | Donations | Pledge lifecycle | Complete and verify schedule, partial payments, fulfilment, reminders, ageing and write-off. | L | P1 | 7 | 3 | 10 | 1.5
9 | 1 Business | Donations | Bulk Donation Upload | Complete & re-test template, validation, partial-failure handling and import receipting. | M | P2 | 5 | 2.5 | 7.5 | 1
10 | 1 Business | Donations | Donation / payment reconciliation | Matching, unmatched queue and matching against the real gateway settlement feed. | L | P1 | 9.5 | 3.5 | 13 | 2
11 | 1 Business | Donations | Refund flow | End-to-end approval, gateway reversal, receipt void and ledger reversal. | M | P1 | 6 | 2.5 | 8.5 | 1.5
12 | 1 Business | Donations | Matching-Gift | Complete screen + employer-match workflow (directory, ratio, claim, reconciliation). | M | P2 | 6 | 2.5 | 8.5 | 1.5
13 | 1 Business | Donations | Ambassador module | Full business-flow testing: collection, book master, allocations (allocation → collection → reconciliation). | M | P2 | 3.5 | 5 | 8.5 | 1.5
14 | 1 Business | Donations | Receipt & tax-certificate issuance | First-class flow: per-tenant number series, country tax format (80G), PDF, re-issue/void, annual consolidated receipts. | XL | P1 | 12 | 3.5 | 15.5 | 2.5
15 | 1 Business | Donations | Donation acknowledgement automation | Auto thank-you on receipt, tiered by amount and first-time vs repeat donor. | S | P2 | 3.5 | 2 | 5.5 | 1
16 | 1 Business | Donations | Recurring / subscription engine | Auto-charge schedule, failed-card retry, dunning, expiry/renewal, pause/cancel (distinct from pledges). | XL | P1 | 14.5 | 5 | 19.5 | 3
17 | 1 Business | Donations | Restricted / designated funds | Donor-restricted fund balances, allocation/release and over-spend guard so Grant/Case movements reconcile. | XL | P1 | 12 | 3.5 | 15.5 | 2.5
18 | 1 Business | Grants | Grant full business testing | Application → communication → fund collection → utilisation → reports, end to end. | M | P1 | 3.5 | 6 | 9.5 | 1.5
19 | 1 Business | Grants | Grant creation-flow fix | Enforce full intake (funder, award-letter evidence, budget lines) before advancing; route stage changes through proper approve/activate handlers. | L | P1 | 7 | 3 | 10 | 1.5
20 | 1 Business | Grants | Grant communication wiring | Compose-from-template funder emails + silent internal notifications + grant communication audit tab. | M | P1 | 5 | 2.5 | 7.5 | 1
21 | 1 Business | Case Management | Case full business retest | Program → fund request → allocation → publish → enrolment → case → service delivery. | M | P1 | 3.5 | 5 | 8.5 | 1.5
22 | 1 Business | Case Management | Case approval gating | Gate assistance and fund steps behind the approval process. | M | P1 | 3.5 | 2 | 5.5 | 1
23 | 1 Business | Case Management | Outcome & impact tracking | Beneficiary/case outcome metrics, before/after, funder-reportable. | L | P2 | 8.5 | 3 | 11.5 | 2
24 | 1 Business | Communication | SMS & WhatsApp real service | End-to-end provider account, send, delivery-status webhooks and templates (not just screens). | L | P1 | 12 | 5 | 17 | 3
25 | 1 Business | Communication | In-app notification service | Produce/deliver/read-state/bell UI, raised from key domain events across modules. | L | P1 | 9.5 | 3.5 | 13 | 2
26 | 1 Business | Communication | Prayer Request & reply service | Submission, moderation, reply dispatch and notification. | M | P2 | 5 | 2.5 | 7.5 | 1
27 | 1 Business | Communication | Contextual send actions | Email/SMS/WhatsApp directly from Event and Case screens. | M | P2 | 5 | 2 | 7 | 1
28 | 1 Business | Communication | Social-media communication | Channel account config + post/share/publish for Event, Case, etc. | M | P2 | 7 | 3 | 10 | 1.5
29 | 1 Business | Communication | Preference & unsubscribe centre | Per-channel/category opt-in-out, one-click unsubscribe, DND/DLT compliance. | M | P1 | 6 | 2.5 | 8.5 | 1.5
30 | 1 Business | Dashboards | All-module dashboards | Build missing, finish partial and bind widgets to live data across every module. | XL | P1 | 14.5 | 5 | 19.5 | 3
31 | 1 Business | Events | Events full-flow retest | Setup → registration → ticketing → check-in → analytics. | M | P2 | 3 | 2.5 | 5.5 | 1
32 | 1 Business | Events | Ticketing / registration / check-in | Paid/free tiers, QR check-in, capacity, waitlist. | L | P2 | 12 | 3.5 | 15.5 | 2.5
33 | 1 Business | Events | Event Auction commission | Commission calculation, payouts, settlement and reporting. | L | P2 | 7 | 2.5 | 9.5 | 1.5
34 | 1 Business | Events | Staff creation & role assignment | Re-test invite, role bind and capability take-effect. | S | P1 | 2.5 | 2 | 4.5 | 1
35 | 2 Vol & Mem | Volunteer | Volunteer module completion | Public registration, profiles/roles, service allocations, working-hours monitoring; reconcile built screens vs scope. | L | P1 | 16 | 6 | 22 | 3.5
36 | 2 Vol & Mem | Volunteer | Volunteer portal | Self-service hour tracking, availabilities, detail collection with hour approval. | L | P1 | 20 | 6 | 26 | 4.5
37 | 2 Vol & Mem | Volunteer | Volunteer service integration | Cross-module volunteer picker into Event, P2P Fundraising and Case Management. | M | P2 | 12 | 5 | 17 | 3
38 | 2 Vol & Mem | Membership | Membership module completion | Plan tiers, renewal, benefits; reconcile built screens vs scope. | L | P1 | 14 | 5 | 19 | 3
39 | 2 Vol & Mem | Membership | Membership portal | Self-service join, renew and manage. | L | P2 | 16 | 5 | 21 | 3.5
40 | 2 Vol & Mem | Membership | Renewal reminders & lapse | Wire renewal reminders and lapse handling into the notification service. | S | P2 | 6 | 3 | 9 | 1.5
41 | 2 Vol & Mem | Engagement | Campaign / appeal management | Goal, thermometer, channel attribution, cost, ROI tying donations/events/P2P/crowdfunding to a parent campaign. | L | P2 | 16 | 5 | 21 | 3.5
42 | 2 Vol & Mem | Engagement | Segmentation & saved lists | Dynamic donor segments feeding communication, exports and campaigns. | M | P2 | 12 | 4 | 16 | 2.5
43 | 3 AI | AI Platform | AI service + fallback | Central AI gateway with provider fallback, ret/timeout, per-tenant keys. | L | P1 | 16 | 5 | 21 | 3.5
44 | 3 AI | AI Platform | AI utilisation tracking | Per-tenant usage metering, token/cost logging and quota surfacing. | M | P2 | 8 | 3 | 11 | 2
45 | 3 AI | AI Platform | AI governance | Prompt/PII redaction before send, per-tenant cost caps, output audit log, human-in-the-loop review. | L | P1 | 16 | 5 | 21 | 3.5
46 | 3 AI | Predictive | Engagement-score prediction | Donor/volunteer engagement scoring model + surfacing on records. | L | P2 | 16 | 5 | 21 | 3.5
47 | 3 AI | Predictive | Churn prediction | Lapse/churn-risk scoring with drivers and worklist. | L | P2 | 16 | 5 | 21 | 3.5
48 | 3 AI | Predictive | Donation / revenue forecasting | Goal-pacing and forecast at campaign and org level. | L | P2 | 20 | 6 | 26 | 4.5
49 | 3 AI | Predictive | Next-best-action & ask-amount | Per-donor recommendation (segmentation + propensity). | L | P2 | 20 | 6 | 26 | 4.5
50 | 3 AI | Predictive | Anomaly / fraud detection | Unusual amount, velocity and card-testing detection on donations/refunds. | L | P1 | 20 | 6 | 26 | 4.5
51 | 3 AI | Assistants | AI chatbot — Ask your data | NL query over tenant data with guardrails, tenant scoping and cited results. | XL | P1 | 30 | 8 | 38 | 6.5
52 | 3 AI | Assistants | Generative content assistant | Draft thank-you/campaign/grant-report/email copy from context with tone/length controls. | L | P2 | 16 | 5 | 21 | 3.5
53 | 3 AI | Assistants | Duplicate/merge suggestions | AI-assisted contact dedupe augmenting rule-based detection. | M | P2 | 12 | 4 | 16 | 2.5
54 | 3 AI | Intelligence | Document / receipt OCR | Scan cheque/receipt/ID into structured fields for offline donation and KYC capture. | XL | P2 | 24 | 8 | 32 | 5.5
55 | 3 AI | Intelligence | Sentiment & topic analysis | On inbound communication, prayer requests and feedback. | M | P3 | 14 | 5 | 19 | 3
56 | 4 System | Config & Roles | Role config & screen setup | Test roles, capabilities, menu access, widgets; confirm capability→menu→widget wiring per role. | M | P1 | 6 | 8 | 14 | 2.5
57 | 4 System | Config & Roles | Grid configuration | Revisit grids, fields, layouts, custom fields, filters, columns; confirm per-grid integrity. | M | P1 | 6 | 6 | 12 | 2
58 | 4 System | Config & Roles | Master Data & Type | Complete & re-test; verify type→data relationship and usage. | M | P2 | 8 | 4 | 12 | 2
59 | 4 System | Config & Roles | Payment gateway & account config | Per-company gateway and bank-account configuration screen. | L | P1 | 12 | 5 | 17 | 3
60 | 4 System | Config & Roles | Comms account config | WhatsApp/SMS/Email credentials, sender, test-send. | M | P1 | 10 | 4 | 14 | 2.5
61 | 4 System | Config & Roles | Template approval flow | WhatsApp and SMS template approval workflow. | M | P2 | 8 | 3 | 11 | 2
62 | 4 System | Config & Roles | Dashboard & widgets config | Layout, widget catalog, role binding. | M | P2 | 10 | 4 | 14 | 2.5
63 | 4 System | Config & Roles | Settings hierarchy config | Setting-Group + Organization-Setting + User-Setting inheritance/override precedence. | M | P2 | 8 | 4 | 12 | 2
64 | 4 System | Config & Roles | Automation-workflow config | Condition-based communication/job creation engine. | L | P2 | 20 | 6 | 26 | 4.5
65 | 4 System | Config & Roles | Approver settings & approval process | Config-driven approval chains, wired into every module + central approval inbox. | XL | P1 | 24 | 8 | 32 | 5.5
66 | 4 System | Platform Services | Grids import/toggle cleanup | Remove Import action + show/hide toggle from grids that don't need them. | S | P2 | 4 | 2 | 6 | 1
67 | 4 System | Platform Services | Timezone handling | Store UTC, display org/user timezone across all dates, filters and reports. | L | P1 | 14 | 6 | 20 | 3.5
68 | 4 System | Platform Services | Global audit trail | Who-changed-what-when with before/after, surfaced in UI, retention policy. | L | P1 | 16 | 6 | 22 | 3.5
69 | 4 System | Platform Services | Document/file storage | Secure private blob (upload/download/virus-scan) unblocking grant attachments & KYC. | L | P1 | 16 | 5 | 21 | 3.5
70 | 4 System | Platform Services | Global search | Across contacts, donations, cases, grants, etc. | M | P2 | 12 | 4 | 16 | 2.5
71 | 4 System | Platform Services | Background-job monitoring | Queue health, retries, dead-letter, manual re-run for messaging/imports. | M | P2 | 12 | 4 | 16 | 2.5
72 | 4 System | Platform Services | Tenant branding / white-label | Logo, colours, sender name, custom domain, email footer. | M | P2 | 12 | 4 | 16 | 2.5
73 | 4 System | Platform Services | Module entitlement per tenant | Turn modules on/off, plan-gated features. | M | P2 | 12 | 4 | 16 | 2.5
74 | 4 System | Platform Services | Reusable import framework | Validation, error report, partial-commit, rollback, mapping templates. | M | P2 | 12 | 5 | 17 | 3
75 | 4 System | Platform Services | Health & observability | Health checks, error monitoring/alerting, structured logging, uptime. | M | P1 | 10 | 4 | 14 | 2.5
76 | 4 System | Platform Services | Data-retention & purge engine | Per-entity/per-tenant archival and purge, compliance-driven. | M | P3 | 12 | 4 | 16 | 2.5
77 | 4 System | Security & Compliance | Authentication hardening | MFA/2FA, SSO/OAuth, password policy, lockout, session timeout, concurrent-session control. | L | P1 | 20 | 6 | 26 | 4.5
78 | 4 System | Security & Compliance | Data-privacy / DSAR | GDPR/DPDP export, erasure/anonymise, consent ledger, processing records. | L | P1 | 16 | 5 | 21 | 3.5
79 | 4 System | Security & Compliance | PII field-level protection | Encryption at rest for sensitive fields, UI/log masking, PCI scope at gateway iframe. | M | P1 | 12 | 5 | 17 | 3
80 | 4 System | Security & Compliance | Role/permission security review | Server-side authz on every mutation, tenant-isolation tests, IDOR checks. | M | P1 | 12 | 6 | 18 | 3
81 | 4 System | Finance & Accounting | Tax integration | Tax config, computation at donation/receipt time, tax receipts and reports. | L | P1 | 12 | 5 | 17 | 3
82 | 4 System | Finance & Accounting | Gateway settlement reconciliation | Match payout report to donations, fees, unsettled/disputed states. | M | P1 | 12 | 4 | 16 | 2.5
83 | 4 System | Finance & Accounting | GL / accounting export | Tally/QuickBooks/Xero/CSV with chart-of-accounts and fund-dimension mapping. | L | P2 | 16 | 5 | 21 | 3.5
84 | 4 System | Finance & Accounting | Financial & statutory reports | FCRA/annual return, fund-utilisation, receipts/donation registers. | M | P2 | 12 | 4 | 16 | 2.5
85 | 4 System | Finance & Accounting | Multi-currency settlement & FX g/l | FX gain/loss at the ledger level. | M | P2 | 10 | 4 | 14 | 2.5
86 | 4 System | Reporting | Standard report pack | Per-module reports (donations, donors, grants, cases, events, volunteers). | M | P2 | 14 | 4 | 18 | 3
87 | 4 System | Reporting | Scheduled report delivery | Email report/export on a cadence to staff, funders, board. | M | P3 | 8 | 3 | 11 | 2
88 | 4 System | Reporting | Export governance | Bulk-export permissions, watermarking, export audit. | S | P3 | 6 | 3 | 9 | 1.5
89 | 4 System | Integrations | Public REST/webhook API | Per-tenant API keys; donate button, Zapier-style automation, CRM sync. | L | P2 | 16 | 5 | 21 | 3.5
90 | 4 System | Integrations | Website embed / donate widget | OG-tagged public pages tying into external donation/crowdfund pages. | M | P2 | 10 | 4 | 14 | 2.5
91 | 4 System | Integrations | Calendar / meeting integration | For events and volunteer scheduling. | M | P3 | 8 | 3 | 11 | 2
92 | 4 System | Integrations | Accounting/CRM/marketing connectors | Connector framework + first connectors. | L | P3 | 16 | 5 | 21 | 3.5
93 | 4 System | Release Readiness | Performance & load testing | Grids, bulk imports, report queries, concurrent tenants. | M | P1 | 10 | 4 | 14 | 2.5
94 | 4 System | Release Readiness | Security testing | OWASP Top 10, dependency/CVE scan, pen-test pass. | M | P1 | 10 | 4 | 14 | 2.5
95 | 4 System | Release Readiness | Accessibility & cross-browser | WCAG 2.1 AA + responsive verification. | M | P2 | 10 | 4 | 14 | 2.5
96 | 4 System | Release Readiness | UAT scripts & regression suite | Per business flow + regression pack. | M | P1 | 12 | 6 | 18 | 3
97 | 4 System | Release Readiness | Documentation set | Admin/user guides, API docs, data dictionary, runbooks. | M | P2 | 12 | 3 | 15 | 2.5
98 | 4 System | Release Readiness | Backup / DR drill | Defined and tested RPO/RTO. | M | P1 | 8 | 3 | 11 | 2
99 | 4 System | Release Readiness | Localization / i18n | Multi-language if serving multiple regions. | M | P3 | 12 | 4 | 16 | 2.5
100 | 5 Onboarding | Leads | Leads / prospect tracking | Lead capture, pipeline stages, owner assignment, follow-up tasks, activity log, convert-to-tenant. | XL | P1 | 24 | 8 | 32 | 5.5
101 | 5 Onboarding | Leads | Lead source & attribution | Source tagging and marketing attribution on conversions. | M | P2 | 8 | 3 | 11 | 2
102 | 5 Onboarding | Leads | Trial-to-paid conversion | Trial provisioning, conversion flow and plan assignment. | M | P1 | 12 | 4 | 16 | 2.5
103 | 5 Onboarding | Onboarding | Guided onboarding wizard | Setup checklist: org profile → branding → users/roles → gateway → comms accounts → master data → go-live. | L | P1 | 20 | 6 | 26 | 4.5
104 | 5 Onboarding | Onboarding | Onboarding progress & health | Per-client onboarding progress tracking and health score. | M | P2 | 10 | 4 | 14 | 2.5
105 | 5 Onboarding | Onboarding | Legacy data-migration toolkit | Templates/validators for contacts, historical donations, receipts, pledges; dedupe on import + reconciliation report. | XL | P1 | 24 | 8 | 32 | 5.5
106 | 5 Onboarding | Onboarding | Seed/demo dataset & sandbox | Demo data and sandbox environment for training and trials. | M | P2 | 10 | 3 | 13 | 2
107 | 5 Onboarding | Onboarding | In-app guidance | Contextual help, tooltips, guided tours, help-centre links. | M | P2 | 12 | 4 | 16 | 2.5
108 | 5 Onboarding | Onboarding | Environment & release management | Staging vs prod config, config promotion, per-tenant go-live cutover runbook. | M | P1 | 10 | 4 | 14 | 2.5
109 | 5 Onboarding | Client Comms | Client communication sequences | Welcome, training invites, onboarding status updates, milestone nudges (staff-facing client lifecycle). | M | P2 | 12 | 4 | 16 | 2.5
110 | 6 Engineering | Architecture & Services | Distributed caching (Redis) | Cache-aside for hot reads, invalidation strategy, per-tenant key scoping. | M | P1 | 14 | 3 | 17 | 3
111 | 6 Engineering | Architecture & Services | Message queue / event bus | Async messaging with outbox pattern, idempotency and dead-letter (infra under the job-monitor UI). | L | P1 | 24 | 5 | 29 | 5
112 | 6 Engineering | Architecture & Services | Background job scheduler | Hangfire/Quartz durable scheduler for recurring and deferred jobs. | M | P1 | 12 | 3 | 15 | 2.5
113 | 6 Engineering | Architecture & Services | Real-time infrastructure | SignalR/WebSocket for in-app notifications and live dashboard updates. | L | P2 | 16 | 4 | 20 | 3.5
114 | 6 Engineering | Architecture & Services | Resilience layer | Global exception handling, Polly retry/circuit-breaker, transient-fault handling. | M | P1 | 12 | 3 | 15 | 2.5
115 | 6 Engineering | Architecture & Services | API & GraphQL versioning | Schema governance, deprecation policy, backward compatibility. | M | P2 | 10 | 3 | 13 | 2
116 | 6 Engineering | Architecture & Services | Webhook delivery infra | Outbound webhook dispatch with retry, signing and dead-letter. | M | P2 | 10 | 3 | 13 | 2
117 | 6 Engineering | Architecture & Services | Email deliverability infra | SPF/DKIM/DMARC, bounce/complaint handling, sender reputation. | M | P1 | 10 | 3 | 13 | 2
118 | 6 Engineering | Data & Persistence | Search engine infra | Azure AI Search/Elasticsearch + indexing pipeline behind the global-search feature. | L | P2 | 20 | 5 | 25 | 4
119 | 6 Engineering | Data & Persistence | DB performance tuning | Indexing, query optimization, connection pooling, N+1 elimination. | M | P1 | 16 | 4 | 20 | 3.5
120 | 6 Engineering | Data & Persistence | Reporting read-model / ETL | Read models / materialized views so heavy reports don't hit the OLTP path. | L | P2 | 20 | 5 | 25 | 4
121 | 6 Engineering | Data & Persistence | Migration strategy & tooling | Repeatable EF migration process, seed framework, zero-downtime approach. | M | P1 | 10 | 3 | 13 | 2
122 | 6 Engineering | Data & Persistence | Optimistic concurrency rollout | Row-versioning / concurrency tokens across mutable entities. | M | P1 | 12 | 4 | 16 | 2.5
123 | 6 Engineering | Observability | Centralized structured logging | Serilog + correlation IDs + log aggregation/retention. | M | P1 | 10 | 2 | 12 | 2
124 | 6 Engineering | Observability | Distributed tracing & APM | OpenTelemetry / Application Insights end-to-end request tracing. | M | P1 | 12 | 3 | 15 | 2.5
125 | 6 Engineering | Observability | Metrics, alerting & SLOs | Uptime/error/latency metrics, dashboards and on-call alerting. | M | P1 | 10 | 3 | 13 | 2
126 | 6 Engineering | Quality Engineering | Automated test suites | Unit + integration coverage on critical paths with CI coverage gates. | XL | P1 | 30 | 6 | 36 | 6
127 | 6 Engineering | Quality Engineering | E2E test automation | Playwright automation for critical business flows in CI. | L | P1 | 20 | 5 | 25 | 4
128 | 6 Engineering | Quality Engineering | Test-data factories | Fixtures/builders and seeded test tenants for deterministic tests. | S | P2 | 8 | 2 | 10 | 1.5
129 | 6 Engineering | Quality Engineering | Code-quality gates | Lint, static analysis (SonarQube), PR checks and standards. | S | P2 | 8 | 2 | 10 | 1.5
130 | 6 Engineering | Security Engineering | Pipeline security scanning | SAST/DAST + dependency and secret scanning in CI. | M | P1 | 12 | 3 | 15 | 2.5
131 | 6 Engineering | Security Engineering | Rate limiting / WAF / DDoS | Throttling, WAF rules and DDoS protection at the edge. | M | P1 | 12 | 3 | 15 | 2.5
132 | 6 Engineering | Security Engineering | Security headers / CSP / CORS | Harden HTTP headers, content-security-policy and CORS. | S | P1 | 6 | 2 | 8 | 1.5
133 | 6 Engineering | Frontend Engineering | Design-system consolidation | Shared component library, tokens and pattern reuse across screens. | L | P2 | 20 | 4 | 24 | 4
134 | 6 Engineering | Frontend Engineering | FE performance & robustness | Code-splitting, bundle optimization, error boundaries, lazy loading. | M | P2 | 12 | 3 | 15 | 2.5
135 | 6 Engineering | Frontend Engineering | SSR/SEO & Core Web Vitals | Server rendering + SEO for public pages, performance budget. | M | P2 | 12 | 3 | 15 | 2.5
136 | 6 Engineering | Scale & Reliability | Azure Front Door setup | Global entry point / navigation: routing rules, origin groups, health probes, latency-based routing and regional failover. | L | P1 | 16 | 4 | 20 | 3.5
137 | 6 Engineering | Scale & Reliability | Front Door custom domains & TLS | Per-tenant / white-label custom-domain routing with managed TLS certificates and CNAME automation. | M | P1 | 12 | 3 | 15 | 2.5
138 | 6 Engineering | Scale & Reliability | Front Door WAF & rules engine | Edge WAF policy, DDoS protection and rules-engine navigation (path routing, redirects, header rewrite, edge caching). | M | P1 | 12 | 3 | 15 | 2.5
139 | 6 Engineering | Scale & Reliability | Horizontal scaling & CDN | Stateless services, distributed session store, CDN for static assets behind Front Door. | M | P2 | 12 | 3 | 15 | 2.5
140 | 6 Engineering | Scale & Reliability | Backup automation & PITR | Automated backups, point-in-time restore, geo-redundancy. | M | P1 | 10 | 3 | 13 | 2
141 | 6 Engineering | Scale & Reliability | Load & autoscaling architecture | Load-test-driven autoscaling rules and capacity planning. | M | P2 | 10 | 3 | 13 | 2
141 |  |  | SOURCE SUBTOTAL (build + QA) |  |  |  | 1657 | 570.5 | 2227.5 | 371.2
|  |  | + Dev-side testing band (30% of Dev/build) |  |  |  | 497.1 |  | 497.1 | 82.8
|  |  | GRAND REMAINING (incl. dev-side testing) | [5 empty] | 2724.6 | 454.1

## Team Utilisation
PSS 2.0 — TEAM UTILISATION (completed effort)
Git-derived contribution per member. Utilisation = active days / ~252 available working days across the 12-month span.
Team member | BE commits | FE commits | Total commits | Active days | Completed h (session) | Sanity h (days×8) | % team effort | Utilisation (days/252)
Karthick | 620 | 569 | 1189 | 207 | 737.8 | 1656 | 63.41% | 82.14%
Kavinkumar Thirumalaisamy | 107 | 153 | 260 | 83 | 184.3 | 664 | 15.84% | 32.94%
Saranya C | 111 | 140 | 251 | 91 | 179.9 | 728 | 15.46% | 36.11%
Shyam Prakash J | 20 | 34 | 54 | 12 | 39.7 | 96 | 3.409% | 4.762%
Ganesh | 5 | 30 | 35 | 10 | 14.7 | 80 | 1.265% | 3.968%
Divya S | 1 | 6 | 7 | 5 | 4.8 | 40 | 0.4096% | 1.984%
PW Data Solutions | 1 | 4 | 5 | 2 | 2.3 | 16 | 0.1988% | 0.7937%
TOTAL / TEAM | 865 | 936 | 1801 | 410 | 1163.5 |  | 100%
Note: 'Completed h (session)' is the primary git-derived figure; 'Sanity h' (active-days×8) is an upper bound. Utilisation reflects calendar engagement, not FTE cost.