## Screen Status
Screen # | Module | Screen Name | Type | Priority | Dev Hrs Est | Development Status | Development Done By | DevTest Hrs Est | Dev Testing Status | Dev Tested By | QA Hrs Est | QA Testing Status | QA Tested By
1 | Fundraising | Donation (Global) | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Passed | Karthick | 1.5 | Not Started
2 | Fundraising | Donation Purpose | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Passed | Saranya | 0.75 | Not Started
3 | Fundraising | Donation Category | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Passed | Saranya | 0.75 | Not Started
4 | Fundraising | Donation Group | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Passed | Saranya | 0.75 | Not Started
5 | Fundraising | Bulk Donation | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
6 | Fundraising | Cheque Donation | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Passed | Karthick | 1.5 | Not Started
7 | Fundraising | In-Kind Donation | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Passed | Saranya | 1.5 | Not Started
8 | Fundraising | Recurring Donation | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
9 | Fundraising | Receipt (GlobalReceipt) | FLOW | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
10 | Fundraising | Online Donation Setup | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
11 | Fundraising | Matching Gift | FLOW | High | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
12 | Fundraising | Pledge | FLOW | High | 1 | Completed | Karthick | 1.5 | Pending | Kavin | 1.5 | Not Started
13 | Fundraising | Refund | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
14 | Fundraising | Payment Reconciliation | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Passed | Karthick | 1.5 | Not Started
15 | Fundraising | P2P Campaign | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
16 | Fundraising | Crowdfunding | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
18 | Contacts | Contact | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Passed | Kavin | 1.5 | Not Started
19 | Contacts | Contact Type | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Blocked - Awaiting Fix | Saranya | 0.75 | Not Started
20 | Contacts | Family | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Saranya | 1.5 | Not Started
21 | Contacts | Duplicate Detection | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
22 | Contacts | Tags & Segmentation | MASTER_GRID | High | 0.75 | Completed | Karthick | 1 | Pending | Saranya | 1 | Not Started
23 | Contacts | Contact Import | FLOW | Medium | 0.75 | Completed | Kavin | 1 | Passed | Kavin | 1 | Not Started
24 | Communication | Email Template | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Passed | Saranya | 1 | Not Started
25 | Communication | Email Campaign/SendJob | FLOW | Medium | 1 | Completed | Saranya | 1.5 | Not Started |  | 1.5 | Not Started
26 | Communication | Placeholder Definition | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Pending | Saranya | 0.75 | Not Started
27 | Communication | Saved Filter | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Passed | Saranya | 1 | Not Started
28 | Communication | Company Email Provider | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Pending | Karthick | 1 | Not Started
29 | Communication | SMS Template | FLOW | High | 0.75 | Completed | Karthick | 1 | Pending | Saranya | 1 | Not Started
30 | Communication | SMS Campaign | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Saranya | 1.5 | Not Started
31 | Communication | WhatsApp Template | FLOW | High | 0.75 | Completed | Karthick | 1 | Pending | Karthick | 1 | Not Started
32 | Communication | WhatsApp Campaign | FLOW | Medium | 1 | Completed | Kavin | 1.5 | Not Started | Kavin | 1.5 | Not Started
33 | Communication | WhatsApp Conversations | FLOW | Medium | 1 | Not Started | Not Started | 1.5 | Not Started | Kavin | 1.5 | Not Started
34 | Communication | WhatsApp Setup | Config | High | 0.75 | Completed | Kavin | 1 | Not Started | Kavin | 1 | Not Started
35 | Communication | Notification Center | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Passed | Kavin | 1 | Not Started
36 | Communication | Notification Templates | FLOW | High | 0.75 | Completed | Karthick | 1 | Passed | Kavin | 1 | Not Started
37 | Communication | Automation Workflow | FLOW | Low | 1 | Not Started | Not Started | 1.5 | Not Started |  | 1.5 | Not Started
38 | Communication | Email Analytics | Dashboard | Low | 0.75 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
39 | Organization | Campaign | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Passed | Kavin | 1 | Not Started
40 | Organization | Event | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Passed | Kavin | 1.5 | Not Started
41 | Organization | Branch | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Passed | Kavin | 0.75 | Not Started
42 | Organization | Staff (combined: Staff + User Role) | FLOW | Medium | 1 | In Progress (Partial) | Not Started | 1.5 | Not Started |  | 1.5 | Not Started
43 | Organization | Staff Category | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Pending | Saranya | 0.75 | Not Started
44 | Organization | Organizational Unit | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Passed | Kavin | 1 | Not Started
45 | Organization | Company | FLOW | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
46 | Organization | Event Ticketing | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
47 | Organization | Event Analytics | Dashboard | Low | 0.75 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
48 | Organization | Auction Management | FLOW | Medium | 1 | Completed | Karthick | 1.5 | In Testing | Karthick | 1.5 | Not Started
49 | Case Management | Beneficiary | FLOW | High | 1 | Completed | Karthick | 1.5 | Pending | Saranya | 1.5 | Not Started
50 | Case Management | Case | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
51 | Case Management | Program | MASTER_GRID | High | 0.75 | Completed | Karthick | 1 | Pending | Karthick | 1 | Not Started
52 | Case Management | Case Dashboard | Dashboard | Low | 0.75 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
53 | Volunteer | Volunteer | FLOW | High | 1 | Completed | Karthick | 1.5 | Passed | Kavin | 1.5 | Not Started
54 | Volunteer | Volunteer Schedule | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Passed | Kavin | 1 | Not Started
55 | Volunteer | Hour Tracking | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Passed | Kavin | 1 | Not Started
57 | Volunteer | Volunteer Dashboard | Dashboard | Low | 0.75 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
58 | Membership | Membership Tier | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Pending | Saranya | 0.75 | Not Started
59 | Membership | Member Enrollment | FLOW | High | 1 | Completed | Karthick | 1.5 | Pending | Saranya | 1.5 | Not Started
60 | Membership | Membership Renewal | MASTER_GRID | Medium | 0.75 | Completed | Karthick | 1 | Pending | Saranya | 1 | Not Started
61 | Membership | Member Portal | FLOW | Low | 1 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
62 | Grants | Grant | FLOW | High | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
63 | Grants | Grant Report | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Pending | Karthick | 1.5 | Not Started
64 | Grants | Grant Calendar | Dashboard | Low | 0.75 | In Progress (Partial) | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
65 | Field Collection | Field Collection | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Pending | Kavin | 1 | Not Started
66 | Field Collection | Receipt Book | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Pending | Kavin | 0.75 | Not Started
67 | Field Collection | Ambassador | FLOW | High | 1 | Completed | Karthick | 1.5 | Pending | Kavin | 1.5 | Not Started
69 | Field Collection | Ambassador Dashboard | Dashboard | Low | 0.75 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
70 | Administration | Role Management (combined: Role + Capability + Role-Capability Matrix) | Config | Medium | 1 | In Progress (Partial) | Not Started | 1.5 | Not Started |  | 1.5 | Not Started
71 | Administration | Menu Management | MASTER_GRID | Medium | 0.75 | In Progress (Partial) | Not Started | 1 | Not Started |  | 1 | Not Started
72 | Administration | User Management | FLOW | High | 1 | In Progress (Partial) | Not Started | 1.5 | Not Started |  | 1.5 | Not Started
74 | Administration | Audit Trail | FLOW | Medium | 1 | In Progress (Partial) | Karthick | 1 | Not Started |  | 1 | Not Started
75 | Administration | Company Settings | Config | Medium | 1.5 | Completed | Not Started | 1.5 | Not Started |  | 1.5 | Not Started
76, 162 | Settings | Master Data (combined: Master Data + Master Data Type) | MASTER_GRID | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
77 | Settings | Grid Config (combined: Grid Config + Field master + Custom Fields) | Config | Medium | 0.75 | In Progress (Partial) | Not Started | 1 | Not Started |  | 1 | Not Started
78 | Settings | Dashboard Config (combined: Dashboard Config + Dashboard Layout + Widget cluster) | Config | Medium | 0.75 | In Progress (Partial) | Not Started | 1 | Not Started |  | 1 | Not Started
79 | Settings | Currency Management | MASTER_GRID | Medium | 0.5 | Not Started | Not Started | 0.75 | Not Started |  | 0.75 | Not Started
80 | Settings | Region Hierarchy | Config | Medium | 1 | Not Started | Not Started | 1.5 | Not Started |  | 1.5 | Not Started
81 | Settings | Document Types | MASTER_GRID | High | 0.5 | Not Started | Not Started | 0.75 | Not Started |  | 0.75 | Not Started
83 | Settings | Certificate Templates | FLOW | Medium | 0.75 | In Progress (Partial) | Not Started | 1 | Not Started |  | 1 | Not Started
84 | Settings | Email Provider Config | Config | Medium | 0.75 | In Progress (Partial) | Karthick | 1 | Not Started |  | 1 | Not Started
85, 165-166 | Settings | Organization Settings (combined: Org Settings + Setting Group + User Setting) | Config | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
86 | Settings | API Management | Config | Low | 1 | Not Started | N/A (Upcoming) | 1.5 | N/A (Upcoming) |  | 1.5 | N/A (Upcoming)
87 | Settings | Integration Marketplace | Config | Low | 1 | Not Started | N/A (Upcoming) | 1.5 | N/A (Upcoming) |  | 1.5 | N/A (Upcoming)
88 | Settings | Accounting Integration | Config | Low | 1 | Not Started | N/A (Upcoming) | 1.5 | N/A (Upcoming) |  | 1.5 | N/A (Upcoming)
89 | Settings | Social Media Integration | Config | Low | 1 | Not Started | N/A (Upcoming) | 1.5 | N/A (Upcoming) |  | 1.5 | N/A (Upcoming)
90 | AI Intelligence | Engagement Scoring | FLOW | Low | 2.5 | Not Started | Not Started | 3 | Not Started |  | 3 | Not Started
91 | AI Intelligence | Churn Prediction | FLOW | Low | 2.5 | Not Started | Not Started | 3 | Not Started |  | 3 | Not Started
92 | AI Intelligence | Action Board | FLOW | Low | 2.5 | Not Started | Not Started | 3 | Not Started |  | 3 | Not Started
93 | AI Intelligence | AI Draft | FLOW | Low | 2.5 | Not Started | N/A (Upcoming) | 3 | N/A (Upcoming) |  | 3 | N/A (Upcoming)
94 | AI Intelligence | NL Reporting | FLOW | Low | 2.5 | Not Started | N/A (Upcoming) | 3 | N/A (Upcoming) |  | 3 | N/A (Upcoming)
95 | AI Intelligence | Predictive Analytics | Dashboard | Low | 2.5 | Not Started | N/A (Upcoming) | 3 | N/A (Upcoming) |  | 3 | N/A (Upcoming)
96 | Reports | Custom Report Builder | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
97 | Reports | PowerBI Viewer | Config | Medium | 0.75 | In Progress (Partial) | Not Started | 1 | Not Started |  | 1 | Not Started
98 | Reports | Donor Retention Dashboard | Dashboard | Low | 0.75 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
99 | Reports | Report Catalog | Dashboard | Low | 0.75 | Completed | Karthick | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
100 | Reports | HTML Report Viewer | Config | Low | 1 | Completed | Karthick | 0.75 | N/A (Upcoming) |  | 0.75 | N/A (Upcoming)
101 | Reports | Scheduled Reports | Config | Low | 0.75 | Not Started | N/A (Upcoming) | 1 | N/A (Upcoming) |  | 1 | N/A (Upcoming)
102-118 | Mobile | Donor App (8 screens) + Agent App (9 screens) | Mobile | Low | — | Not Started | N/A (Upcoming) | N/A | N/A (Upcoming) |  | N/A | N/A (Upcoming)
119 | Root / Layout | Login | Auth | Medium | 0.5 | Not Started | Not Started | 0.75 | Not Started |  | 0.75 | Not Started
120 | Root / Layout | Main Dashboard | Dashboard | Medium | 1 | Not Started | Not Started | 1.5 | Not Started |  | 1.5 | Not Started
121 | Root / Layout | App Layout | Layout | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
122 | Contacts | Contact Source | MASTER_GRID | Medium | 0.5 | Completed | Karthick | 0.75 | Passed | Karthick | 0.75 | Not Started
123 | Contacts | Contact Dashboard | Dashboard | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
124 | Fundraising | Donation Dashboard | Dashboard | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
125 | Communication | Communication Dashboard | Dashboard | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
126 | Administration | Modules | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
130 | Certificate | Certificate Management (combined: Process + Print) | FLOW | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
132 | Communication | Email Keywords | MASTER_GRID | Medium | 0.5 | Not Started | Not Started | 0.75 | Not Started |  | 0.75 | Not Started
133 | Field Collection | Record Collection | FLOW | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
134 | Field Collection | Ambassador Performance | Dashboard | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
135 | Fundraising | P2P Fundraisers | FLOW | Medium | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
136 | Prayer Request | Prayer Request Entry | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
137 | Prayer Request | Reply Queue | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
138 | Prayer Request | Review Reply | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
139 | General | Bank | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
140 | General | Blood Group | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
141 | General | Currency Conversion | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
142 | General | Gender | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
143 | General | Language | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
144 | General | Occupation | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
145 | General | Payment Mode | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
146 | General | Relation | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
147 | General | Salutation | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
148 | General | City | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
149 | General | Country | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
150 | General | District | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
151 | General | Locality | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
152 | General | Pincode | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
153 | General | State | MASTER_GRID | High | 0.5 | Completed | Karthick | 0.75 | Not Started |  | 0.75 | Not Started
154 | Reports | Generate Report | FLOW | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
155 | Reports | PowerBI Reports (combined: Report Master + User Mapping) | Config | Medium | 0.5 | Not Started | Not Started | 0.75 | Not Started |  | 0.75 | Not Started
157 | Settings | SMS Setup | Config | Medium | 0.75 | Completed | Karthick | 1 | Not Started |  | 1 | Not Started
167 | Settings | Payment Gateways (combined: Per-Company + Gateway Master) | Config | Medium | 0.75 | Not Started | Not Started | 1 | Not Started |  | 1 | Not Started
169 | Settings | Event Registration Page | Config | Low | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
170 | Settings | P2P Campaign Pages | Config | Low | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
171 | Settings | Prayer Request Page | Config | Low | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
172 | Settings | Volunteer Registration Page | Config | Low | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started
173 | Settings | Crowdfunding Page | Config | Low | 1 | Completed | Karthick | 1.5 | Not Started |  | 1.5 | Not Started

## Lookups
Development Status | Testing Status | Team Members | Priority
Completed | Not Started | Karthick | High
Completed - Needs Fix | Pending | Saranya | Medium
Ready to Build | In Testing | Kavin | Low
In Progress (Partial) | Passed | Sangeetha
Not Started | Failed
Upcoming (Dashboard) | Issues Found
Upcoming (Config) | Blocked - Awaiting Fix
Upcoming (Mobile) | N/A (Upcoming)
Upcoming

## Summary
PSS 2.0 — Screen Status Summary
Generated 2026-04-28 · Total screens: 106 · Source: Screen Status sheet (live formulas)
Total | Completed | Needs Fix | In Progress | Ready to Build | Not Started | Upcoming | Dev Tested (Passed) | QA Tested (Passed)
① Development Status by Module
Module | Completed | Completed - Needs Fix | Ready to Build | In Progress (Partial) | Not Started | Upcoming (Dashboard) | Upcoming (Config) | Upcoming (Mobile) | Upcoming | Total
AI Intelligence
Administration
Case Management
Communication
Contacts
Field Collection
Fundraising
Grants
Membership
Mobile
Organization
Reports
Root / Layout
Settings
Volunteer
Total
② Testing Progress (Dev + QA)
Module | Dev: Not Started | Dev: Pending | Dev: In Testing | Dev: Passed | Dev: Failed | Dev: Issues Found | Dev: Blocked | Dev: N/A | QA: Not Started | QA: Pending | QA: In Testing | QA: Passed | QA: Failed | QA: Issues Found | QA: Blocked | QA: N/A
AI Intelligence
Administration
Case Management
Communication
Contacts
Field Collection
Fundraising
Grants
Membership
Mobile
Organization
Reports
Root / Layout
Settings
Volunteer
Total
③ Priority Breakdown
Priority | Completed | In Progress (Partial) | Other (Ready / Not Started / Upcoming) | Total
High
Medium
Low
④ Team Workload (counts ONLY when work is actually done)
Team Member | Dev Completed | Dev: Passed | Dev: Failed | Dev: Issues | Dev: Pending | QA: Passed | QA: Failed | QA: Issues | QA: Pending | Total Engaged
Karthick
Saranya
Kavin
Sangeetha